## Blockers Tracker
Case ID | Group | Area (TestRail section) | Title | Current VIU status | State | Blocker category | Who unblocks | What's needed to unblock | Related story/req | Sub-bucket
FD-WO-001 | A (WO/Parts) | Work Order — Whole-WO Fee/Discount | Verify the whole-work-order Add dialog opens from the WO toolbar more (⋯) menu at Whole Work Order scope | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | QA (case-text update) | Build deviates from spec wording/UX — update case text once the build is confirmed intended (label/copy/UX drift; see viu-qb-findings.md). | S1-R1 / S2-R9 / S2-R12 | case-update
FD-WO-002 | A (WO/Parts) | Work Order — Whole-WO Fee/Discount | Verify adding a whole-WO Flat Amount fee saves and shows the success toast | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S2-R19..R27 / S2-R29 / §7 toast | verified
FD-WO-003 | A (WO/Parts) | Work Order — Whole-WO Fee/Discount | Verify the live preview computes and displays a whole-WO percentage discount (8% of $10,715.39 → −$857.23) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S2-R31..R35 / §5-R3 | verified
FD-WO-004 | A (WO/Parts) | Work Order — Whole-WO Fee/Discount | Verify 'Apply from template' auto-fills the dialog fields with the template's values | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S2-R13 / S2-R14 | verified
FD-WO-005 | A (WO/Parts) | Work Order — Whole-WO Fee/Discount | Verify the Add button is disabled until Name, Type, Calculation type and Amount>0 are all set | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | QA (case-text update) | Build deviates from spec wording/UX — update case text once the build is confirmed intended (label/copy/UX drift; see viu-qb-findings.md). | Design §6 validateForm() / S2-N1 / S2-N2 | case-update
FD-WO-006 | A (WO/Parts) | Work Order — Whole-WO Fee/Discount | Verify Max Amount (Max cap) caps a percentage adjustment (20% fee on $100 → +$15 with Max $15) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S2-R24 / §5-R6 | verified
FD-WO-007 | A (WO/Parts) | Work Order — Whole-WO Fee/Discount | Verify the add confirm button label follows the Type (Add Fee vs Add Discount) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S2-R27 | verified
FD-WO-008 | A (WO/Parts) | Work Order — Whole-WO Fee/Discount | Verify an empty Name blocks saving a whole-WO adjustment | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S2-N1 | verified
FD-WO-009 | A (WO/Parts) | Work Order — Whole-WO Fee/Discount | Verify an empty or zero Amount blocks saving a whole-WO adjustment | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S2-N2 / §5-R1 | verified
FD-WO-010 | A (WO/Parts) | Work Order — Whole-WO Fee/Discount | Verify a percentage discount over 100% is rejected while a percentage fee has no upper limit | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | §5-R2 / S3 §3 discounts | verified
FD-WO-011 | A (WO/Parts) | Work Order — Whole-WO Fee/Discount | Verify whole-WO percentage methods resolve against the correct base (% of Subtotal example) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | §5-R4 / §5-R10 / S2-R3 | verified
FD-WO-012 | A (WO/Parts) | Work Order — Whole-WO Fee/Discount | Verify 'Add Fee / Discount' is hidden and rejected on an Invoiced or Paid work order | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S1-N1 / S3-R1b | verified
FD-WO-013 | A (WO/Parts) | Work Order — Whole-WO Fee/Discount | Verify whole-WO starting places are hidden without Work Orders: Create & Edit | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | Product Owner / Dev ruling | PO ruling — Whole-WO starting-places hidden without WO Create&Edit is FE-only (BUG-FD-3). Same FE-vs-BE ruling as FD-PERM-002. | S1-N2 / S13-R3 / S13-N2 | PO-question
FD-WO-014 | A (WO/Parts) | Work Order — Whole-WO Fee/Discount | Verify the live preview shows the empty-amount prompt before an amount is entered | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S2-R41 | verified
FD-WO-015 | A (WO/Parts) | Work Order — Whole-WO Fee/Discount | Verify the preview adjustment row is signed and colored (fee vs discount) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S2-R33 / S12-R2 | verified
FD-LABOR-001 | A (WO/Parts) | Work Order — Labor-line Fee/Discount | Verify a labor line's 3-dot menu opens the Add dialog locked to that Labor Line scope | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | QA (case-text update) | Build deviates from spec wording/UX — update case text once the build is confirmed intended (label/copy/UX drift; see viu-qb-findings.md). | S1-R3 / S2-R10 | case-update
FD-LABOR-002 | A (WO/Parts) | Work Order — Labor-line Fee/Discount | Verify a labor-line % of Labor Total fee resolves against the line's gross labor price (10% of $150.00 → +$15.00) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | §5-R4 / §5-R3 / S2-R22 | verified
FD-LABOR-003 | A (WO/Parts) | Work Order — Labor-line Fee/Discount | Verify each labor line row exposes its own 3-dot menu on hover | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S1-R2 | verified
FD-LABOR-004 | A (WO/Parts) | Work Order — Labor-line Fee/Discount | Verify a labor-line Flat Amount resolves to the exact amount with no quantity multiplier | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | §5-R14 / S2-R23 | verified
FD-LABOR-005 | A (WO/Parts) | Work Order — Labor-line Fee/Discount | Verify a labor-line adjustment resolves to $0.00 when its line is not billable (declined) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | §5-R12 | verified
FD-LABOR-006 | A (WO/Parts) | Work Order — Labor-line Fee/Discount | Verify deleting a labor line removes any adjustment pointing to it | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S3-R2 | verified
FD-LABOR-007 | A (WO/Parts) | Work Order — Labor-line Fee/Discount | Verify labor-line 'Add fee / discount' is hidden without Work Order Lines: Create & Edit | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S13-R4 / S13-N2 | verified
FD-PART-001 | A (WO/Parts) | Work Order / Parts — Part-line Fee/Discount | Verify a part's menu opens the Add dialog locked to that Part Line scope | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | QA (case-text update) | Build deviates from spec wording/UX — update case text once the build is confirmed intended (label/copy/UX drift; see viu-qb-findings.md). | S1-R4 / S1-R5 / S2-R11 | case-update
FD-PART-002 | A (WO/Parts) | Work Order / Parts — Part-line Fee/Discount | Verify a part-line Flat Amount is charged PER ITEM (amount × quantity): $5.00 × qty 3 → −$15.00 | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | §5-R14 | verified
FD-PART-003 | A (WO/Parts) | Work Order / Parts — Part-line Fee/Discount | Verify a fee/discount can be added to a requested (not-yet-received) part and shows before pick | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S1-R4 / §5-R13 | verified
FD-PART-004 | A (WO/Parts) | Work Order / Parts — Part-line Fee/Discount | Verify a part-line % of Parts Total resolves against quantity × sell price (gross) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | §5-R4 / §5-R10 / §5-R3 | verified
FD-PART-005 | A (WO/Parts) | Work Order / Parts — Part-line Fee/Discount | Verify a part-line adjustment stays attached when the part changes from requested to received | VIU-Pending | BLOCKED | BLOCKED — VIU PENDING (QA) | QA (needs cookies+seed data) | Fresh qb cookies + seeded/throwaway data; drive this built surface (parts UI flows, invoice-time walk, misc retests — see viu-qb-findings.md batch-2 backlog). | §5-R13 | reachable/needs-data
FD-PART-006 | A (WO/Parts) | Work Order / Parts — Part-line Fee/Discount | Verify a part-line adjustment resolves to $0.00 when the part is declined or returned with no quantity left | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | §5-R12 | verified
FD-PART-007 | A (WO/Parts) | Work Order / Parts — Part-line Fee/Discount | Verify deleting a part removes any adjustment pointing to it | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S3-R2 | verified
FD-PART-008 | A (WO/Parts) | Work Order / Parts — Part-line Fee/Discount | Verify per-item Flat Amount edge: quantity 1 resolves to the base amount (−$5.00) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | §5-R14 | verified
FD-INLINE-001 | A (WO/Parts) | Work Order — Inline display (Lines tab) | Verify a labor-line adjustment shows inline under its line with ↳ arrow, name, signed rate badge and grey amount | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S3-R12 / S3-R14 / S12-R3 | verified
FD-INLINE-002 | A (WO/Parts) | Work Order — Inline display (Lines tab) | Verify a part-line adjustment shows inline under its part with ↳ arrow, name, signed rate badge and grey amount | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S3-R13 / S3-R14 | verified
FD-INLINE-003 | A (WO/Parts) | Work Order — Inline display (Lines tab) | Verify a line/part with 2+ adjustments shows only the first plus a 'Show N more' toggle | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | QA (case-text update) | Build deviates from spec wording/UX — update case text once the build is confirmed intended (label/copy/UX drift; see viu-qb-findings.md). | S3-R15 / S3-R16 / S12-R6 | case-update
FD-INLINE-004 | A (WO/Parts) | Work Order — Inline display (Lines tab) | Verify the per-line Total column shows the line's gross total plus its own adjustment amounts (display only) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S3-R18 / S3-R19 | verified
FD-INLINE-005 | A (WO/Parts) | Work Order — Inline display (Lines tab) | Verify each inline adjustment row has a hover 3-dot Edit/Delete menu when the WO is open with change permission | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S3-R17 / S12-R5 | verified
FD-STATS-001 | A (WO/Parts) | Work Order — Statistics tab | Verify the Stats tab shows a 'Fees & Discounts (N)' breakdown with Value/% and Amount columns | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | Product Owner / Dev ruling | PO ruling — Stats F&D section is aggregate (Fees/Discounts/Net), not the spec's per-adjustment %+Amount rows (BUG-FD-2/FDBUG-6). PO: is aggregate the intended V1? | S4-R1 / S4-R2 / S4-R3 | PO-question
FD-STATS-002 | A (WO/Parts) | Work Order — Statistics tab | Verify each Stats F&D row shows a scope hyperlink naming its target | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | QA (case-text update) | Build deviates from spec wording/UX — update case text once the build is confirmed intended (label/copy/UX drift; see viu-qb-findings.md). | S4-R3 / design §3 | case-update
FD-STATS-003 | A (WO/Parts) | Work Order — Statistics tab | Verify the Stats F&D breakdown Total row equals the signed sum of all resolved amounts, with correct signs | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S4-R4 / S4-R6 | verified
FD-STATS-004 | A (WO/Parts) | Work Order — Statistics tab | Verify the Stats F&D rows are listed in creation order (oldest first) | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | QA (case-text update) | Build deviates from spec wording/UX — update case text once the build is confirmed intended (label/copy/UX drift; see viu-qb-findings.md). | §5-R9 | case-update
FD-STATS-005 | A (WO/Parts) | Work Order — Statistics tab | Verify the Stats 'Fees & Discounts' section is hidden when the WO has no adjustments | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S4-N1 | verified
FD-FIN-001 | A (WO/Parts) | Work Order — Financial Info card | Verify the Financial Info card shows a collapsed 'Fees & Discounts (N)' row with the net total in grey | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S3-R20 / S3-R21 / S3-R22 | verified
FD-FIN-002 | A (WO/Parts) | Work Order — Financial Info card | Verify expanding the Financial Info 'Fees & Discounts' row lists each adjustment (read-only, creation order) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S3-R23 / S3-R24 / §5-R9 | verified
FD-FIN-003 | A (WO/Parts) | Work Order — Financial Info card | Verify the Financial Info 'Fees & Discounts' row is hidden with no adjustments and the money section is hidden without See Financial Data | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S3-N2 / S3-N4 | verified
FD-FIN-004 | A (WO/Parts) | Work Order — Sidebar 'Work Order Fee / Discount' card | Verify the sidebar 'Work Order Fee / Discount' card lists whole-WO adjustments with name, signed rate badge, grey amount and hover Edit/Delete | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | QA (case-text update) | Build deviates from spec wording/UX — update case text once the build is confirmed intended (label/copy/UX drift; see viu-qb-findings.md). | S3-R3 / S3-R5 / S3-R8 / S3-R9 | case-update
FD-FIN-005 | A (WO/Parts) | Work Order — Sidebar 'Work Order Fee / Discount' card | Verify the sidebar card is hidden with no whole-WO adjustments and has no Add control | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S3-R4 / S3-R10 / S3-N1 | verified
FD-PCOL-001 | A (WO/Parts) | Parts page — 'FEES & DISCOUNTS' column | Verify the Parts page 'Fees & Discounts' column shows a single adjustment's name and rate | VIU-Blocked-NotBuilt | BLOCKED | BLOCKED — DEV NOT BUILT | Dev team | Dev deploys Story 11 — Part Sales fees/discounts (SV-73xx); then QA re-runs VIU. | S11-R10a / design §5 | Story 11 — Part Sales fees/discounts (SV-73xx)
FD-PCOL-002 | A (WO/Parts) | Parts page — 'FEES & DISCOUNTS' column | Verify the 'Fees & Discounts' column shows a '+N' badge when a part has multiple adjustments | VIU-Blocked-NotBuilt | BLOCKED | BLOCKED — DEV NOT BUILT | Dev team | Dev deploys Story 11 — Part Sales fees/discounts (SV-73xx); then QA re-runs VIU. | S11-R10b / design §5 | Story 11 — Part Sales fees/discounts (SV-73xx)
FD-PCOL-003 | A (WO/Parts) | Parts page — 'FEES & DISCOUNTS' column | Verify the 'Fees & Discounts' column shows a '+ Add' button on a part with no adjustments | VIU-Blocked-NotBuilt | BLOCKED | BLOCKED — DEV NOT BUILT | Dev team | Dev deploys Story 11 — Part Sales fees/discounts (SV-73xx); then QA re-runs VIU. | S11-R9 / design §5 | Story 11 — Part Sales fees/discounts (SV-73xx)
FD-PCOL-004 | A (WO/Parts) | Parts page — breakdown modal | Verify clicking a populated 'Fees & Discounts' cell opens the per-part breakdown modal with the correct columns | VIU-Blocked-NotBuilt | BLOCKED | BLOCKED — DEV NOT BUILT | Dev team | Dev deploys Story 11 — Part Sales fees/discounts (SV-73xx); then QA re-runs VIU. | S11-R11 / S11-R12 / S11-R13 / S11-R16 | Story 11 — Part Sales fees/discounts (SV-73xx)
FD-PCOL-005 | A (WO/Parts) | Parts page — breakdown modal | Verify the breakdown modal 'Net adjustment' row equals the signed sum of the part's adjustments | VIU-Blocked-NotBuilt | BLOCKED | BLOCKED — DEV NOT BUILT | Dev team | Dev deploys Story 11 — Part Sales fees/discounts (SV-73xx); then QA re-runs VIU. | S11-R15 | Story 11 — Part Sales fees/discounts (SV-73xx)
FD-PCOL-006 | A (WO/Parts) | Parts page — breakdown modal | Verify a per-row Remove (trash) on the breakdown modal removes the adjustment and closes the modal when the last is removed | VIU-Blocked-NotBuilt | BLOCKED | BLOCKED — DEV NOT BUILT | Dev team | Dev deploys Story 11 — Part Sales fees/discounts (SV-73xx); then QA re-runs VIU. | S11-R14 / S11-R17 | Story 11 — Part Sales fees/discounts (SV-73xx)
FD-PCOL-007 | A (WO/Parts) | Parts page — 'FEES & DISCOUNTS' column | Verify the '+ Add' button is disabled on a part when the sale/WO cannot be edited | VIU-Blocked-NotBuilt | BLOCKED | BLOCKED — DEV NOT BUILT | Dev team | Dev deploys Story 11 — Part Sales fees/discounts (SV-73xx); then QA re-runs VIU. | S11-R9 / S3-R1b | Story 11 — Part Sales fees/discounts (SV-73xx)
FD-EDIT-001 | A (WO/Parts) | Work Order — Edit an adjustment | Verify editing an adjustment allows Name/Value/Max Amount/Taxable but locks Type, Calculation type, and Scope | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S2-R4 / S2-R5 / S2-R8 | verified
FD-EDIT-002 | A (WO/Parts) | Work Order — Edit an adjustment | Verify editing re-resolves the adjustment against current totals, hides the template picker, and uses a 'Save' button | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S2-R6 / S2-R7 / S2-R18 / S2-R28 | verified
FD-EDIT-003 | A (WO/Parts) | Work Order — Edit an adjustment | Verify a save failure keeps the Edit dialog open and shows the returned error | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S2-R30 | verified
FD-REMOVE-001 | A (WO/Parts) | Work Order — Remove an adjustment | Verify removing a whole-WO adjustment shows the 'Remove Fee / Discount' confirm and a success toast | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | QA (case-text update) | Build deviates from spec wording/UX — update case text once the build is confirmed intended (label/copy/UX drift; see viu-qb-findings.md). | S3-R11a / S3-R11b / §7 | case-update
FD-REMOVE-002 | A (WO/Parts) | Work Order — Remove an adjustment | Verify removing an adjustment uses 'Create and Edit', NOT the 'Delete' permission | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S13-R7 / S13-N2 | verified
FD-REMOVE-003 | A (WO/Parts) | Work Order — Remove an adjustment | Verify removing a line-level adjustment via its inline 3-dot menu | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S3-R17 / S3-R11a | verified
FD-STACK-001 | A (WO/Parts) | Work Order — Multiple adjustments (stacking / netting) | Verify multiple adjustments on one part each resolve on the part's own base (do not compound) and net correctly | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | §5-R5 (Step 1) / S3-R15 / S11-R15 | verified
FD-STACK-002 | A (WO/Parts) | Work Order — Multiple adjustments (stacking / netting) | Verify two whole-WO percentage adjustments resolve against the same net totals and do not change each other's base | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | §5-R5 (Step 2) / spec §5 worked example | verified
FD-STACK-003 | A (WO/Parts) | Work Order — Multiple adjustments (stacking / netting) | Verify the same template can be applied to one work order more than once by hand | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | Overview 'apply same template more than once' / §3 key decisions | verified
FD-CUST-001 | B (Customer/Admin/Finance) | Customer Fees & Discounts tab | Verify the customer "Fees & Discounts (N)" tab shows the correct default count | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S9-R11 | verified
FD-CUST-002 | B (Customer/Admin/Finance) | Customer Fees & Discounts tab | Verify the "Default Fees & Discounts" card header, caption, and table columns | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S9-R12, S9-R13, S9-R14, S9-R15, S12-R8 | verified
FD-CUST-003 | B (Customer/Admin/Finance) | Customer Fees & Discounts tab | Verify adding a single template as a customer default via the picker | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | QA (case-text update) | Build deviates from spec wording/UX — update case text once the build is confirmed intended (label/copy/UX drift; see viu-qb-findings.md). | S9-R18, S9-R19, S9-R20, S9-R21, S9-R23a | case-update
FD-CUST-004 | B (Customer/Admin/Finance) | Customer Fees & Discounts tab | Verify several templates are added as customer defaults one at a time (no multi-select) | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | QA (case-text update) | Build deviates from spec wording/UX — update case text once the build is confirmed intended (label/copy/UX drift; see viu-qb-findings.md). | S9-R20, S9-R21, S9-R23a | case-update
FD-CUST-005 | B (Customer/Admin/Finance) | Customer Fees & Discounts tab | Verify the picker lists only unlinked templates and shows Processing Fee templates as type "Fee" | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | QA (case-text update) | Build deviates from spec wording/UX — update case text once the build is confirmed intended (label/copy/UX drift; see viu-qb-findings.md). | S9-R19, S8-R15, S9-R... (Processing Fee shows as "Fee") | case-update
FD-CUST-006 | B (Customer/Admin/Finance) | Customer Fees & Discounts tab | Verify the empty picker message when there are no templates left to add | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | QA (case-text update) | Build deviates from spec wording/UX — update case text once the build is confirmed intended (label/copy/UX drift; see viu-qb-findings.md). | S9-R22 | case-update
FD-CUST-007 | B (Customer/Admin/Finance) | Customer Fees & Discounts tab | Verify removing a customer default via the row's remove action needs no confirm and toasts | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | QA (case-text update) | Build deviates from spec wording/UX — update case text once the build is confirmed intended (label/copy/UX drift; see viu-qb-findings.md). | S9-R16, S9-R24 | case-update
FD-CUST-008 | B (Customer/Admin/Finance) | Customer Fees & Discounts tab | Verify the empty-state text on the Default Fees & Discounts card | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S9-R17 | verified
FD-CUST-009 | B (Customer/Admin/Finance) | Customer defaults → new work order | Verify a customer default is added as an independent adjustment on every NEW work order | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S9-R2, S9-R3, S9-R4 | verified
FD-CUST-010 | B (Customer/Admin/Finance) | Customer defaults → new work order | Verify a percentage customer default re-resolves per work order (keeps percent, not a fixed dollar) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S9-R6, S9-R7 | verified
FD-CUST-011 | B (Customer/Admin/Finance) | Customer defaults lifecycle | Verify removing a customer default does NOT change adjustments already on existing work orders | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S9-R8 | verified
FD-CUST-012 | B (Customer/Admin/Finance) | Customer defaults lifecycle | Verify deleting a template that is a customer default drops the default link but keeps existing WO adjustments | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S9-R9, S7-R4, S7-N1 | verified
FD-CUST-013 | B (Customer/Admin/Finance) | Customer defaults lifecycle | Verify deleting a customer removes that customer's default links | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S9-R10 | verified
FD-CUST-014 | B (Customer/Admin/Finance) | Customer defaults seeding | Verify a newly created customer inherits every auto-apply location template as a default | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S9-R1 | verified
FD-CUST-015 | B (Customer/Admin/Finance) | Customer Fees & Discounts tab — permissions | Verify the customer Fees & Discounts tab and controls are hidden without the required permissions | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S13-R9, S13-N3 | verified
FD-CUST-016 | B (Customer/Admin/Finance) | Customer defaults — known bug | Verify a template that is both location auto-apply AND a customer default is added only ONCE to a new WO | VIU-Verified | READY | READY (VIU-Verified) | — | Verified, but Double-add (BUG-FD-1) did NOT reproduce on batch-2 (backend dedupes) — PO to confirm the S9 fix shipped; re-scope to single adjustment. | S9 known gap (§14 item 4) | verified (PO-confirm)
FD-CUST-017 | B (Customer/Admin/Finance) | API — Customer Fees & Discounts tab — negative | Verify add/remove/load failure on customer defaults shows the standard error notification | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S9-N1 | verified
FD-TMPL-001 | B (Customer/Admin/Finance) | Template admin — location | Verify the location template library lives at Administration → Service → Fees & Discounts, below Canned Lines | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | QA (case-text update) | Build deviates from spec wording/UX — update case text once the build is confirmed intended (label/copy/UX drift; see viu-qb-findings.md). | S7-R7a, S7-R7c | case-update
FD-TMPL-002 | B (Customer/Admin/Finance) | Template admin — list | Verify the template list columns and the delete action | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S7-R8, S12-R8 | verified
FD-TMPL-003 | B (Customer/Admin/Finance) | Template admin — create | Verify creating a Fee template (dialog fields, confirm button, success toast) | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | QA (case-text update) | Build deviates from spec wording/UX — update case text once the build is confirmed intended (label/copy/UX drift; see viu-qb-findings.md). | S7-R10, S7-R12a-g, S7-R16, S7-R17, S7-R18a | case-update
FD-TMPL-004 | B (Customer/Admin/Finance) | Template admin — create | Verify creating a Discount template shows the "Discount added" toast | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | QA (case-text update) | Build deviates from spec wording/UX — update case text once the build is confirmed intended (label/copy/UX drift; see viu-qb-findings.md). | S7-R12a, S7-R18a | case-update
FD-TMPL-005 | B (Customer/Admin/Finance) | Template admin — auto-apply | Verify the auto-apply checkbox adds the template to every new WO at that location | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S7-R12g, S7-R5, S7-R6a, S7-R6b | verified
FD-TMPL-006 | B (Customer/Admin/Finance) | Template admin — edit | Verify editing a template (open by row click, "Save" button, update toast) | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | QA (case-text update) | Build deviates from spec wording/UX — update case text once the build is confirmed intended (label/copy/UX drift; see viu-qb-findings.md). | S7-R9, S7-R16, S7-R17, S7-R18b | case-update
FD-TMPL-007 | B (Customer/Admin/Finance) | Template admin — delete | Verify the template delete confirm dialog copy and buttons | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S7-R20 | verified
FD-TMPL-008 | B (Customer/Admin/Finance) | Template admin — delete | Verify the delete confirm adds a warning when the template is a default for one or more customers | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | QA (case-text update) | Build deviates from spec wording/UX — update case text once the build is confirmed intended (label/copy/UX drift; see viu-qb-findings.md). | S7-R21 | case-update
FD-TMPL-009 | B (Customer/Admin/Finance) | Template admin — delete | Verify deleting a template leaves work-order adjustments made from it unchanged | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S7-N1, S7-R4 | verified
FD-TMPL-010 | B (Customer/Admin/Finance) | Template admin — scoping | Verify template scoping — labour-method templates only appear in labour modals, parts-method only in parts modals | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | QA (case-text update) | Build deviates from spec wording/UX — update case text once the build is confirmed intended (label/copy/UX drift; see viu-qb-findings.md). | S2-R14, S2-R15, S2-R16, S5-R10 | case-update
FD-TMPL-011 | B (Customer/Admin/Finance) | Template admin — dialog fields | Verify Max Amount appears only for percentage methods and 0 is treated as empty | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | QA (case-text update) | Build deviates from spec wording/UX — update case text once the build is confirmed intended (label/copy/UX drift; see viu-qb-findings.md). | S7-R12e, S7-R14, §5-R6 | case-update
FD-TMPL-012 | B (Customer/Admin/Finance) | Template admin — list | Verify the template list empty-state message | VIU-Blocked-Env | BLOCKED | BLOCKED — ENV | QA env | Environment window — shared env: cannot empty the location's template library (real templates in use). | S7-R11 | flag-off/env
FD-TMPL-013 | B (Customer/Admin/Finance) | Template admin — validation | Verify a percentage-discount template is capped at 100% while a percentage-fee template is uncapped | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S7-R3, §5-R2 | verified
FD-TMPL-014 | B (Customer/Admin/Finance) | Template admin — dialog fields | Verify a Fee/Discount template offers the four whole-WO methods and no scope field | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S7-R2, S7-R13, S7-R15 | verified
FD-TMPL-015 | B (Customer/Admin/Finance) | Template admin — negative | Verify the template save-failure toast | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S7-R19 | verified
FD-TMPL-016 | B (Customer/Admin/Finance) | Template admin — permissions | Verify the admin Fees & Discounts page is gated by Settings → Finance | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S13-R8, S7-R7b | verified
FD-TMPL-017 | B (Customer/Admin/Finance) | Template admin — dialog fields | Verify template Name enforces the 100-character limit | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S7-R12c | verified
FD-PROC-001 | B (Customer/Admin/Finance) | Processing Fee — template builder | Verify "Processing Fee" is a third type in the template builder (template-only) | VIU-Blocked-NotBuilt | BLOCKED | BLOCKED — DEV NOT BUILT | Dev team | Dev deploys Story 8 — Processing-Fee builder UI (SV-73xx); then QA re-runs VIU. | S8-R1, S8-R3, S7-R12a | Story 8 — Processing-Fee builder UI (SV-73xx)
FD-PROC-002 | B (Customer/Admin/Finance) | Processing Fee — methods | Verify a Processing Fee offers only Flat Amount (default) and % of Grand Total, with a tax-inclusive base | VIU-Blocked-NotBuilt | BLOCKED | BLOCKED — DEV NOT BUILT | Dev team | Dev deploys Story 8 — Processing-Fee builder UI (SV-73xx); then QA re-runs VIU. | S8-R5, S8-R6, S8-R9, §5-R4, §5-R10 | Story 8 — Processing-Fee builder UI (SV-73xx)
FD-PROC-003 | B (Customer/Admin/Finance) | Processing Fee — no Max Amount | Verify the Max Amount field is hidden for every Processing Fee (both methods) | VIU-Blocked-NotBuilt | BLOCKED | BLOCKED — DEV NOT BUILT | Dev team | Dev deploys Story 8 — Processing-Fee builder UI (SV-73xx); then QA re-runs VIU. | S8-R10, S8-N3, S7-R12e | Story 8 — Processing-Fee builder UI (SV-73xx)
FD-PROC-004 | B (Customer/Admin/Finance) | Processing Fee — taxable + legal disclosure | Verify the Processing Fee Taxable control defaults Yes and renders the legal disclosure | VIU-Blocked-NotBuilt | BLOCKED | BLOCKED — DEV NOT BUILT | Dev team | Dev deploys Story 8 — Processing-Fee builder UI (SV-73xx); then QA re-runs VIU. | S8-R11, S8-R12 | Story 8 — Processing-Fee builder UI (SV-73xx)
FD-PROC-005 | B (Customer/Admin/Finance) | Processing Fee — no manual add | Verify a Processing Fee cannot be added to a work order by hand | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S8-R16, S8-N1, S8-N2 | verified
FD-PROC-006 | B (Customer/Admin/Finance) | Processing Fee — auto-apply | Verify a Processing Fee reaches a new work order via location auto-apply | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S8-R14, S7-R5 | verified
FD-PROC-007 | B (Customer/Admin/Finance) | Processing Fee — customer default | Verify a Processing Fee reaches a new work order via a customer default | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S8-R15, S9-R2 | verified
FD-PROC-008 | B (Customer/Admin/Finance) | Processing Fee — WO behavior | Verify a Processing Fee on a WO can be removed but not edited | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | QA (case-text update) | Build deviates from spec wording/UX — update case text once the build is confirmed intended (label/copy/UX drift; see viu-qb-findings.md). | S8-R17, S8-N5, S3-R9 | case-update
FD-PROC-009 | B (Customer/Admin/Finance) | Processing Fee — calculation | Verify a % of Grand Total Processing Fee resolves last on a tax-inclusive base (3% of $324 → +$9.72) | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | Dev team | Dev fix — FDBUG-2 — processing-fee Grand-Total base wrongly includes whole-WO fees + their tax. | S8-R5, §5-R4, §5-R5 (Step 3) | code-bug
FD-PROC-010 | B (Customer/Admin/Finance) | API — Processing Fee — negative | Verify a Processing Fee with a Max Amount or a disallowed method is rejected | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S8-N4 | verified
FD-PROC-011 | B (Customer/Admin/Finance) | Processing Fee — sign | Verify a Processing Fee always adds to the total (never a discount) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S8-R2 | verified
FD-PROC-012 | B (Customer/Admin/Finance) | Processing Fee — template edit independence | Verify editing a Processing Fee template does not change Processing Fees already on existing WOs | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S8-R18, S8-R19 | verified
FD-PROC-013 | B (Customer/Admin/Finance) | Processing Fee — calculation edge | Verify multiple Processing Fees each exclude ALL Processing Fees' amounts and tax from the shared base | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | §5-R4 (multiple Processing Fees) | verified
FD-PROC-014 | B (Customer/Admin/Finance) | Processing Fee — negative | Verify the system rejects a Processing Fee carrying a minimum amount | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S8-N6 | verified
FD-DOC-001 | B (Customer/Admin/Finance) | Customer document (estimate/invoice) | Verify one layout renders adjustments on both the estimate and the invoice | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S5-R1 | verified
FD-DOC-002 | B (Customer/Admin/Finance) | Customer document — per-line adjustments | Verify a labor-line percentage adjustment renders indented with ↳, the "(% of labor)" phrase, and correct amount sign | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S5-R2, S5-R3, S5-R4, S12-R3 | verified
FD-DOC-003 | B (Customer/Admin/Finance) | Customer document — per-line adjustments | Verify a part-line adjustment renders with "(% of parts)" (percentage) and no phrase for Flat Amount | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S5-R2, S5-R3 | verified
FD-DOC-004 | B (Customer/Admin/Finance) | Customer document — amount format | Verify fee vs discount amount formatting (fee "$X.XX", discount "($X.XX)") | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S5-R4, S5-R9, S12-R7 | verified
FD-DOC-005 | B (Customer/Admin/Finance) | Customer document — Adjustments block | Verify the bottom "Adjustments" block lists whole-WO adjustments one by one in creation order | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S5-R5, S5-R6 | verified
FD-DOC-006 | B (Customer/Admin/Finance) | Customer document — Adjustments block | Verify line-level adjustments are grouped by name+type in the bottom block with a "(×N)" count | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S5-R7, S5-R8 | verified
FD-DOC-007 | B (Customer/Admin/Finance) | Customer document — Processing Fee phrase | Verify a % of Grand Total Processing Fee shows the "% of grand total" phrase on the document | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S5-R6, S8-R22 | verified
FD-DOC-008 | B (Customer/Admin/Finance) | Customer document — Shop Supplies (S14) | Verify Shop Supplies is hidden on the estimate/invoice/financial tab when the total is $0.00 | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S14-R1 | verified
FD-DOC-009 | B (Customer/Admin/Finance) | Customer document — Shop Supplies (S14) | Verify Shop Supplies reappears on the customer views when its total becomes greater than $0.00 | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S14-R2 | verified
FD-DOC-010 | B (Customer/Admin/Finance) | Customer document — line-level $0 target | Verify a line-level adjustment on a not-billable (declined) line resolves to $0.00 but still shows | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | §5-R12 | verified
FD-DOC-011 | B (Customer/Admin/Finance) | Customer document — layout | Verify the Adjustments block sits after Labor/Parts/Shop Supplies and before Subtotal → Tax → Total | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | Dev team | Dev fix — FDBUG-1 (MAJOR) — WO/estimate Subtotal/Total exclude adjustments while GST taxes them. | S5-R5 | code-bug
FD-QB-001 | B (Customer/Admin/Finance) | QuickBooks sync | Verify each fee/discount exports to QuickBooks as its own invoice line item (fee +, discount −) | VIU-Blocked-Env | BLOCKED | BLOCKED — ENV | Dev / QA env | QuickBooks integration not present on qb env (Story 6). Needs a QB-connected env or dev/QB-side inspection. | S6-R1 | quickbooks
FD-QB-002 | B (Customer/Admin/Finance) | QuickBooks sync | Verify the QuickBooks line description equals the adjustment name and the item is the mapped Fee/Discount item | VIU-Blocked-Env | BLOCKED | BLOCKED — ENV | Dev / QA env | QuickBooks integration not present on qb env (Story 6). Needs a QB-connected env or dev/QB-side inspection. | S6-R3, S6-R5 | quickbooks
FD-QB-003 | B (Customer/Admin/Finance) | QuickBooks sync — edge | Verify a $0.00 resolved adjustment is skipped when sent to QuickBooks | VIU-Blocked-Env | BLOCKED | BLOCKED — ENV | Dev / QA env | QuickBooks integration not present on qb env (Story 6). Needs a QB-connected env or dev/QB-side inspection. | S6-R1, §5-R8 | quickbooks
FD-QB-004 | B (Customer/Admin/Finance) | QuickBooks — mapping guard | Verify adding a fee is blocked when the Fee item is unmapped (exact message) | VIU-Blocked-Env | BLOCKED | BLOCKED — ENV | Dev / QA env | QuickBooks integration not present on qb env (Story 6). Needs a QB-connected env or dev/QB-side inspection. | S6-R6, S6-R6a, S6-R6d | quickbooks
FD-QB-005 | B (Customer/Admin/Finance) | QuickBooks — mapping guard | Verify adding a discount is blocked when the Discount item is unmapped (exact message) | VIU-Blocked-Env | BLOCKED | BLOCKED — ENV | Dev / QA env | QuickBooks integration not present on qb env (Story 6). Needs a QB-connected env or dev/QB-side inspection. | S6-R6, S6-R6d | quickbooks
FD-QB-006 | B (Customer/Admin/Finance) | QuickBooks — mapping guard scope | Verify the mapping guard blocks adds on every add surface (WO, labor line, part, part sale, template-apply) | VIU-Blocked-Env | BLOCKED | BLOCKED — ENV | Dev / QA env | QuickBooks integration not present on qb env (Story 6). Needs a QB-connected env or dev/QB-side inspection. | S6-R6a | quickbooks
FD-QB-007 | B (Customer/Admin/Finance) | QuickBooks — mapping guard (auto-apply) | Verify an auto-apply default cannot be saved while the matching QuickBooks item is unmapped | VIU-Blocked-Env | BLOCKED | BLOCKED — ENV | Dev / QA env | QuickBooks integration not present on qb env (Story 6). Needs a QB-connected env or dev/QB-side inspection. | S6-R6b | quickbooks
FD-QB-008 | B (Customer/Admin/Finance) | QuickBooks — mapping guard exceptions | Verify creating/editing a non-auto-apply template is always allowed and no block exists when QuickBooks is not connected | VIU-Blocked-Env | BLOCKED | BLOCKED — ENV | Dev / QA env | QuickBooks integration not present on qb env (Story 6). Needs a QB-connected env or dev/QB-side inspection. | S6-R6c | quickbooks
FD-QB-009 | B (Customer/Admin/Finance) | QuickBooks — unmap recovery | Verify unmapping an in-use item routes affected invoices to Unexported Items (recoverable, no data lost) | VIU-Blocked-Env | BLOCKED | BLOCKED — ENV | Dev / QA env | QuickBooks integration not present on qb env (Story 6). Needs a QB-connected env or dev/QB-side inspection. | S6-R7, S6-R7a | quickbooks
FD-QB-010 | B (Customer/Admin/Finance) | QuickBooks — Class | Verify a single QuickBooks Class applies to every synced line including fee/discount lines | VIU-Blocked-Env | BLOCKED | BLOCKED — ENV | Dev / QA env | QuickBooks integration not present on qb env (Story 6). Needs a QB-connected env or dev/QB-side inspection. | S6-R8 | quickbooks
FD-QB-011 | B (Customer/Admin/Finance) | QuickBooks — Class validation | Verify a deleted/deactivated Class aborts the entire invoice sync (no substitution) | VIU-Blocked-Env | BLOCKED | BLOCKED — ENV | Dev / QA env | QuickBooks integration not present on qb env (Story 6). Needs a QB-connected env or dev/QB-side inspection. | S6-R9 | quickbooks
FD-QB-012 | B (Customer/Admin/Finance) | QuickBooks — negative totals | Verify the net subtotal floors at $0.00 with the $100/$10/$150 worked example (non-taxable vs taxable discount) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S6-R10, S6-R10a, S6-R10b, S6-R10c | verified
FD-QB-013 | B (Customer/Admin/Finance) | QuickBooks — negative totals | Verify discount lines to QuickBooks are capped with largest-remainder whole-cent penny allocation | VIU-Blocked-Env | BLOCKED | BLOCKED — ENV | Dev / QA env | QuickBooks integration not present on qb env (Story 6). Needs a QB-connected env or dev/QB-side inspection. | S6-R10d | quickbooks
FD-QB-014 | B (Customer/Admin/Finance) | QuickBooks — negative totals | Verify a mandatory warn/confirm before saving when discounts exceed the net subtotal | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | QA (case-text update) | Build deviates from spec wording/UX — update case text once the build is confirmed intended (label/copy/UX drift; see viu-qb-findings.md). | S6-R12 | case-update
FD-QB-015 | B (Customer/Admin/Finance) | QuickBooks — negative totals | Verify the excess is recorded as a customer credit and posts to QuickBooks as a tax-exempt goodwill credit memo | VIU-Pending | BLOCKED | BLOCKED — VIU PENDING (QA) | QA (needs cookies+seed data) | Fresh qb cookies + seeded/throwaway data; drive this built surface (parts UI flows, invoice-time walk, misc retests — see viu-qb-findings.md batch-2 backlog). | S6-R11, S6-R13 | reachable/needs-data
FD-QB-016 | B (Customer/Admin/Finance) | QuickBooks sync — tax | Verify a synced line's tax follows the adjustment's taxable setting | VIU-Blocked-Env | BLOCKED | BLOCKED — ENV | Dev / QA env | QuickBooks integration not present on qb env (Story 6). Needs a QB-connected env or dev/QB-side inspection. | S6-R2, §5-R11 | quickbooks
FD-HIST-001 | B (Customer/Admin/Finance) | History log | Verify one history entry per add/edit/remove with the correct bold event labels | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | Dev team | Dev fix — FDBUG-3 — auto-applied adjustments write NO history-log entry. | S10-R2, S10-R4a, S10-R4b, S10-R4c | code-bug
FD-HIST-002 | B (Customer/Admin/Finance) | History log | Verify the history detail block shows Name, Type, Amount (set rate), and Applied-to label | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | QA (case-text update) | Build deviates from spec wording/UX — update case text once the build is confirmed intended (label/copy/UX drift; see viu-qb-findings.md). | S10-R6a, S10-R6b, S10-R6c, S10-R6d | case-update
FD-HIST-003 | B (Customer/Admin/Finance) | History log | Verify an adjustment entry leaves the saved-state icon empty and the Line column shows "−" | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S10-R3, S10-R5 | verified
FD-HIST-004 | B (Customer/Admin/Finance) | History log — visibility | Verify fee/discount history stays visible when the F&D UI is hidden by the feature flag | VIU-Blocked-Env | BLOCKED | BLOCKED — ENV | QA env | Environment window — flag-off history visibility (org flag toggle skipped on shared env). | S10-R1 | flag-off/env
FD-HIST-005 | B (Customer/Admin/Finance) | History log — visibility | Verify F&D history stays visible when the F&D UI is hidden by See Financial Data being off | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S10-R1, S10-R6c, S13-R10 | verified
FD-HIST-006 | B (Customer/Admin/Finance) | History log — permission | Verify fee/discount history entries are gated by the View History Logs permission | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S13-R10 | verified
FD-HIST-007 | B (Customer/Admin/Finance) | History log — Processing Fee | Verify a Processing Fee is logged as a fee with "Full invoice" applied-to and no "updated" entry | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | QA (case-text update) | Build deviates from spec wording/UX — update case text once the build is confirmed intended (label/copy/UX drift; see viu-qb-findings.md). | S8-R25, S8-R26, S10 (Processing Fee note) | case-update
FD-HIST-008 | B (Customer/Admin/Finance) | History log — edit entry | Verify an edit that changes the rate records the new set rate (not the resolved total) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S10-R6c, S2-R6 | verified
FD-CALC-001 | C (Calc/Perms/Validation) | Calculation contract | Verify a percentage adjustment resolves as base × percent (10% fee on $150.00 → +$15.00) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | §5-R3 | verified
FD-CALC-002 | C (Calc/Perms/Validation) | Calculation contract | Verify percentage rounding — half a cent or more rounds UP (5% discount on $33.33 → $1.6665 → −$1.67) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | §5-R3 | verified
FD-CALC-003 | C (Calc/Perms/Validation) | Calculation contract | Verify a Flat Amount on Whole-WO or Labor Line resolves to the set amount exactly (no quantity multiplier) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | §5-R14 | verified
FD-CALC-004 | C (Calc/Perms/Validation) | Calculation contract | Verify a Flat Amount on a Part Line is PER ITEM (amount × quantity: $5.00 × qty 3 → −$15.00; qty 1 → −$5.00) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | §5-R14 | verified
FD-CALC-005 | C (Calc/Perms/Validation) | Calculation contract | Verify a percentage discount cannot exceed 100% (fee percentages have no upper limit) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | §5-R2 | verified
FD-CALC-006 | C (Calc/Perms/Validation) | Calculation contract | Verify minimum values — Flat Amount smallest is $0.01, Percentage smallest is 0.01% | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | Dev team | Dev fix — FDBUG-10 — percent below minimum silently coerced up instead of rejected. | §5-R1 | code-bug
FD-CALC-007 | C (Calc/Perms/Validation) | Calculation contract | Verify Max Amount clamps a percentage result (20% fee on $100 → $20 → Max $15 → +$15.00) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | §5-R6 | verified
FD-CALC-008 | C (Calc/Perms/Validation) | Calculation contract | Verify Max Amount = $0 forces resolve to $0.00, while blank/empty Max Amount means no cap | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | Dev team | Dev fix — FDBUG-9 — maxCap 0 accepted and treated as NO cap (should force $0.00). | §5-R6 | code-bug
FD-CALC-009 | C (Calc/Perms/Validation) | Calculation contract | Verify a $0.00 base resolves to $0.00 and the $0.00 line is skipped in QuickBooks (still shown on screens) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | §5-R8 | verified
FD-CALC-010 | C (Calc/Perms/Validation) | Calculation contract | Verify a negative base is treated as $0 (resolved amount = $0.00, base never goes below zero) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | §5-R3, §5-R4 | verified
FD-CALC-011 | C (Calc/Perms/Validation) | Calculation contract | Verify a taxable fee raises the taxable amount, a taxable discount lowers it, and a non-taxable adjustment does not change tax | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | §5-R11 | verified
FD-CALC-012 | C (Calc/Perms/Validation) | Calculation contract | Verify the 3-step resolution ORDER — line-level on gross first, whole-WO on net second, no stacking within a step | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | §5-R5 | verified
FD-CALC-013 | C (Calc/Perms/Validation) | Calculation contract | Verify a Processing Fee resolves LAST on the tax-inclusive Grand Total (3% of $324 → +$9.72) | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | Dev team | Dev fix — FDBUG-2 — processing-fee base includes whole-WO adjustments. | §5-R4, §5-R5 | code-bug
FD-CALC-014 | C (Calc/Perms/Validation) | Calculation contract | Verify the Processing Fee base includes tax on purpose and never uses a Max Amount | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | §5-R4, S8-R10 | verified
FD-CALC-015 | C (Calc/Perms/Validation) | Calculation contract | Verify negative-total floor at $0.00 — non-taxable $150 discount on $100 parts + $10 tax: subtotal floors, customer pays $10, $50 excess → tax-exempt goodwill credit | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S6-R10, S6-R11, S6-R12, S6-R13 | verified
FD-CALC-016 | C (Calc/Perms/Validation) | Calculation contract | Verify a TAXABLE $150 discount on $100 parts drives the taxable amount to $0 → tax $0.00, customer pays $0.00 | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S6-R10c | verified
FD-CALC-017 | C (Calc/Perms/Validation) | Calculation contract | Verify multiple discount lines are penny-capped via largest-remainder so capped discounts sum exactly to the floored net subtotal (no negative, whole-cent) | VIU-Blocked-Env | BLOCKED | BLOCKED — ENV | QA env | Environment window — environment limitation on the shared qb env. | S6-R10d | flag-off/env
FD-PERM-001 | C (Calc/Perms/Validation) | Permissions (Story 13) | Verify See Financial Data gates ALL fee/discount dollar amounts everywhere (without SFD, amounts are hidden) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S13-R2, S13-N1 | verified
FD-PERM-002 | C (Calc/Perms/Validation) | Permissions (Story 13) | Verify Whole-WO adjustment add/edit/remove requires Work Orders: Create and Edit | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | Product Owner / Dev ruling | PO ruling — Whole-WO adjustment add/edit/remove is FE-only at the BE (tech got 201) (BUG-FD-3). PO/dev: should whole-WO writes be BE-enforced for V1? | S13-R3 | PO-question
FD-PERM-003 | C (Calc/Perms/Validation) | Permissions (Story 13) | Verify Labor-line and Part-line adjustment add/edit/remove requires Work Order Lines: Create and Edit | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S13-R4 | verified
FD-PERM-004 | C (Calc/Perms/Validation) | Permissions (Story 13) | Verify Part-Sale part adjustment add/edit/remove requires Part Sales: Create and Edit | VIU-Blocked-NotBuilt | BLOCKED | BLOCKED — DEV NOT BUILT | Dev team | Dev deploys Story 11 — Part Sales fees/discounts (SV-73xx); then QA re-runs VIU. | S13-R5 | Story 11 — Part Sales fees/discounts (SV-73xx)
FD-PERM-005 | C (Calc/Perms/Validation) | Permissions (Story 13) | Verify any add/edit/remove of an adjustment also requires See Financial Data to be ON | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S13-R6 | verified
FD-PERM-006 | C (Calc/Perms/Validation) | Permissions (Story 13) | Verify REMOVING an adjustment is governed by "Create and Edit", NOT the separate "Delete" permission | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S13-R7 | verified
FD-PERM-007 | C (Calc/Perms/Validation) | Permissions (Story 13) | Verify create/edit/delete of an adjustment TEMPLATE requires Settings → Finance | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S13-R8 | verified
FD-PERM-008 | C (Calc/Perms/Validation) | Permissions (Story 13) | Verify viewing/changing a customer's default fees & discounts requires BOTH Customer Management: Create and Edit AND Manage Accounts Payable and Receivable | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S13-R9, S13-N3 | verified
FD-PERM-009 | C (Calc/Perms/Validation) | Permissions (Story 13) | Verify seeing fee/discount entries in the WO history log requires View History Logs (and stays visible even when F&D UI is hidden) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S13-R10 | verified
FD-PERM-010 | C (Calc/Perms/Validation) | Permissions (Story 13) | Verify BOTH gates are required — the FeesAndDiscounts flag ON AND the matching permission | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S13-R1, feature flag + permission (both gates) | verified
FD-PERM-011 | C (Calc/Perms/Validation) | Permissions (Story 13) | Verify add/edit/remove is blocked when the WO is Invoiced/Paid or the user is in history mode | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S1-N1, S3-R1b, S3-R1a | verified
FD-FLAG-001 | C (Calc/Perms/Validation) | Feature-flag gating | Verify with the FeesAndDiscounts flag OFF, all F&D UI and behavior are hidden everywhere | VIU-Blocked-Env | BLOCKED | BLOCKED — ENV | QA env | Environment window — flag-off window (org-level FeesAndDiscounts toggle skipped on shared env). | §1 feature flag, S13-R1 | flag-off/env
FD-FLAG-002 | C (Calc/Perms/Validation) | Feature-flag gating | Verify the WO history log STILL shows fee/discount entries even when the feature flag is OFF | VIU-Blocked-Env | BLOCKED | BLOCKED — ENV | QA env | Environment window — flag-off exception (history log visible with flag off). | S10-R1 (flag-off exception) | flag-off/env
FD-FLAG-003 | C (Calc/Perms/Validation) | Feature-flag gating | Verify with the flag ON, the matching permission is still required to use F&D | VIU-Blocked-Env | BLOCKED | BLOCKED — ENV | QA env | Environment window — flag ON + permission-required interaction (flag-side complement). | §1 feature flag + S13-R1 | flag-off/env
FD-VAL-001 | C (Calc/Perms/Validation) | Validation / Edge | Verify the Add button stays DISABLED until Name AND Type AND Calculation type AND Amount > 0 are all set | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | QA (case-text update) | Build deviates from spec wording/UX — update case text once the build is confirmed intended (label/copy/UX drift; see viu-qb-findings.md). | design §6 (Add-button enable rule); S2-N1, S2-N2 | case-update
FD-VAL-002 | C (Calc/Perms/Validation) | Validation / Edge | Verify a blank or 0 Amount/Percent blocks save with an inline error | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S2-N2, §5-R1 | verified
FD-VAL-003 | C (Calc/Perms/Validation) | Validation / Edge | Verify an empty Name blocks save with an inline error (Name required, up to 100 characters) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S2-N1, S2-R19 | verified
FD-VAL-004 | C (Calc/Perms/Validation) | Validation / Edge | Verify a percentage discount > 100% is invalid while a percentage fee has no upper cap | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | §5-R2 | verified
FD-VAL-005 | C (Calc/Perms/Validation) | Validation / Edge | Verify negative Amount/Percent values are rejected (values must be > 0) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | §5-R1 | verified
FD-VAL-006 | C (Calc/Perms/Validation) | Validation / Edge | Verify Max cap edge behavior — 0 or empty = no maximum, and Max Amount shows only for percentage methods | VIU-Deviation | BLOCKED | BLOCKED — DEVIATION | Dev team | Dev fix — FDBUG-9 — maxCap 0 not treated as empty/never-sent. | §5-R6, S2-R24, S2-R25 | code-bug
FD-VAL-007 | C (Calc/Perms/Validation) | Validation / Edge | Verify a template that is BOTH location auto-apply and a customer default yields ONE adjustment on a new WO | VIU-Verified | READY | READY (VIU-Verified) | — | Verified, but Double-add (BUG-FD-1) not reproduced — PO to confirm fixed. | S9 known gap (auto-apply + customer-default duplication); S7-R5, S9-R2 | verified (PO-confirm)

## Summary
Fees & Discounts V1 — Blockers Tracker · Summary
Total authored cases | 182
Blocker category | Count | Owner
READY (VIU-Verified) | 113 | — (ready to upload)
BLOCKED — DEVIATION | 36 | Dev fix / PO ruling / QA case-update
BLOCKED — DEV NOT BUILT | 12 | Dev team (Stories 8 & 11)
BLOCKED — ENV | 19 | Dev / QA env (QuickBooks, flag-off)
BLOCKED — NEEDS-ACCOUNT | 0 | QA (restricted-role session)
BLOCKED — VIU PENDING (QA) | 2 | QA (fresh cookies + seed data)
TOTAL | 182
By authoring group | Count
A (WO/Parts) | 61
B (Customer/Admin/Finance) | 83
C (Calc/Perms/Validation) | 38
DEVIATION — by sub-bucket | Count
code-bug | 7
PO-question | 3
case-update | 26
DEV NOT BUILT — by story | Count
Story 11 — Part Sales fees/discounts (SV-73xx) | 8
Story 8 — Processing-Fee builder UI (SV-73xx) | 4
ENV — by sub-bucket | Count
quickbooks | 13
flag-off/env | 6
WHAT TO SEND ME NEXT (to unblock each batch)
• Fresh qb QA cookies (admin; tech quick-login is FLAKY — retest each run) | unblocks the 2 VIU-PENDING cases (parts UI flows, invoice-time walk, retests) AND — via the self-service staff role-switch — the 0 NEEDS-ACCOUNT Story-13 per-role negatives.
• Dev deploys Story 8 (Processing-Fee builder UI) + Story 11 (Part Sales fees/discounts) | unblocks the 12 DEV-NOT-BUILT cases (Story 8 = 4, Story 11 = 8); then QA re-runs VIU.
• A QuickBooks-connected env (or dev/QB-side inspection) for Story 6 | unblocks the 13 QuickBooks ENV cases (mapping guard, sync, negative-total credit memo).
• A flag-off maintenance window on a non-shared env | unblocks the 6 flag-off/shared-env cases (FD-FLAG-001/002/003, FD-HIST-004, FD-TMPL-012).
• PO/dev rulings on the deviations + double-add + NOTE-FD-4 | finalizes the 3 PO-question deviations (Stats layout, whole-WO FE-vs-BE enforcement), the double-add confirmation (FD-CUST-016/FD-VAL-007), and NOTE-FD-4 (BE accepts processing_fee). Dev fixes finalize the 7 code-bug deviations; QA updates the 26 copy/UX-drift deviations once the build is confirmed intended.
• Restricted-role accounts (or confirmation the self-service staff role-switch is usable on qb) | unblocks the 0 NEEDS-ACCOUNT Story-13 per-role negatives (restore Tech afterward).