## Change list
Report Suite - spec-relevance reconciliation change list (2026-07-28)
515 cases total. 2 edited now (green). The rest need a decision or await Chris's spec update / a live-build check - listed below. All other cases are clean (no change needed now). NO TestRail writes this pass.
Legend: APPLIED-NOW = edited locally this pass (firmly confirmed). PENDING-CHRIS = video intent the current spec still contradicts - not edited, awaiting Chris's spec update. OPEN-DECISION = not settled on the call. LIVE-VIU-PENDING = needs the live QA build to confirm (no QA branch yet).
Internal ID | TestRail Case ID | TestRail link | Report | Driving source | Classification | What needs to be done (plain)
SBR-DEACT-04 | C30255 | https://shopview.testrail.io/index.php?/cases/view/30255 | SBR | PO answer Q1 = B (overrides spec S13-R8) | APPLIED-NOW | DONE THIS PASS. Reworded so pressing the Esc key does NOT close the 'deactivate a sales rep' confirm pop-up - only the Cancel button and the X icon close it (matches Chris's answer and the app's house rule that pop-ups do not close on Esc). Long title shortened to fit. Still to be confirmed live on the QA branch.
SBR-DEACT-05 | C30256 | https://shopview.testrail.io/index.php?/cases/view/30256 | SBR | PO answer Q1 = B (consistency) | APPLIED-NOW | DONE THIS PASS. Small consistency fix: made clear the Esc key never closes this dialog at any time (aligns with the case above). Overlong title shortened. Confirm live.
SBC-LBL-01 | C30134 | https://shopview.testrail.io/index.php?/cases/view/30134 | SBC | Video P24 - serial-number identifier | PENDING-CHRIS | If Chris ratifies it, change the asset label to use the SERIAL NUMBER (bin number) as the identifier instead of Unit -> plate -> VIN. NOT changed yet: the current written spec (S8-R8 '· Unit {unit}') still uses the unit number, and Chris said he will 'double-check the spec' first. Also touches SBC-LBL-02 C30135, SBC-LBL-03 C30136, SBC-LBL-04 C30137.
WIP-COL-05 | C30470 | https://shopview.testrail.io/index.php?/cases/view/30470 | WIP | Video P24 - serial-number identifier | PENDING-CHRIS | Same serial-number change for the Work In Progress Asset cell (currently the unit number over the VIN, per spec S4-R7). NOT changed yet - awaiting Chris's spec update. Also touches WIP-FLT-03 C30500, WIP-SORT-03 C30485, WIP-EXP-07 C30516.
SBC-EXP-01 | C30159 | https://shopview.testrail.io/index.php?/cases/view/30159 | SBC | Video P25 - remove SBC Print | PENDING-CHRIS | If Chris cuts Print from the spec, remove the 'Print' item from the report's overflow (three-dot) menu. NOT changed yet: the current spec (Story 16) still includes Print; Chris said 'this should not exist... I'm going to make sure that's cut out of the spec.'
SBC-EXP-13 | C30171 | https://shopview.testrail.io/index.php?/cases/view/30171 | SBC | Video P25 - remove SBC Print | PENDING-CHRIS | Retire the SBC Print-behavior case once Print is cut from the spec. NOT changed yet. Print is also referenced in the empty-state export case SBC-EXP-15 C30173.
(new - to author) |  |  | SBC | Video P21 - add compressed download | PENDING-CHRIS | Chris agreed live to ADD a compressed/summary download to Sales By Customer, alongside the existing expanded (nested) download - like the other reports' Summary/Expanded split. NOT authored yet: the current spec has only the single flat export. Author a new export case once the spec adds it.
SBC-LOC-03 | C30111 | https://shopview.testrail.io/index.php?/cases/view/30111 | SBC | Video P10 - per-row location label | PENDING-CHRIS | When 'All locations' is selected, add a per-row (or per-section) location label so a user can tell which shop each row belongs to. NOT added yet on the five non-WIP reports; add once the spec calls for it. Work In Progress already has a Location column. Also affects SBR-LOC-03 C30215, PV-FILT-10 C30337, TU-LOC-01 C30442, IV-LOC-01 C30574 - likely a new case per report.
PV-FILT-01 | C30328 | https://shopview.testrail.io/index.php?/cases/view/30328 | PV | Video P31 - Catalogue rename | PENDING-CHRIS | If Chris renames/truncates 'Catalogue' (it means special-order parts never stocked), update the Type filter option, the Type column value, and the tooltips to the new label. NOT changed yet - the rename is not decided and the current spec still says 'Catalogue'. Also touches PV-FILT-09 C30336, PV-ROW-05 C30345, PV-EXP-08 C30382.
SBR-LOC-04 | C30216 | https://shopview.testrail.io/index.php?/cases/view/30216 | SBR | Video P33 - hide location filter when <=1 location | PENDING-CHRIS | Chris's intent: HIDE the Location filter when a user can access only one location, SHOW it when they can access two or more. This case currently says the OPPOSITE (a one-location user STILL sees the filter, spec S21-N1) straight from the current spec. Do NOT change until Chris updates the spec - the written spec directly contradicts the video here. Ties to the Q2 permission question.
TU-LOC-05 | C30446 | https://shopview.testrail.io/index.php?/cases/view/30446 | TU | Video P33 - hide location filter when <=1 location | PENDING-CHRIS | Same location-filter hide-when-one-location change. NOT changed - the current spec (S9-N1) says a one-location user still sees the filter.
IV-LOC-04 | C30577 | https://shopview.testrail.io/index.php?/cases/view/30577 | IV | Video P33 - hide location filter when <=1 location | PENDING-CHRIS | Same location-filter hide-when-one-location change. NOT changed - the current spec (S7-N1) says a one-location user still sees the filter.
PV-FILT-13 | C30340 | https://shopview.testrail.io/index.php?/cases/view/30340 | PV | Video P33 - hide location filter when <=1 location | PENDING-CHRIS | Same location-filter hide-when-one-location change. NOT changed - the current spec (S2-E4) says a one-location user still sees the filter.
WIP-FLT-03 | C30500 | https://shopview.testrail.io/index.php?/cases/view/30500 | WIP | Video P12 - asset dropdown behavior | OPEN-DECISION | Undecided on the call: the Asset dropdown stays open while you pick several (Chris) vs matching the native reports that close on each pick, plus a toggle (Stefan). Do not pass/fail on this until decided; confirm the final behavior live. Not changed.
IV-PERS-01 | C30579 | https://shopview.testrail.io/index.php?/cases/view/30579 | IV | Video P18 / P36 - column-selector scope | OPEN-DECISION | Column-selector scope was left open across the suite (Chris vetoed one on Technician Utilization, 'not married to it'). Inventory Value currently HAS a column selector per the spec (S8-R1). Confirm with Chris whether Inventory Value keeps its selector. Not changed.
PV-API-01 | C30388 | https://shopview.testrail.io/index.php?/cases/view/30388 | PV | Video P30 - pagination vs infinite-scroll | OPEN-DECISION | Chris wants to revisit forced pagination vs infinite-scroll / lazy-load for large part lists. The behavior may change; treat as a performance caveat and confirm live. Not changed. Also PV-API-02 C30389.
(no case - TU) |  |  | TU | Video P18 - TU column selector | OPEN-DECISION | Chris vetoed a column selector on Technician Utilization but is 'not married to it.' Our TU cases correctly have none, matching the spec. No case to change now; if Chris later adds one, author cases then.
WIP-CALC-08 | C30481 | https://shopview.testrail.io/index.php?/cases/view/30481 | WIP | Video P14 vs spec S4-R23 - labor-delta basis | LIVE-VIU-PENDING | Video P14 says the labor delta = clocked/tech hours vs INVOICED hours; the WIP spec (S4-R23) uses QUOTED (estimate) hours minus worked hours because WIP is a pre-invoice report. The case matches the SPEC (quoted-basis) and is NOT changed. Confirm live which basis actually ships. Do NOT conflate with Sales By Customer / Sales By Representative, which correctly use invoiced-minus-worked (SBC-CALC-03 C30151, SBR-CALC-02 C30230).
TU-NAV-01 | C30392 | https://shopview.testrail.io/index.php?/cases/view/30392 | TU | Video P3 - move TU down in nav | LIVE-VIU-PENDING | Video: Technician Utilization is in a bad nav spot and must move toward the bottom (additive, not interruptive). The spec says the order among the six reports does not matter, so no wording change; confirm the final nav placement live. Not changed.

## Blocked on Chris spec update
Report Suite - items blocked on Chris Ward's spec update (PENDING-CHRIS)
These are firm video-intent items where the CURRENT written spec still says otherwise. Per the process, we do NOT rewrite cases to un-ratified verbal intent - each waits for Chris to update the Confluence spec, then we edit + live-VIU.
Internal ID | TestRail Case ID | TestRail link | Report | Driving source | Classification | What needs to be done (plain)
SBC-LBL-01 | C30134 | https://shopview.testrail.io/index.php?/cases/view/30134 | SBC | Video P24 - serial-number identifier | PENDING-CHRIS | If Chris ratifies it, change the asset label to use the SERIAL NUMBER (bin number) as the identifier instead of Unit -> plate -> VIN. NOT changed yet: the current written spec (S8-R8 '· Unit {unit}') still uses the unit number, and Chris said he will 'double-check the spec' first. Also touches SBC-LBL-02 C30135, SBC-LBL-03 C30136, SBC-LBL-04 C30137.
WIP-COL-05 | C30470 | https://shopview.testrail.io/index.php?/cases/view/30470 | WIP | Video P24 - serial-number identifier | PENDING-CHRIS | Same serial-number change for the Work In Progress Asset cell (currently the unit number over the VIN, per spec S4-R7). NOT changed yet - awaiting Chris's spec update. Also touches WIP-FLT-03 C30500, WIP-SORT-03 C30485, WIP-EXP-07 C30516.
SBC-EXP-01 | C30159 | https://shopview.testrail.io/index.php?/cases/view/30159 | SBC | Video P25 - remove SBC Print | PENDING-CHRIS | If Chris cuts Print from the spec, remove the 'Print' item from the report's overflow (three-dot) menu. NOT changed yet: the current spec (Story 16) still includes Print; Chris said 'this should not exist... I'm going to make sure that's cut out of the spec.'
SBC-EXP-13 | C30171 | https://shopview.testrail.io/index.php?/cases/view/30171 | SBC | Video P25 - remove SBC Print | PENDING-CHRIS | Retire the SBC Print-behavior case once Print is cut from the spec. NOT changed yet. Print is also referenced in the empty-state export case SBC-EXP-15 C30173.
(new - to author) |  |  | SBC | Video P21 - add compressed download | PENDING-CHRIS | Chris agreed live to ADD a compressed/summary download to Sales By Customer, alongside the existing expanded (nested) download - like the other reports' Summary/Expanded split. NOT authored yet: the current spec has only the single flat export. Author a new export case once the spec adds it.
SBC-LOC-03 | C30111 | https://shopview.testrail.io/index.php?/cases/view/30111 | SBC | Video P10 - per-row location label | PENDING-CHRIS | When 'All locations' is selected, add a per-row (or per-section) location label so a user can tell which shop each row belongs to. NOT added yet on the five non-WIP reports; add once the spec calls for it. Work In Progress already has a Location column. Also affects SBR-LOC-03 C30215, PV-FILT-10 C30337, TU-LOC-01 C30442, IV-LOC-01 C30574 - likely a new case per report.
PV-FILT-01 | C30328 | https://shopview.testrail.io/index.php?/cases/view/30328 | PV | Video P31 - Catalogue rename | PENDING-CHRIS | If Chris renames/truncates 'Catalogue' (it means special-order parts never stocked), update the Type filter option, the Type column value, and the tooltips to the new label. NOT changed yet - the rename is not decided and the current spec still says 'Catalogue'. Also touches PV-FILT-09 C30336, PV-ROW-05 C30345, PV-EXP-08 C30382.
SBR-LOC-04 | C30216 | https://shopview.testrail.io/index.php?/cases/view/30216 | SBR | Video P33 - hide location filter when <=1 location | PENDING-CHRIS | Chris's intent: HIDE the Location filter when a user can access only one location, SHOW it when they can access two or more. This case currently says the OPPOSITE (a one-location user STILL sees the filter, spec S21-N1) straight from the current spec. Do NOT change until Chris updates the spec - the written spec directly contradicts the video here. Ties to the Q2 permission question.
TU-LOC-05 | C30446 | https://shopview.testrail.io/index.php?/cases/view/30446 | TU | Video P33 - hide location filter when <=1 location | PENDING-CHRIS | Same location-filter hide-when-one-location change. NOT changed - the current spec (S9-N1) says a one-location user still sees the filter.
IV-LOC-04 | C30577 | https://shopview.testrail.io/index.php?/cases/view/30577 | IV | Video P33 - hide location filter when <=1 location | PENDING-CHRIS | Same location-filter hide-when-one-location change. NOT changed - the current spec (S7-N1) says a one-location user still sees the filter.
PV-FILT-13 | C30340 | https://shopview.testrail.io/index.php?/cases/view/30340 | PV | Video P33 - hide location filter when <=1 location | PENDING-CHRIS | Same location-filter hide-when-one-location change. NOT changed - the current spec (S2-E4) says a one-location user still sees the filter.