## Executive Summary
Simple Flow — SV-8183 Permission Test vs. QA-found Issues: Reconciliation & Honest Analysis
Feature: Simple Flow (Epic SV-7301) — permission/role controls (Story SV-8183) · Environment: app.staging.shopview.com · PO: Milos · Date: 2026-07-24 · No TestRail writes
Prior report under review: SimpleFlow_SV-8183_Permission-Test-Report_2026-07-23.md (concluded 11/11 PASS). Live re-verify on clean template roles (drift ruled out, Rule 26).
CORRECTION 2026-07-24 — our 2026-07-23 report over-claimed.
On 2026-07-23 we published a permission report concluding "11 of 11 test cases passed, zero mismatches, controls behave exactly as specified — PASS." QA (Ayesha) then raised three issues (SV-8515, SV-8516, SV-8541) against the same feature.
We re-checked all three LIVE on staging against clean (template-reset) roles, capturing the real screen and the real system response for each step. All three are real coverage gaps. Our report over-claimed: the 11 cases were correct for what they tested, but the SUITE did not cover the action paths these issues live on — and we reported "all pass" as if the whole feature were clean.
SV-8515 — REAL defect (developer accepting the fix, "Ready to Fix").
A view-only parts user is correctly NOT shown the per-order Receive button, but can still tick several orders, click "Receive Selected," and the full editable receiving screen opens — which should never appear for a view-only user. GOOD NEWS: when they actually try to receive, the system REFUSES it (Access denied / HTTP 403) — nothing is received or changed. So it is a misleading, dead-end screen that shouldn't be reachable, NOT a view-only user really receiving. QA's "receive same as Admin / bypasses the permission model" is right that there's a defect but OVERSTATED — the back end blocks the actual receive.
SV-8516 — REAL, front-end already fixed, one back-end residue to flag.
A Time Clock user used to edit/cancel/return parts and change the vendor. The front-end fix HOLDS — that user now only sees "Return." BUT the system will still accept a part EDIT sent directly to it (API returns 200 and the change persists). Per Standing Rule 24 a front-end block the API can still get past is FLAGGED, not a re-opened bug, unless the PO decides the back end must enforce it.
SV-8541 — REAL, but pre-existing and awaiting a product decision.
A user WITHOUT "Work Order Line: Create & Edit" can still RESOLVE CORES — the system accepts it (returns success / HTTP 201) even for the lowest-privilege Time Clock role. This is NOT something Simple Flow broke; it behaves the SAME on Production, and the spec itself (§9.4) says these fine-grained work-order gates are front-end conveniences the back end does not separately enforce. Correctly OPEN with the developer (Sasha) as a clarification.
CORRECTED VERDICT.
The 11 cases still pass for what they tested (the documented per-role matrix cells). But the report's FEATURE-WIDE "PASS / everything behaves as specified" claim is CORRECTED: there are three action-path coverage gaps — two real defects (one front-end-exposure defect the developer is already fixing; one front-end-fixed-but-back-end-open flag) and one pre-existing/spec-interpretation item open with the developer. QA caught three genuine gaps our pass missed.

## Per-Issue Analysis
Issue (link) | What QA reported | Role / env QA used | Our prior finding (case + C-id + link) | Live ground truth this run (UI + API status + evidence) | Verdict | Spec wording it deviates from (verbatim, Rule 25) | Was QA right? | Our miss (path not driven)
SV-8515 https://shopview.atlassian.net/browse/SV-8515 (Story Defect · Ready to Fix · Dusan) | Office / Vendor & Order Mgmt VIEW-only user has no per-PO Receive button but can multi-select → "Receive Selected" → edit invoice/vendor and bulk receive "same as Admin." | Office user (real prereq = Vendor & Order Mgmt: View only). Staging vs Production. | SF-PERM-03 / C29407 (https://shopview.testrail.io/index.php?/cases/view/29407) — "which roles can Bulk Receive"; we said "Office view-only per spec — PASS." Adjacent: SF-PERM-05 / C29409 (https://shopview.testrail.io/index.php?/cases/view/29409) — per-PO button hidden (still valid). | UI: per-PO Receive HIDDEN (matches). BUT after multi-select the "Receive Selected" button appears and opens the full editable /bulk-receive "Receive Vendor Parts" screen (33 editable inputs — invoice#, date, cost $, tax), no front-end gate (sv8515-office-after-select.png, sv8515-bulk-receive-screen.png). API: read receive-view = 200 (why the screen loads); actual POST /api/inventory/orders/accept = HTTP 403 {"error":"Access denied."} — receive does NOT complete (sv8515-recv5-net.json). Control: empty body = 400 (validation) for Admin vs 403 for Office = real back-end gate. Clean role (drift ruled out). | REAL front-end-exposure defect (dev-accepted, Ready to Fix). NOT a data bypass — back end blocks the actual receive. | §9.1: "Bulk Receive page (accountant, PO-list driven) ¦ 7/8/9 ¦ Vendor & Order Mgmt: Create & Edit (route gate hasPartsPermissions) + See Financial Data..." — front-end must require Create & Edit to reach the screen. §9.2 Office = "No (4)", footnote 4: "Office has Vendor & Order Mgmt: View only → can open Bulk Receive but cannot receive." → back end matches spec; FRONT-END deviates by exposing the Receive-Selected entry point. | YES — real front-end defect — but OVERSTATED the bypass (receive is blocked at the back end; no escalation / no data mutation). | We never drove the multi-select "Receive Selected" alternate entry point for a View-only user. SF-PERM-03/C29407 stopped at route-level nav; SF-PERM-05/C29409 stopped at the per-PO button.
SV-8516 https://shopview.atlassian.net/browse/SV-8516 (Story Defect · Done · Staging_Verified · Dusan) | Time Clock user could edit / cancel / return parts and change vendor (should have no access; Production blocks it). | Time Clock user. Staging vs Production. | No dedicated part-action negative existed. Nearest: SF-PERM-09 / C29413 (https://shopview.testrail.io/index.php?/cases/view/29413) — financial part-add gate; SF-PERM-10 / C29414 (https://shopview.testrail.io/index.php?/cases/view/29414) — per-role COMPLETION matrix only. | UI (the fix): Time Clock part-row ⋮ menu now shows ONLY "Return" — Edit / Cancel / Change-Vendor removed (sv8516-tc-menus.json, sv8516-tc-wo-lines.png) → Done/Staging_Verified fix HOLDS at the front end. API (the residue): Time Clock (confirmed 3/3 perms live) can STILL edit a part via POST /api/work-orders/part/change-request = HTTP 200, change PERSISTED (re-GET showed new description) — same as Admin. Edit of an already-received part is blocked by STATE ("can't be modified once received"), not permission. Clean role (drift ruled out). | Original over-grant was REAL, now front-end-FIXED; residual back-end-accepts-edit = Rule-24 API-possible FLAG — not a re-opened bug unless PO requires back-end enforcement. | §9.2: Time Clock = "No" across every column (no access) — a Time Clock editing a part contradicts this. §9.1 (Sasha's mapping): part-request management (make/edit/cancel) → "WO Lines: Create & Edit"; Time Clock lacks it → back end should block. §9.4 counterweight: "FE distinctions ... are conveniences, not BE-enforceable boundaries" → residual back-end-possibility is spec-anticipated (flag). | YES — real; front-end FIXED, back-end still OPEN (Rule-24 flag). | We had NO per-role part edit / cancel / return negative anywhere in the suite.
SV-8541 https://shopview.atlassian.net/browse/SV-8541 (Story Defect / Clarification · Open · Sasha) | A user WITHOUT "WO Line: Create & Edit" can return a received special-order part and resolve cores (OK/Not OK). Same on Staging AND Production. | User lacking WOL C&E (tested Office and Time Clock). Staging + Production. | SF-REV-14 / C29399 (https://shopview.testrail.io/index.php?/cases/view/29399) — "cores decided before receiving" — touches core resolution but NO per-role permission-negative. | API: POST /api/work-orders/{id}/pre-resolve-cores {cores:[{partRequestId,isCoreOk:true}]} = HTTP 201 {"resolvedCount":1} for OFFICE (WO 3996683a) AND TIME CLOCK (WO 1b6f0ae6) — endpoint applies ZERO permission check (LOG-SV-8541). Part-action endpoints returned STATE 400 (not permission 403) for Office & Time Clock. UI: low-priv roles also SEE the controls (Office shows Return/Core/Edit; Time Clock ⋮ shows Return). Clean template roles (drift ruled out, before==after). | REAL & reproduces on clean roles. Time Clock holds NONE of the §9.4 collapsing atoms yet still succeeds → genuine missing back-end check — BUT pre-existing (matches Production), spec-anticipated per §9.4. Correctly OPEN for Sasha (Rule 24/25 clarification). | §9.1: "Resolve inventory / special-order cores (Ok/Not OK) ¦ 3/4/16 ¦ WO Lines: Create & Edit." — spec requires WOL C&E. §9.2: Time Clock = "No" every column. Counterweight (Rule 25): §9.4: collapse is "a deliberate, spec-sanctioned low-privilege trade-off (SV-7864). FE distinctions ... are conveniences, not BE-enforceable boundaries." The one part §9.4 does NOT cover: a role (Time Clock) holding NONE of the collapsing atoms still succeeding = the gap for Sasha. | YES — real; PRE-EXISTING / spec-interpretation (flag), correctly a clarification. | SF-REV-14/C29399 exercised cores FUNCTIONALLY but never as a per-role permission-negative.

## Where Our Report Was Wrong
THE THREE DIMENSIONS WE MISSED
# | Dimension we missed | What we DID do | What we SHOULD have done | Issue it hid
1 | Alternate entry points not driven per role | Verified route-level nav (/parts/orders allowed/denied) and the per-PO Receive button being hidden. | Also drive the multi-select → "Receive Selected" path into the editable Bulk-Receive screen. A hidden button on one path ≠ action unreachable on every path. | SV-8515
2 | Back end not probed per granular action | Probed the settings SAVE endpoint (403/200) and concluded "back end enforces." | Probe the specific part-action endpoints (part/change-request, pre-resolve-cores, status-action) as EACH no-access role — the only way to catch front-end-exposure gaps AND Rule-24 API-possible flags. | SV-8516, SV-8541
3 | No cases existed for these negatives | Suite covered completion / bulk-receive routing / review only. | Have per-role part edit/cancel/return negatives and per-role core-resolution negatives. Several report rows were "PASS (composition-verified)" — inferred from the role's permission list + an inherited gate, not driven live per action (Rule 12: matching permission list ≠ observed enforced action). | SV-8516, SV-8541
4 | The completeness FRAMING was mis-scoped | Reported "110 combinations, zero mismatches, controls behave exactly as specified — PASS" as FEATURE-WIDE completeness. | Scope the claim: "the documented §9.2 matrix cells pass; action-path and back-end-per-action coverage is not yet exhaustive." A passing matrix cell ≠ a fully-enforced action. | All three
WHAT WE GOT RIGHT (honest credit)
On SV-8515, our report said Office is "view-only (can open, cannot receive) exactly per spec" and that the back end enforces (403). That conclusion is CORRECT — the live accept call returns 403 and nothing is received. What we missed was the front-end EXPOSURE of the editable screen along the way. So: right about back-end enforcement, wrong to assume the front-end path was therefore clean.

## Root Cause
Cause | Detail
Summary | Our VIU applied the four documented layers (composition / back-end endpoint / front-end route / on-screen element) to the 11 cases we had, and did that well for those cells. The failure was in SCOPE and METHOD BREADTH, not in the individual observations.
(a) Action-path coverage not exhaustive | We tested WHETHER a role can reach a feature (route/nav/button) but not EVERY way to perform the action — alternate entry points (multi-select / bulk / kebab menus) were not driven per role.
(b) Per-action back-end probing not exhaustive | We probed one endpoint family (settings) for 403/200 and generalised "back end enforces." We did not send the specific granular action (part edit, core resolve) to the back end AS each no-access role — the only way to catch front-end-exposure gaps and Rule-24 API-possible flags.
(c) Suite had no cases | No per-role part edit/cancel/return negative and no per-role core-resolution negative existed — so nothing prompted the checks.
(d) Completeness claim mis-scoped | "All pass" was reported as feature-wide. A passing matrix cell is not a fully-enforced action, and several rows were composition-inferred rather than action-driven.
In one line | We proved the documented gates were configured correctly, but did not adversarially try to BREAK every action from every role by every path and against the back end — so the enforcement holes hid in the paths and endpoints we never exercised.

## Corrective Actions
# | Proposed case (NOT authored / NOT pushed) | Assert / flag | Driving ticket + spec anchor (Rule 20) | Status
1 | (NEW) Bulk-Receive "Receive Selected" multi-select negative for a Vendor & Order Mgmt View-only user. Also UPDATE SF-PERM-03 / C29407 (https://shopview.testrail.io/index.php?/cases/view/29407) to drive the multi-select path, not just route nav. | Assert: per-PO Receive hidden (passes) AND the multi-select "Receive Selected" must NOT open the editable /bulk-receive screen for a View-only user (currently the front-end EXPOSES it — defect) AND the actual receive is blocked at the back end (accept → 403). | SV-8515 / SV-8183 (§9.1 Bulk-Receive route gate hasPartsPermissions; §9.2 footnote 4). | Needs user approval to author + eventual TestRail add (Rule 6).
2 | (NEW) No-access role (Time Clock) part edit / cancel / return negative. | Assert: UI HIDES Edit / Cancel / Change-Vendor for Time Clock (passes — the SV-8516 front-end fix) AND flag per Rule 24 that the action is still possible via the API (part/change-request → 200, persisted). Not a bug unless PO requires back-end enforcement. | SV-8516 / SV-8183 (§9.2 Time Clock row; §9.1 part-request → WO Lines: Create & Edit; §9.4 atom-collapse). | Needs user approval to author + eventual TestRail add (Rule 6).
3 | (NEW) WO-Lines-C&E-gated core-resolution / received-part-return negative. | Assert: a role WITHOUT WO Lines: Create & Edit (test Time Clock) — intended rule is it cannot resolve cores / return a received special part; capture that the back end CURRENTLY returns 201 with no gate (pre-resolve-cores). Pending Sasha's SV-8541 ruling on whether back-end enforcement is required. | SV-8541 / SV-8183 (§9.1 resolve cores → WO Lines: Create & Edit; §9.2 Time Clock row; §9.4 atom-collapse caveat). | Needs user approval to author + eventual TestRail add (Rule 6).

## Was QA Right
Issue | Our nearest case (C-id + link) | QA's call | Reality (live-verified) | Was QA right?
SV-8515 | SF-PERM-03 / C29407 (https://shopview.testrail.io/index.php?/cases/view/29407) · SF-PERM-05 / C29409 (https://shopview.testrail.io/index.php?/cases/view/29409) | Real defect; "view-only can receive same as Admin — bypasses the permission model." | Real FRONT-END-EXPOSURE defect (dev accepting, Ready to Fix). Back end BLOCKS the actual receive (403) — no data bypass. | YES — real defect, but OVERSTATED the bypass.
SV-8516 | SF-PERM-09 / C29413 (https://shopview.testrail.io/index.php?/cases/view/29413) · SF-PERM-10 / C29414 (https://shopview.testrail.io/index.php?/cases/view/29414) | Real over-grant (Time Clock could edit/cancel/return/change-vendor). | Was real; front-end now FIXED (⋮ = only Return). Back end still accepts a part edit (change-request → 200) = Rule-24 flag. | YES — real, front-end-fixed, back-end still open.
SV-8541 | SF-REV-14 / C29399 (https://shopview.testrail.io/index.php?/cases/view/29399) | Real; user without WO Lines: C&E can resolve cores / return received part (Staging + Production). | Real; PRE-EXISTING (matches Production), spec-anticipated (§9.4). Time Clock exceeds the documented collapse. Correctly OPEN for Sasha. | YES — real, pre-existing / flag, correctly a clarification.
NET | — | 3 issues raised. | 3 real coverage gaps confirmed. Two real defects (one front-end-exposure dev-accepted; one front-end-fixed / back-end-open Rule-24 flag) + one pre-existing/spec-interpretation clarification open with the dev. | QA caught 3 real gaps. OUR REPORT OVER-CLAIMED completeness.