## Questions for Chris
Questions - Invoice UI Refresh - Chris Ward - 2026-08-25 (refreshed; supersedes 2026-08-21)
Two questions about the Invoice UI Refresh spec (Confluence 755990532). Each is a plain choice; please pick an option and/or type an answer in 'Your answer'. Nothing here blocks the test import.
# | Topic | What happens now | The question | Options | Your answer
PO-1 | Invoice UI Refresh - Credit Invoice balance | The spec describes the money 'Balance' shown on a Credit Invoice in two places, and they say different things. One place (Story 11 rule S11-R6a) says show the remaining credit; the glossary in Section 6 says something else. | Which should the Credit Invoice show as the 'Balance'? We have written the test cases to follow the first version (show the remaining credit, and $0.00 only once it is used up or voided). | A) Show the remaining credit (positive), $0.00 only when used up or voided - and we will correct the glossary line. B) Show what the glossary says - and we will rewrite the affected test cases. | RESOLVED BY SPEC v45 (Confluence 755990532, change-log entry 2026-08-27): the Terminology "Balance" for the Credit Invoice was rewritten to the open-balance definition, matching S11-R6a and Option A. The v39 conflict that prompted this question no longer exists, so no answer is needed. Our case INV-CRED-06 (C44969) already reflects this. — QA, 2026-08-31
PO-2 | Invoice UI Refresh - recent spec edits not in the change log | The spec's own change log lists changes only up to 12 August 2026. Since then the page has been edited at least twice without a log entry: once on 13 August 2026 (version 38) and once around 25 August 2026 (version 39). We have confirmed the 25 August edit only added a Slack-channel link to the header - nothing that affects the documents. The 13 August edit's content is still unknown to us. | Did anything meaningful change in the 13 August 2026 edit? If yes, could you tell us what, so we can check our test cases still match? (The 25 August edit needs no action - we have verified it is just a Slack link.) | A) Nothing meaningful changed in the 13 August edit (formatting/typo only). B) Yes, something changed - I will describe it (please note it in 'Your answer').

## QA-internal (do not send)
QA-ONLY - INTERNAL - NOT FOR CHRIS. Do not send this tab.
Q# | Spec anchor | Affected cases | Our authored position | Register id
PO-1 | S11-R6a vs Terminology (Section 6) | INV-CRED-06; Balance col of INV-CRED-03 | Authored to S11-R6a (open balance); Rule 32 latest/specific wins; glossary line stale ¦ STATUS 2026-08-31: RESOLVED by spec v45 (Terminology rewritten to open-balance = S11-R6a, change-log 2026-08-27). Question moot; do not send. | PO-1 / DELIBERATE-DECISIONS D2
PO-2 | Confluence v38 edited 2026-08-13 and v39 edited ~2026-08-25; change log last entry 2026-08-12 | Whole suite (version pin) | Suite pinned to v39 (25 Aug); v38->v39 delta reconciled 25 Aug = Slack-link only, non-substantive; 13 Aug (v37->v38) content still un-diffable (no v37 held) | PO-2 / DELIBERATE-DECISIONS D4