## Blockers Tracker
Case ID | Area | Title | Current VIU status | State | Blocker category | Who unblocks | What's needed to unblock | Related story/question | VIU sub-bucket | VIU sub-bucket detail (QA-pending only) | TestRail ID | TestRail Link
SF-SET-01 | Work Order Settings | Verify the Work Orders settings tab lists all Work Order setting toggles in order | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S1-R1..R8 / Story 1 AC | — |  | C29275 | https://shopview.testrail.io/index.php?/cases/view/29275
SF-SET-02 | Work Order Settings | Verify there is no operating-mode selector and no VIN-required setting on the Work Order settings page | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S1 AC / Key Decision (no operatingMode) | — |  | C29276 | https://shopview.testrail.io/index.php?/cases/view/29276
SF-SET-03 | Work Order Settings | Verify a 'Create Purchase Orders' toggle exists on the Work Orders tab and controls the Vendor Invoice setting | Deviation | BLOCKED | MILOS ANSWER | Milos (Product Owner) | Milos answers Open Question Q5 — 'Create purchase orders' toggle absent / POs always-on — descope or bug? | Q5 ¦ S1-R2 (Create purchase orders) | — |  | C29277 | https://shopview.testrail.io/index.php?/cases/view/29277
SF-SET-04 | API — Work Order Settings | Verify the Require Vendor Invoice Number toggle is present with helper text and drives Optional vs Required completion | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S1-R3 (Vendor invoice Optional/Required) | — |  | C29278 | https://shopview.testrail.io/index.php?/cases/view/29278
SF-SET-05 | Work Order Settings | Verify Auto-approve Lines ON approves a work-order line the moment it is added | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S1-R1 (Auto-approve ON) | — |  | C29279 | https://shopview.testrail.io/index.php?/cases/view/29279
SF-SET-06 | Work Order Settings | Verify Auto-approve Lines OFF leaves a new line in Needs Approval with Approve/Decline actions | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S1-R1 (Auto-approve OFF) | — |  | C29280 | https://shopview.testrail.io/index.php?/cases/view/29280
SF-SET-07 | API — Work Order Settings | Verify existing settings (tech story, mileage, engine hours, auto-pick) display the org's current values | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S1-R5..R8 (existing settings surfaced) | — |  | C29281 | https://shopview.testrail.io/index.php?/cases/view/29281
SF-SET-08 | Work Order Settings | Verify first-use defaults on a brand-new org (auto-approve OFF, create POs ON, vendor invoice REQUIRED) | Blocked-Env | BLOCKED | MILOS ANSWER | Milos (Product Owner) | Milos answers Open Question Q3, Q4 — First-use defaults: spec (Auto-approve OFF / invoice REQUIRED) vs design (ON / Optional). | Q3, Q4 ¦ S1 first-use defaults / §4 | — |  | C29282 | https://shopview.testrail.io/index.php?/cases/view/29282
SF-SET-09 | API — Work Order Settings | Verify saving a settings change persists after page reload | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S1-R9 (Save persists org-wide) | — |  | C29283 | https://shopview.testrail.io/index.php?/cases/view/29283
SF-SET-10 | Work Order Settings | Verify a settings change applies to future completions only and not to already-completed work orders | VIU-Pending | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: toggle the setting and confirm the downstream behaviour. | S1-R9 (future completions only, never retroactive) | reachable-now | admin+tech + normal WO data; needs another VIU pass (no new inputs). | C29284 | https://shopview.testrail.io/index.php?/cases/view/29284
SF-SET-11 | API — Work Order Settings | Verify a non-admin user cannot see or modify the Work Order settings | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S1 AC (non-admin can't see/modify) | — |  | C29285 | https://shopview.testrail.io/index.php?/cases/view/29285
SF-SET-12 | API — Work Order Settings | Verify the settings model contains no operatingMode field and no requireVin setting | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S1 AC (no requireVin / no operatingMode field) | — |  | C29286 | https://shopview.testrail.io/index.php?/cases/view/29286
SF-SET-13 | Work Order Settings | Verify the Save Settings button is only enabled when there is an unsaved change | VIU-Verified | BLOCKED | MILOS ANSWER | Milos (Product Owner) | Milos answers Open Question Q6 — Save Settings always enabled (no dirty-state gating) — intended or bug? | Q6 ¦ S1 (Save dirty-state) | — |  | C29287 | https://shopview.testrail.io/index.php?/cases/view/29287
SF-SET-14 | Work Order Settings | Verify the Require Review Before Completion toggle is present on the settings page and drives the review flow | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S1-R4 (Require review before completion) | — |  | C29288 | https://shopview.testrail.io/index.php?/cases/view/29288
SF-SET-15 | Work Order Settings | Verify every Work Order setting toggle has descriptive helper text | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S1 AC (helper text per toggle) | — |  | C29289 | https://shopview.testrail.io/index.php?/cases/view/29289
SF-COMP-01 | Completion — No-PO / Skip (Story 2) | Verify a Complete Work Order button appears next to New Line on the work order | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S2-R1 | — |  | C29290 | https://shopview.testrail.io/index.php?/cases/view/29290
SF-COMP-02 | Completion — No-PO / Skip (Story 2) | Verify a work order with no parts completes in one confirm and reaches the Success screen | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S2-R2 / S2-R3 / S2-R4 | — |  | C29291 | https://shopview.testrail.io/index.php?/cases/view/29291
SF-COMP-03 | Completion — No-PO / Skip (Story 2) | Verify the Success screen shows the work order number and total with Done and Go to Invoice actions | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S2-R4 / S2-R5 / S15-R3 | — |  | C29292 | https://shopview.testrail.io/index.php?/cases/view/29292
SF-COMP-04 | Completion — No-PO / Skip (Story 2) | Verify Go to Invoice from the Success screen opens the Finance step where the invoice number is shown | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S2-R5 / S15-R3 | — |  | C29293 | https://shopview.testrail.io/index.php?/cases/view/29293
SF-COMP-05 | Completion — No-PO / Skip (Story 2) | Verify completion is blocked when a required vehicle field is missing | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S2-R2 / S2 AC (missing required fields blocked) | — |  | C29294 | https://shopview.testrail.io/index.php?/cases/view/29294
SF-COMP-06 | Completion — No-PO / Skip (Story 2) | Verify with Create POs OFF a work order with vendor parts completes with no PO, no vendor bill and no AP sync | Blocked-Env | BLOCKED | MILOS ANSWER | Milos (Product Owner) | Milos answers Open Question Q5 — Create-POs-OFF => no PO config not possible (toggle absent). | Q5 ¦ S2-R6 / S2 AC (Create POs off ⇒ no PO) | — |  | C29295 | https://shopview.testrail.io/index.php?/cases/view/29295
SF-COMP-07 | Completion — No-PO / Skip (Story 2) | Verify in-stock inventory parts decrement inventory and write Part History on simple completion | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S2-R6 / §5 invariant 1 | — |  | C29296 | https://shopview.testrail.io/index.php?/cases/view/29296
SF-COMP-08 | Completion — No-PO / Skip (Story 2) | Verify with Auto-pick Inventory OFF the completion modal requires picking parts before Complete | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S2-R2 / S2 AC (auto-pick off ⇒ pick in modal) | — |  | C29297 | https://shopview.testrail.io/index.php?/cases/view/29297
SF-COMP-09 | Completion — No-PO / Skip (Story 2) | Verify adding a new line to a completed work order returns it to Approved | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S2-R6 / S2 AC (re-open returns to Approved) | — |  | C29298 | https://shopview.testrail.io/index.php?/cases/view/29298
SF-COMP-10 | Completion — No-PO / Skip (Story 2) | Verify individual-line Complete and per-part receive actions still work alongside Simple completion | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S2 AC (individual-line Complete + per-part receive kept) | — |  | C29299 | https://shopview.testrail.io/index.php?/cases/view/29299
SF-COMP-11 | Completion — PO + Optional Invoice (Story 3) | Verify the optional-invoice completion wizard offers Receive Parts, Complete Without Receiving and Cancel | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S3-R4 | — |  | C29300 | https://shopview.testrail.io/index.php?/cases/view/29300
SF-COMP-12 | Completion — PO + Optional Invoice (Story 3) | Verify the optional-invoice modal creates POs in the background and shows the count of parts to receive | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S3-R1 / S3-R2 / S3-R9 | — |  | C29301 | https://shopview.testrail.io/index.php?/cases/view/29301
SF-COMP-13 | Completion — PO + Optional Invoice (Story 3) | Verify Receive Parts opens the shared Accept Delivery page to receive all vendors at once | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S3-R5 | — |  | C29302 | https://shopview.testrail.io/index.php?/cases/view/29302
SF-COMP-14 | Completion — PO + Optional Invoice (Story 3) | Verify Complete Without Receiving completes the WO, keeps unreceived parts waiting, and keeps the line Receive button | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S3-R6 | — |  | C29303 | https://shopview.testrail.io/index.php?/cases/view/29303
SF-COMP-15 | Completion — PO + Optional Invoice (Story 3) | Verify Cancel closes the completion modal with no change and no duplicate POs on re-open | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S3-R7 / S3-R9 (Cancel idempotent) | — |  | C29304 | https://shopview.testrail.io/index.php?/cases/view/29304
SF-COMP-16 | Completion — PO + Optional Invoice (Story 3) | Verify the completion modal collects the missing required vehicle fields (Mileage and Engine Hours; no VIN field in the modal) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S3-R3 | — |  | C29305 | https://shopview.testrail.io/index.php?/cases/view/29305
SF-COMP-17 | Completion — PO + Optional Invoice (Story 3) | Verify the optional-invoice flow reaches the Success screen with WO number and total | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S3-R8 | — |  | C29306 | https://shopview.testrail.io/index.php?/cases/view/29306
SF-COMP-18 | Completion — PO + Required Invoice (Story 4) | Verify the required-invoice wizard disables Complete until parts are received and offers no skip option | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S4-R4 | — |  | C29307 | https://shopview.testrail.io/index.php?/cases/view/29307
SF-COMP-19 | Completion — PO + Required Invoice (Story 4) | Verify the required-invoice receive round-trip returns to the modal and enables Complete once all received | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S4-R5 / S4-R7 | — |  | C29308 | https://shopview.testrail.io/index.php?/cases/view/29308
SF-COMP-20 | Completion — PO + Required Invoice (Story 4) | Verify Cancel in the required-invoice wizard makes no change to the work order | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S4-R6 | — |  | C29309 | https://shopview.testrail.io/index.php?/cases/view/29309
SF-COMP-21 | Completion — Line approval gate | Verify on a required-invoice work order an unapproved line disables the Complete Work Order button with a tooltip | VIU-Pending | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: seed the specific completion configuration and drive the wizard to Success. | S4-R8 / Key Decision (all lines approved) / S3-R9 | reachable-now | admin+tech + normal WO data; needs another VIU pass (no new inputs). | C29310 | https://shopview.testrail.io/index.php?/cases/view/29310
SF-COMP-22 | Completion — Line approval gate | Verify a manually unapproved line disables the required-invoice Complete Work Order button with a tooltip even when Auto-approve is ON | VIU-Pending | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: seed the specific completion configuration and drive the wizard to Success. | S4-R8 / Key Decision (holds regardless of Auto-approve) | reachable-now | admin+tech + normal WO data; needs another VIU pass (no new inputs). | C29311 | https://shopview.testrail.io/index.php?/cases/view/29311
SF-COMP-23 | Completion — Idempotency | Verify re-running completion after a prior attempt does not create duplicate POs | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S3-R9 (no duplicate POs on re-Complete) | — |  | C29312 | https://shopview.testrail.io/index.php?/cases/view/29312
SF-CORE-01 | Core parts — Completion modal (Stories 3/4/16) | Verify inventory cores are resolved via a line-level Ok/Not-OK control (no distinct Resolve-Cores wizard step) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S3-C1 / S4-C1 / Resolve Cores handoff | — |  | C29313 | https://shopview.testrail.io/index.php?/cases/view/29313
SF-CORE-02 | Core parts — Completion modal | Verify a work order with no cores completes with no core sub-lines and no Resolve-Cores wizard step | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S3-C1 (skipped if none) | — |  | C29314 | https://shopview.testrail.io/index.php?/cases/view/29314
SF-CORE-03 | Core parts — Completion modal | Verify special-order cores leave the optional-invoice completion unchanged and Complete Without Receiving stays available | VIU-Pending | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: seed a WO with core-charge parts, drive the completion Resolve-Cores modal + invoice-gate round-trip. | S3-C2 | needs-data | a special-order core part + optional-invoice completion (needs is_core part). | C29315 | https://shopview.testrail.io/index.php?/cases/view/29315
SF-CORE-04 | Core parts — Invoice gate | Verify the invoice shows a 'Cores pending' flag when unresolved special-order cores exist | VIU-Pending | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: seed a WO with core-charge parts, drive the completion Resolve-Cores modal + invoice-gate round-trip. | S3-C3 | needs-data | an unresolved special-order core at the invoice gate ('Cores pending' flag) — needs is_core part + receiving. | C29316 | https://shopview.testrail.io/index.php?/cases/view/29316
SF-CORE-05 | Core parts — Invoice gate | Verify resolving cores at the Create Invoice gate routes to receive the cored line then lets invoicing proceed | VIU-Pending | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: seed a WO with core-charge parts, drive the completion Resolve-Cores modal + invoice-gate round-trip. | S3-C4 | needs-data | resolve cores at the Create-Invoice gate -> receive the cored line (needs is_core part + receiving). | C29317 | https://shopview.testrail.io/index.php?/cases/view/29317
SF-CORE-06 | Core parts — Invoice gate | Verify cancelling the invoice-gate core resolution leaves the WO completed, un-invoiced and cores-pending | VIU-Pending | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: seed a WO with core-charge parts, drive the completion Resolve-Cores modal + invoice-gate round-trip. | S3-C4 (cancel path) | needs-data | cancel the invoice-gate core resolution (needs is_core part + invoice gate). | C29318 | https://shopview.testrail.io/index.php?/cases/view/29318
SF-CORE-07 | Core parts — Required invoice (Story 4) | Verify special-order cores are resolved after the required-invoice Receive round-trip before Complete | VIU-Pending | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: seed a WO with core-charge parts, drive the completion Resolve-Cores modal + invoice-gate round-trip. | S4-C2 | needs-data | special-order cores in the required-invoice receive round-trip (needs is_core part + receiving). | C29319 | https://shopview.testrail.io/index.php?/cases/view/29319
SF-CORE-08 | Core parts — Guardrail | Verify the invoice gate detects an unresolved special-order core that exists only as a PartRequest | VIU-Pending | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: seed a WO with core-charge parts, drive the completion Resolve-Cores modal + invoice-gate round-trip. | S3 Guardrail (PartRequest-only core) | needs-data | an unresolved special-order core that exists only as a PartRequest (needs is_core part). | C29320 | https://shopview.testrail.io/index.php?/cases/view/29320
SF-CORE-09 | Core parts — Guardrail | Verify part-sale work orders auto-resolve cores at receive while service work orders require manual Ok/Not OK | VIU-Pending | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: seed a WO with core-charge parts, drive the completion Resolve-Cores modal + invoice-gate round-trip. | S3 Guardrail (part-sale vs service WO) | needs-data | a part-sale WO vs service WO with cores (needs is_core part + receiving). | C29321 | https://shopview.testrail.io/index.php?/cases/view/29321
SF-CORE-10 | Core parts — Resolve step UI | Verify the core '+$ to invoice' amount is shown at the line level as a core is marked Not-OK (no Resolve-Cores wizard total) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | Resolve Cores handoff (live +$ total) | — |  | C29322 | https://shopview.testrail.io/index.php?/cases/view/29322
SF-TECH-01 | Tech Story Flow (Story 17) | Verify each work order line shows a Story sub-row with an 'Add tech story for this line' link when empty | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | TS-R1 | — |  | C29323 | https://shopview.testrail.io/index.php?/cases/view/29323
SF-TECH-02 | Tech Story Flow (Story 17) | Verify with Require tech story ON every line needs a story before the work order can complete | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | TS-R2 | — |  | C29324 | https://shopview.testrail.io/index.php?/cases/view/29324
SF-TECH-03 | Tech Story Flow (Story 17) | Verify Complete opens the tech-story modal first and then chains into completion (order: tech story → parts → complete) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | TS-R3 | — |  | C29325 | https://shopview.testrail.io/index.php?/cases/view/29325
SF-TECH-04 | Tech Story Flow (Story 17) | Verify the tech-story modal structure (header, per-line card, Line X of N, required textarea, disabled Next) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | TS-R4 | — |  | C29326 | https://shopview.testrail.io/index.php?/cases/view/29326
SF-TECH-05 | Tech Story Flow (Story 17) | Verify multi-line tech-story navigation (Back after line 1, Continue/Save on the last line) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | TS-R4 (multi-line navigation) | — |  | C29327 | https://shopview.testrail.io/index.php?/cases/view/29327
SF-TECH-06 | Tech Story Flow (Story 17) | Verify a saved tech story renders inline with a green check, the text and an Edit link | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | TS-R5 | — |  | C29328 | https://shopview.testrail.io/index.php?/cases/view/29328
SF-TECH-07 | Tech Story Flow (Story 17) | Verify the tech-story modal has a text box for typing the story | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | TS-R6 (test id) | — |  | C29329 | https://shopview.testrail.io/index.php?/cases/view/29329
SF-TECH-08 | Tech Story Flow (Story 17) | Verify tech story is captured both inline and via the gate modal (Story 17 supersedes on-the-line-only wording) | VIU-Verified | BLOCKED | MILOS ANSWER | Milos (Product Owner) | Milos answers Open Question Q9, Q4 — Tech-story placement: Story 17 (inline + gate-modal) vs S15-R2 (line-only). | Q9, Q4 ¦ TS Decision vs S15-R2 | — |  | C29330 | https://shopview.testrail.io/index.php?/cases/view/29330
SF-VPART-01 | Vendorless / No-PN Part (Story 5) | Verify a vendorless part can be requested with description, quantity and category (part number, cost, vendor and sell price left empty) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S5-R1 | — |  | C29331 | https://shopview.testrail.io/index.php?/cases/view/29331
SF-VPART-02 | Vendorless / No-PN Part (Story 5) | Verify adding a part is blocked when description, quantity or category is missing (sell price not enforced) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S5-R1 / S5 AC (validation) | — |  | C29332 | https://shopview.testrail.io/index.php?/cases/view/29332
SF-VPART-03 | Vendorless / No-PN Part (Story 5) | Verify a vendorless part's type uses the existing source field (vendor or found) and never inventory | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S5-R2 | — |  | C29333 | https://shopview.testrail.io/index.php?/cases/view/29333
SF-VPART-04 | Vendorless / No-PN Part (Story 5) | Verify a vendorless part is editable after creation | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S5-R3 | — |  | C29334 | https://shopview.testrail.io/index.php?/cases/view/29334
SF-VPART-05 | Vendorless / No-PN Part (Story 5) | Verify a no-part-number part creates no inventory item and no Part History | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S5-R4 / S5 AC (no inventory interaction) | — |  | C29335 | https://shopview.testrail.io/index.php?/cases/view/29335
SF-VPART-06 | Vendorless / No-PN Part (Story 5) | Verify adding a part number and vendor later transitions the part out of vendorless | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S5 AC (transitions out of vendorless) | — |  | C29336 | https://shopview.testrail.io/index.php?/cases/view/29336
SF-VPART-07 | Vendorless / No-PN Part (Story 5) | Verify a vendorless / no-PN part cannot be received until a part number (and vendor) is entered | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S5-R4 / S5 AC (receive gate) | — |  | C29337 | https://shopview.testrail.io/index.php?/cases/view/29337
SF-VMIS-01 | Vendor Missing on WO PO (Story 6) | Verify a vendorless vendor-part goes onto the work order's normal PO with no separate dummy PO | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S6-R1 | — |  | C29338 | https://shopview.testrail.io/index.php?/cases/view/29338
SF-VMIS-02 | Vendor Missing on WO PO (Story 6) | Verify a 'Vendor Missing +N' indication shows on the PO list and PO detail | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S6-R2 | — |  | C29339 | https://shopview.testrail.io/index.php?/cases/view/29339
SF-VMIS-03 | Vendor Missing on WO PO (Story 6) | Verify a Vendor Missing PO is flagged and excluded from QuickBooks sync | Blocked-Env | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: seed a WO PO with a vendor-missing part, drive the flag flow. | S6-R3 | needs-data | QuickBooks sync inspection (vendor-missing PO excluded from QB). | C29340 | https://shopview.testrail.io/index.php?/cases/view/29340
SF-VMIS-04 | Vendor Missing on WO PO (Story 6) | Verify a Vendor Missing PO offers options to select a vendor and enter/edit the part number | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S6-R4 | — |  | C29341 | https://shopview.testrail.io/index.php?/cases/view/29341
SF-VMIS-05 | Vendor Missing on WO PO (Story 6) | Verify the Vendor Missing flag clears once both a vendor and a part number are provided | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S6-R5 | — |  | C29342 | https://shopview.testrail.io/index.php?/cases/view/29342
SF-VMIS-06 | Vendor Missing on WO PO (Story 6) | Verify reports mark Vendor Missing POs as 'needs vendor' | VIU-Pending | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: seed a WO PO with a vendor-missing part, drive the flag flow. | S6-R6 | needs-data | reports data (Vendor Missing POs flagged 'needs vendor'). | C29343 | https://shopview.testrail.io/index.php?/cases/view/29343
SF-VMIS-07 | Vendor Missing on WO PO (Story 6) | Verify a sell-price-only part is orderable from the line's Order action, joins the Vendor-Missing PO and moves to waiting-to-receive | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S6-R7 | — |  | C29439 | https://shopview.testrail.io/index.php?/cases/view/29439
SF-POSEL-01 | PO Multi-Select (Story 7) | Verify the PO list has a select-all checkbox and per-PO checkboxes | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S7-R1 | — |  | C29344 | https://shopview.testrail.io/index.php?/cases/view/29344
SF-POSEL-02 | PO Multi-Select (Story 7) | Verify selecting POs shows a bar with 'N purchase orders selected', Clear and Receive Selected | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S7-R2 | — |  | C29345 | https://shopview.testrail.io/index.php?/cases/view/29345
SF-POSEL-03 | PO Multi-Select (Story 7) | Verify Receive Selected opens the PO Bulk Receive page carrying the selected POs | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S7-R3 | — |  | C29346 | https://shopview.testrail.io/index.php?/cases/view/29346
SF-POSEL-04 | PO Multi-Select (Story 7) | Verify fulfilled (already-received) POs are not selectable | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S7-R4 | — |  | C29347 | https://shopview.testrail.io/index.php?/cases/view/29347
SF-POSEL-05 | PO Multi-Select (Story 7) | Verify Vendor Missing POs are selectable and clearly indicated in the list | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S7-R5 | — |  | C29348 | https://shopview.testrail.io/index.php?/cases/view/29348
SF-POSEL-06 | PO Multi-Select (Story 7) | Verify select-all only toggles POs on the current page/filter | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S7 (select-all scope) | — |  | C29349 | https://shopview.testrail.io/index.php?/cases/view/29349
SF-BULK-01 | PO Bulk Receive Page (Story 8) | Verify the Bulk Receive page has a 'Back To Purchase Orders' link that returns to the PO list | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S8-R1 | — |  | C29350 | https://shopview.testrail.io/index.php?/cases/view/29350
SF-BULK-02 | PO Bulk Receive Page (Story 8) | Verify the Bulk Receive page groups POs by vendor with a vendor count and per-vendor expand/collapse | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S8-R2 / S8-R3 | — |  | C29351 | https://shopview.testrail.io/index.php?/cases/view/29351
SF-BULK-03 | PO Bulk Receive Page (Story 8) | Verify each PO row shows the PO number, related work order (or inventory/no-WO indicator) and parts count | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S8-R4 | — |  | C29352 | https://shopview.testrail.io/index.php?/cases/view/29352
SF-BULK-04 | PO Bulk Receive Page (Story 8) | Verify selection behavior: nothing selected by default; selecting a PO selects all its parts; individual parts selectable; actions locked until checked | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S8-R5 | — |  | C29353 | https://shopview.testrail.io/index.php?/cases/view/29353
SF-BULK-05 | PO Bulk Receive Page (Story 8) | Verify the per-PO 'Receive parts (N)' button is disabled until a vendor invoice number is entered | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S8-R6 | — |  | C29354 | https://shopview.testrail.io/index.php?/cases/view/29354
SF-BULK-06 | PO Bulk Receive Page (Story 8) | Verify field editability and locking on Bulk Receive (qty and cost editable; sell locks after WO invoiced/paid) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S8-R7 / S10-R2 | — |  | C29355 | https://shopview.testrail.io/index.php?/cases/view/29355
SF-BULK-07 | PO Bulk Receive Page (Story 8) | Verify assigning a vendor to a Vendor Missing PO moves it into that vendor's group and entering the missing PN enables receiving | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S8-R8 | — |  | C29356 | https://shopview.testrail.io/index.php?/cases/view/29356
SF-BULK-08 | PO Bulk Receive Page (Story 8) | Verify Receive All receives everything selected at once and supports partial receive | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S8-R10 | — |  | C29357 | https://shopview.testrail.io/index.php?/cases/view/29357
SF-BULK-09 | PO Bulk Receive Page (Story 8) | Verify Bulk Receive uses the same pipeline as single-PO receive (Delivery → Vendor Bill → QuickBooks) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S8-R11 | — |  | C29358 | https://shopview.testrail.io/index.php?/cases/view/29358
SF-BULK-10 | PO Bulk Receive Page (Story 8) | Verify a cored part's Ok/Not OK resolution becomes available once received, and core-only partial receive is supported | VIU-Pending | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: fresh sv7301 cookies + seeded data to drive this scenario. | S8-C1 / S8-C2 | needs-data | RE-VIU 2026-07-09: Bulk Receive page BUILT; this case needs a genuine cored part received on the bulk page to expose Ok/Not-OK resolution (is_core part not seedable via canned/sub-form). | C29359 | https://shopview.testrail.io/index.php?/cases/view/29359
SF-INV-01 | Apply Invoice to Selected POs (Story 9) | Verify each vendor group has an 'Apply to selected POs' control enabled only with an invoice # and ≥1 PO selected | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S9-R1 | — |  | C29360 | https://shopview.testrail.io/index.php?/cases/view/29360
SF-INV-02 | Apply Invoice to Selected POs (Story 9) | Verify Apply pre-fills one invoice number into only the selected POs of that vendor, still editable per PO | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S9-R2 | — |  | C29361 | https://shopview.testrail.io/index.php?/cases/view/29361
SF-INV-03 | Apply Invoice to Selected POs (Story 9) | Verify Apply Invoice is scoped per vendor, not offered for the vendorless group, and allows a reused invoice number | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S9-R3 | — |  | C29362 | https://shopview.testrail.io/index.php?/cases/view/29362
SF-PNFIX-01 | Inline Part-Number Fix (Story 10) | Verify a no-number part shows 'Missing part number' with Edit → enter → save that persists immediately | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S10-R1 | — |  | C29363 | https://shopview.testrail.io/index.php?/cases/view/29363
SF-PNFIX-02 | Inline Part-Number Fix (Story 10) | Verify entering a NEW part number creates a new inventory/catalog part with stock and Part History on receive | VIU-Pending | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: drive the inline part-number fix flow with seeded PO lines. | S10 AC (new number) | needs-data | receiving + inventory/catalog inspection (new PN creates inventory part + stock + Part History on receive). | C29364 | https://shopview.testrail.io/index.php?/cases/view/29364
SF-PNFIX-03 | Inline Part-Number Fix (Story 10) | Verify entering an EXISTING part number links to that item and updates stock/cost/history without overwriting description or category | VIU-Pending | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: drive the inline part-number fix flow with seeded PO lines. | S10 AC (existing number) | needs-data | receiving + inventory inspection (existing PN links to item, updates stock/cost/history). | C29365 | https://shopview.testrail.io/index.php?/cases/view/29365
SF-PNFIX-04 | Inline Part-Number Fix (Story 10) | Verify inline part-number field-locking rules match the receive-screen rules (sell locks after invoiced/paid) | VIU-Pending | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: drive the inline part-number fix flow with seeded PO lines. | S10-R2 / S8-R7 | needs-data | a WO in invoiced/paid state (sell-field locking). | C29366 | https://shopview.testrail.io/index.php?/cases/view/29366
SF-PNFIX-05 | Inline Part-Number Fix (Story 10) | Verify a part cannot be received without a part number, a vendor (for vendor-missing) and a cost / sell price, even on an invoiced/paid WO | VIU-Pending | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: drive the inline part-number fix flow with seeded PO lines. | S10 Negative / S13-R6 / S13-R7 | needs-data | an invoiced/paid WO + a receive attempt (cannot receive without PN). | C29367 | https://shopview.testrail.io/index.php?/cases/view/29367
SF-PNFIX-06 | Inline Part-Number Fix (Story 10) | Verify the inline part-number save drives real catalog creation/linking, inventory stock and Part History (not just a stored string) | VIU-Pending | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: drive the inline part-number fix flow with seeded PO lines. | S10 Technical guardrails | needs-data | receiving + catalog/inventory back-end inspection (real creation/linking, not a stored string). | C29368 | https://shopview.testrail.io/index.php?/cases/view/29368
SF-RCV-01 | Receive Button on WO POs (Story 11) | Verify a Receive action appears on WO-originated POs in both the PO list and the PO detail card | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S11-R1 | — |  | C29369 | https://shopview.testrail.io/index.php?/cases/view/29369
SF-RCV-02 | Receive Button on WO POs (Story 11) | Verify the Receive action opens the shared Accept Delivery surface | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S11-R2 | — |  | C29370 | https://shopview.testrail.io/index.php?/cases/view/29370
SF-RCV-03 | Receive Button on WO POs (Story 11) | Verify the Receive action is hidden for office/readonly users and for fulfilled POs | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S11-R3 | — |  | C29371 | https://shopview.testrail.io/index.php?/cases/view/29371
SF-RCV-04 | Accept Delivery (Story 12) | Verify the existing Accept Delivery screen groups by vendor with per-group invoice #, date, tax, note and Receive | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S12 (existing multi-vendor) | — |  | C29372 | https://shopview.testrail.io/index.php?/cases/view/29372
SF-RCV-05 | Accept Delivery (Story 12) | Verify new vendorless/no-PN WO parts and WO-originated POs appear and are receivable on Accept Delivery, with the vendor-missing group at the top | VIU-Pending | BLOCKED | MILOS ANSWER | Milos (Product Owner) | Milos answers Open Question Q11 — Vendor-missing group ordering on Accept Delivery — spec contradicts itself. | Q11 ¦ S12-R1 | — |  | C29373 | https://shopview.testrail.io/index.php?/cases/view/29373
SF-RCV-06 | Accept Delivery (Story 12) | Verify Accept Delivery receive gates: vendor set, part number entered, cost / sell price entered, vendor invoice # captured | VIU-Pending | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: seed deliverable POs, drive the Receive / Accept-Delivery flow. | S12-R2 / S13-R6 / S13-R7 | needs-data | BATCH 6: on a deliverable WO PO the Accept Delivery gates are present (vendor set, invoice # field), but Receive 500s (BUG-11); on a vendor-missing WO PO there is no assign-vendor / PN-edit control. Happy path was proven on an INVENTORY PO in BATCH 5; the WO-PO negative sub-gates need BUG-11 fixed. | C29374 | https://shopview.testrail.io/index.php?/cases/view/29374
SF-RCV-07 | Accept Delivery (Story 12) | Verify Accept Delivery shows a '+N' vendor indicator and leads with the vendor-missing group | VIU-Pending | BLOCKED | MILOS ANSWER | Milos (Product Owner) | Milos answers Open Question Q11 — Vendor-missing group ordering (S12-R1 bottom vs S12-R3 top). | Q11 ¦ S12-R3 | — |  | C29375 | https://shopview.testrail.io/index.php?/cases/view/29375
SF-RCV-08 | Accept Delivery (Story 12) | Verify each vendor group produces its own vendor bill and separate AP entry in QuickBooks | Blocked-Env | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: seed deliverable POs, drive the Receive / Accept-Delivery flow. | S12-R4 | needs-data | QuickBooks inspection (per-vendor vendor bill + separate AP entry) — and WO-PO receive additionally blocked by BUG-11 (500). | C29376 | https://shopview.testrail.io/index.php?/cases/view/29376
SF-RCV-09 | Accept Delivery (Story 12) | Verify a 'received more than ordered' warning appears when received quantity exceeds ordered quantity | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S12 (existing) received-more-than-ordered | — |  | C29377 | https://shopview.testrail.io/index.php?/cases/view/29377
SF-RCV-10 | Accept Delivery (Story 12) | Verify cost is editable on the Accept Delivery screen when $0 or missing (parity with Bulk Receive) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S12-R5 | — |  | C29440 | https://shopview.testrail.io/index.php?/cases/view/29440
SF-VEND-01 | Assign Vendor + Merge (Story 13) | Verify the vendor-missing group provides a vendor dropdown that assigns a vendor at PO level and saves it | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S13-R1 | — |  | C29378 | https://shopview.testrail.io/index.php?/cases/view/29378
SF-VEND-02 | Assign Vendor + Merge (Story 13) | Verify assigning a vendor already on this PO prompts 'Add to {vendor}?' with Merge vs Keep Separate | VIU-Pending | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: seed vendor-missing POs, drive Assign-Vendor + merge. | S13-R2 | needs-data | a PO where the assigned vendor already exists on the PO (Add-to-vendor merge vs keep-separate prompt). | C29379 | https://shopview.testrail.io/index.php?/cases/view/29379
SF-VEND-03 | Assign Vendor + Merge (Story 13) | Verify assigning a vendor that is on another PO for the same WO prompts to merge the POs | VIU-Pending | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: seed vendor-missing POs, drive Assign-Vendor + merge. | S13-R3 | needs-data | two POs for the same WO with the same vendor (merge-POs prompt). | C29380 | https://shopview.testrail.io/index.php?/cases/view/29380
SF-VEND-04 | Assign Vendor + Merge (Story 13) | Verify assigning a different vendor with no collision auto-assigns and clears the QB flag, and Receive enables only once the part number and cost / sell price are also present | VIU-Pending | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: seed vendor-missing POs, drive Assign-Vendor + merge. | S13-R4 / S13-R5 / S13-R6 / S13-R7 | needs-data | a vendor-missing PO + receive-enable + QB-flag-clear check after auto-assign. | C29381 | https://shopview.testrail.io/index.php?/cases/view/29381
SF-VEND-05 | Assign Vendor + Merge (Story 13) | Verify vendor matching is by ID (not name), merge is scoped to the same WO, and receiving is blocked when the WO is invoiced/paid | VIU-Pending | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: seed vendor-missing POs, drive Assign-Vendor + merge. | S13 Technical guardrails | needs-data | invoiced/paid WO + multi-PO merge guardrail state (match-by-ID, merge scoped to same WO, receive blocked when invoiced/paid). | C29382 | https://shopview.testrail.io/index.php?/cases/view/29382
SF-VEND-06 | Assign Vendor + Merge (Story 13) | Verify a part cannot be received until a missing cost / sell price is entered | VIU-Pending | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: seed vendor-missing POs, drive Assign-Vendor + merge. | S13-R7 | reachable-now | admin+tech + normal WO data; needs another VIU pass (no new inputs). | C29442 | https://shopview.testrail.io/index.php?/cases/view/29442
SF-WOP-01 | Waiting on Parts Column (Story 14) | Verify an optional 'Waiting on Parts' column can be enabled from the column selector and shows the unreceived-parts count per WO | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S14-R1 | — |  | C29383 | https://shopview.testrail.io/index.php?/cases/view/29383
SF-WOP-02 | Waiting on Parts Column (Story 14) | Verify clicking the Waiting on Parts count opens Accept Delivery for the WO's first unreceived PO | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S14-R2 | — |  | C29384 | https://shopview.testrail.io/index.php?/cases/view/29384
SF-WOP-03 | Waiting on Parts Column (Story 14) | Verify a work order with nothing to receive shows '—' with no link in the Waiting on Parts column | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S14-R3 | — |  | C29385 | https://shopview.testrail.io/index.php?/cases/view/29385
SF-REV-01 | Review ON (Story 16) | Verify the Require Review setting drives the review flow when turned on | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | R1 | — |  | C29386 | https://shopview.testrail.io/index.php?/cases/view/29386
SF-REV-02 | Review ON (Story 16) | Verify the completion action reads 'Send To Review' when Require Review is on | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | R2 | — |  | C29387 | https://shopview.testrail.io/index.php?/cases/view/29387
SF-REV-03 | Review ON (Story 16) | Verify the Details step collects only mileage and engine hours when review is on (VIN captured later by reviewer) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | R3 | — |  | C29388 | https://shopview.testrail.io/index.php?/cases/view/29388
SF-REV-04 | Review ON (Story 16) | Verify 'Receive Parts' routes to the shared receive page (no inline modal) in the review flow | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | R4 | — |  | C29389 | https://shopview.testrail.io/index.php?/cases/view/29389
SF-REV-05 | Review ON (Story 16) | Verify Send to Review moves the WO to Review (amber) with a 'Ready for Review' banner and locks lines to Complete | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | R5 / R6 | — |  | C29390 | https://shopview.testrail.io/index.php?/cases/view/29390
SF-REV-06 | Review ON (Story 16) | Verify the Mark Reviewed dialog captures VIN (required) and disables Confirm until VIN is entered | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | R7 / R10 | — |  | C29391 | https://shopview.testrail.io/index.php?/cases/view/29391
SF-REV-07 | Review ON (Story 16) | Verify on Send to Review lines lock to Complete and inventory is auto-picked | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | R6 | — |  | C29392 | https://shopview.testrail.io/index.php?/cases/view/29392
SF-REV-08 | Review ON (Story 16) | Verify Confirm Review signs off and completes the work order directly (no distinct Reviewed holding state) | VIU-Verified | BLOCKED | MILOS ANSWER | Milos (Product Owner) | Milos answers Open Question Q8, Q4 — Distinct 'Reviewed' state before final Complete — expected or single-step? | Q8, Q4 ¦ R5 / R8 (direct sign-off, no separate Complete) | — |  | C29393 | https://shopview.testrail.io/index.php?/cases/view/29393
SF-REV-09 | Review ON (Story 16) | Verify Mark Reviewed is gated by the Review Work Orders permission and disabled for a role without it | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | R7 (role-gating) | — |  | C29394 | https://shopview.testrail.io/index.php?/cases/view/29394
SF-REV-10 | Review ON (Story 16) | Verify the Mark Reviewed dialog includes VIN / Serial # (required) with no review note field | VIU-Verified | BLOCKED | MILOS ANSWER | Milos (Product Owner) | Milos answers Open Question Q7 — Optional review-note field absent — descope or bug? | Q7 ¦ R7 (VIN required, no note) | — |  | C29395 | https://shopview.testrail.io/index.php?/cases/view/29395
SF-REV-11 | Review ON (Story 16) | Verify sign-off completes the work order directly (no separate final Complete) and invoicing is blocked until reviewed | VIU-Pending | BLOCKED | MILOS ANSWER | Milos (Product Owner) | Milos answers Open Question Q8 — Invoicing-blocked-until-reviewed depends on the Reviewed-state ruling (Q8). | Q8 ¦ R8 | — |  | C29396 | https://shopview.testrail.io/index.php?/cases/view/29396
SF-REV-12 | Review ON (Story 16) | Verify a 'Ready for Review' list filter/column surfaces the reviewer queue | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | R9 | — |  | C29397 | https://shopview.testrail.io/index.php?/cases/view/29397
SF-REV-13 | Review ON (Story 16) | Verify all lines must be approved before Send To Review (the 'Send To Review' action is disabled until every line is approved) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | R11 | — |  | C29398 | https://shopview.testrail.io/index.php?/cases/view/29398
SF-REV-14 | Review ON (Story 16) | Verify cores are resolved per rules before sign-off and invoicing is blocked until both Reviewed and all cores resolved | VIU-Pending | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: enable Require Review and drive the review/sign-off round-trip. | R Core parts / invoicing block | needs-data | cores + receiving in the review flow — blocked by BUG-10 (no wizard resolve step) + BUG-11 (WO-PO receive 500) + special-order cores not seedable. | C29399 | https://shopview.testrail.io/index.php?/cases/view/29399
SF-REV-15 | Review ON (Story 16) | Verify the Require Review default for new vs existing orgs matches the agreed cohort rule | Blocked-Env | BLOCKED | MILOS ANSWER | Milos (Product Owner) | Milos answers Open Question Q1 — Require-review default cohort rule + new-org preset. | Q1 ¦ R Open (default) | — |  | C29400 | https://shopview.testrail.io/index.php?/cases/view/29400
SF-UX-01 | UX Refinements (Story 15) | Verify the work order primary button reads 'Create Work Order' | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S15-R1 | — |  | C29401 | https://shopview.testrail.io/index.php?/cases/view/29401
SF-UX-02 | UX Refinements (Story 15) | Verify required fields at completion appear in a centralized center modal and the tech story is NOT in that modal | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S15-R2 | — |  | C29402 | https://shopview.testrail.io/index.php?/cases/view/29402
SF-UX-03 | UX Refinements (Story 15) | Verify the success screen shows WO number and total with Done and Go to Invoice, and the invoice number is on the Finance step | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S15-R3 | — |  | C29403 | https://shopview.testrail.io/index.php?/cases/view/29403
SF-UX-04 | UX Refinements (Story 15) | Verify the close-confirmation modal behavior (Close = closes modal only; Cancel = closes modal + returns to previous screen) | VIU-Pending | BLOCKED | MILOS ANSWER | Milos (Product Owner) | Milos answers Open Question Q10 — Close-vs-cancel confirm modal — design 'still to be added'. | Q10 ¦ S15-R4 | — |  | C29404 | https://shopview.testrail.io/index.php?/cases/view/29404
SF-PERM-01 | API — Permissions | Verify only owner/admin can view and modify Work Order settings (non-admin blocked) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S1 AC / §8 Permissions | — |  | C29405 | https://shopview.testrail.io/index.php?/cases/view/29405
SF-PERM-02 | Permissions | Verify which roles can complete a work order (Simple completion) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | §8 Permissions | — |  | C29406 | https://shopview.testrail.io/index.php?/cases/view/29406
SF-PERM-03 | Permissions | Verify which roles can perform Bulk Receive | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | §8 Permissions | — |  | C29407 | https://shopview.testrail.io/index.php?/cases/view/29407
SF-PERM-04 | Permissions | Verify which roles can Mark Reviewed (sign off) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | R7 / §8 role-gating review | — |  | C29408 | https://shopview.testrail.io/index.php?/cases/view/29408
SF-PERM-05 | Permissions | Verify the PO Receive button is hidden for office/readonly users | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S11-R3 | — |  | C29409 | https://shopview.testrail.io/index.php?/cases/view/29409
SF-PERM-06 | API — Permissions | Verify permission gating of Simple-Flow settings and work-order actions (UI gating is the v1 pass criterion) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | §8 BE enforcement | — |  | C29410 | https://shopview.testrail.io/index.php?/cases/view/29410
SF-PERM-07 | Permissions | Verify review sign-off is governed by the Review Work Orders custom-role permission (not open to all) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | §8 role-gating review | — |  | C29411 | https://shopview.testrail.io/index.php?/cases/view/29411
SF-PERM-08 | Permissions | Verify a user who holds the Mark Reviewed permission can Mark Reviewed a work order they completed | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | R7 (review sign-off) — self-review permission-gated (identity rule NOT in v1) | — |  | C29412 | https://shopview.testrail.io/index.php?/cases/view/29412
SF-PERM-09 | Permissions | Verify a Technician cannot add a vendorless / no-part-number part (lacks See Financial Data) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S5 / §9 (See Financial Data gate) | — |  | C29413 | https://shopview.testrail.io/index.php?/cases/view/29413
SF-PERM-10 | Permissions | Verify the Complete Work Order action follows the per-role completion permission matrix | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | §9 per-role completion matrix | — |  | C29414 | https://shopview.testrail.io/index.php?/cases/view/29414
SF-VAL-01 | Validation / Edge | Verify completion is blocked when required mileage is missing | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S2-R2 / S3-R3 / S4-R3 | — |  | C29415 | https://shopview.testrail.io/index.php?/cases/view/29415
SF-VAL-02 | Validation / Edge | Verify completion is blocked when a required VIN is missing (non-review No-PO / Optional-invoice flow) | VIU-Pending | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: drive the specific validation/edge scenario with seeded data. | S15-R2 / S3-R3 / S4-R3 | needs-data | an asset/vehicle with NO VIN so the non-review wizard prompts for VIN. BATCH 6: VIN prefills from the asset; the asset-creation flow (VIN likely required) was not reliably drivable in-harness. Needs a VIN-less asset seeded. | C29416 | https://shopview.testrail.io/index.php?/cases/view/29416
SF-VAL-03 | Validation / Edge | Verify completion is blocked when required engine hours are missing | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S3-R3 / S4-R3 | — |  | C29417 | https://shopview.testrail.io/index.php?/cases/view/29417
SF-VAL-04 | Validation / Edge | Verify the tech-story Next/Continue button stays disabled while the story textarea is empty | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | TS-R4 | — |  | C29418 | https://shopview.testrail.io/index.php?/cases/view/29418
SF-VAL-05 | Validation / Edge | Verify a required-invoice receive is blocked without a vendor invoice number | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S3-R3 / S4-R5 / §4 | — |  | C29419 | https://shopview.testrail.io/index.php?/cases/view/29419
SF-VAL-06 | Validation / Edge | Verify a vendor-missing part cannot be received without a vendor, a part number, and a cost / sell price | VIU-Pending | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: drive the specific validation/edge scenario with seeded data. | S10 / S12-R2 / S13-R6 / S13-R7 | needs-data | BATCH 6: blocked by BUG-11 (WO-PO receive 500) and no assign-vendor UI on the reachable receive surface. | C29420 | https://shopview.testrail.io/index.php?/cases/view/29420
SF-VAL-07 | Validation / Edge | Verify Confirm Review is disabled until a VIN is entered in the Mark Reviewed dialog | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | R7 | — |  | C29421 | https://shopview.testrail.io/index.php?/cases/view/29421
SF-VAL-08 | Validation / Edge | Verify re-completing after cancelling does not create duplicate POs | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S3-R9 (idempotency) | — |  | C29422 | https://shopview.testrail.io/index.php?/cases/view/29422
SF-VAL-09 | Validation / Edge | Verify the sell field is locked after the work order is invoiced/paid with a lock icon and tooltip | VIU-Pending | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: drive the specific validation/edge scenario with seeded data. | S8-R7 / §4 field locking | needs-data | RE-VIU 2026-07-09: Bulk Receive field-locking BUILT (qty/cost/sell editable verified); the sell-lock-after-invoiced/paid clause needs an invoiced/paid WO to drive. | C29423 | https://shopview.testrail.io/index.php?/cases/view/29423
SF-VAL-10 | Validation / Edge | Verify the same vendor invoice number can be reused across POs (uniqueness relaxed) | VIU-Verified | READY | READY (VIU-Verified) | — | None — VIU-verified; uploadable now. | S9-R3 / §4 (uniqueness relaxed) | — |  | C29424 | https://shopview.testrail.io/index.php?/cases/view/29424
SF-VAL-11 | Validation / Edge | Verify an unapproved line blocks completion — required-invoice shows a disabled Complete button with a tooltip; other flows show the approve-line error | VIU-Pending | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: drive the specific validation/edge scenario with seeded data. | S4-R8 / S3-R9 / Key Decision (line approval) | reachable-now | admin+tech + normal WO data; needs another VIU pass (no new inputs). | C29425 | https://shopview.testrail.io/index.php?/cases/view/29425
SF-QB-01 | QuickBooks / Inventory Integrity | Verify in-stock parts decrement inventory and write Part History on simple completion (skip path still runs lifecycle) | VIU-Pending | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: complete a WO end-to-end and inspect the QuickBooks / inventory side-effects (Journal Entry, Part History, inventory decrement). | §5 invariant 1 | needs-data | FRESH VIU 2026-07-10: decrement half PROVEN (P550848 on-hand 6->5 on pick, persisted through simple-complete 201). Part-History LOG surface BLOCKED-ENV: GET /api/inventory/parts/history -> 500; /parts/inventory/{id} detail page crashes ('page is totaled'); other history endpoints 404/405 (see bugs-log OBS-6). QuickBooks-integrity leg needs QB access. | C29426 | https://shopview.testrail.io/index.php?/cases/view/29426
SF-QB-02 | QuickBooks / Inventory Integrity | Verify Create POs OFF produces no PO, vendor bill or AP sync and no catalog/inventory sync | Blocked-Env | BLOCKED | MILOS ANSWER | Milos (Product Owner) | Milos answers Open Question Q5 — QuickBooks integrity when Create-POs is OFF (toggle absent). | Q5 ¦ §5 / §4 (Create POs OFF) | — |  | C29427 | https://shopview.testrail.io/index.php?/cases/view/29427
SF-QB-03 | QuickBooks / Inventory Integrity | Verify POs ON plus receiving runs the full pipeline: receive → Delivery → Vendor Bill → QuickBooks (both surfaces sync) | Blocked-Env | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: complete a WO end-to-end and inspect the QuickBooks / inventory side-effects (Journal Entry, Part History, inventory decrement). | §5 invariant 2 | needs-data | QuickBooks / inventory back-end inspection (receive -> Delivery -> Vendor Bill -> QBO) — likely needs dev/QB access. | C29428 | https://shopview.testrail.io/index.php?/cases/view/29428
SF-QB-04 | QuickBooks / Inventory Integrity | Verify a vendorless / no-PN part has zero inventory interaction until a vendor and/or part number is added | VIU-Pending | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: complete a WO end-to-end and inspect the QuickBooks / inventory side-effects (Journal Entry, Part History, inventory decrement). | §5 (vendorless/no-PN) | needs-data | QuickBooks / inventory inspection (vendorless/no-PN part = zero inventory interaction) — likely needs dev/QB access. | C29429 | https://shopview.testrail.io/index.php?/cases/view/29429
SF-QB-05 | QuickBooks / Inventory Integrity | Verify Vendor Missing POs are excluded from QuickBooks until a vendor and part number are provided | Blocked-Env | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: complete a WO end-to-end and inspect the QuickBooks / inventory side-effects (Journal Entry, Part History, inventory decrement). | §5 / S6-R3 | needs-data | QuickBooks inspection (Vendor-Missing POs excluded from QB until vendor + PN) — likely needs dev/QB access. | C29430 | https://shopview.testrail.io/index.php?/cases/view/29430
SF-QB-06 | QuickBooks / Inventory Integrity | Verify cost at completion behavior to avoid $0-cost margins in QuickBooks | Blocked-Env | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: complete a WO end-to-end and inspect the QuickBooks / inventory side-effects (Journal Entry, Part History, inventory decrement). | §8 (cost at completion) | needs-data | QuickBooks inspection (cost-at-completion to avoid $0-cost margins) — likely needs dev/QB access. | C29431 | https://shopview.testrail.io/index.php?/cases/view/29431
SF-QB-07 | QuickBooks / Inventory Integrity | Verify the Journal Entry / Inventory sync to QuickBooks fires on invoice creation (not PO-dependent) | Blocked-Env | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: complete a WO end-to-end and inspect the QuickBooks / inventory side-effects (Journal Entry, Part History, inventory decrement). | §5 (Journal Entry / Inventory → QBO) | needs-data | QuickBooks inspection (Journal Entry / Inventory sync fires on invoice creation) — likely needs dev/QB access. | C29432 | https://shopview.testrail.io/index.php?/cases/view/29432
SF-QB-08 | QuickBooks / Inventory Integrity | Verify Inventory Part History is preserved for any part that becomes inventory-tracked | VIU-Pending | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: complete a WO end-to-end and inspect the QuickBooks / inventory side-effects (Journal Entry, Part History, inventory decrement). | §5 invariant 3 | needs-data | Inventory Part History inspection for any part that becomes inventory-tracked — likely needs dev/QB access. | C29433 | https://shopview.testrail.io/index.php?/cases/view/29433
SF-QB-09 | QuickBooks / Inventory Integrity | Investigate: Part Sales unaffected by the shared order/status logic (requested -> orderable/waiting-to-receive) | Open-Question | BLOCKED | VIU PENDING (QA) | QA (needs cookies+seed data) | QA VIU: complete a WO end-to-end and inspect the QuickBooks / inventory side-effects (Journal Entry, Part History, inventory decrement). | §8 open question (Part Sales impact — BE investigation) | reachable-now | admin+tech + normal WO data; needs another VIU pass (no new inputs).

## Summary
Simple Flow — Blockers Tracker · Summary
Total authored cases | 163
Blocker category | Count | Owner
READY (VIU-Verified) | 112 | — (ready to upload)
BLOCKED — DEV NOT BUILT | 0 | Dev team
BLOCKED — VIU PENDING (QA) | 38 | QA
BLOCKED — MILOS ANSWER | 13 | Milos (PO)
BLOCKED — BUG/RULING | 0 | Dev / PO ruling
TOTAL | 163
DEV NOT BUILT — by story | Count
VIU PENDING (QA) — by sub-bucket | Count | Meaning
reachable-now | 6 | admin+tech + normal data; just needs another VIU pass (no new inputs).
needs-data | 32 | needs a data state not seedable via the app (see per-case detail).
needs-account | 0 | needs a role account we don't have (see per-case detail).
TOTAL VIU PENDING (QA) | 38
WHAT TO SEND ME NEXT (to unblock each batch)
• Milos's answers to the 11 Open Questions | unblocks 13 cases (all the MILOS-ANSWER rows). Send the filled-in OpenQuestions-for-Milos sheet.
• Fresh QA cookies for sv7301 (admin + tech) + seeded test data | unblocks the bulk of the 38 VIU-PENDING (QA) cases (cores, receiving, vendor, validation round-trips).
• A 2nd/3rd role account (Office, Service Manager, Foreman) — some WITHOUT 'See Financial Data' | unblocks SF-PERM-09 and SF-PERM-10 (per-role completion + vendorless-add gate).
• A dev/PO ruling on FE-only BE enforcement + the missing reviewer!=completer rule (resolve SV-8183 'BE enforces' vs SV-7864 atom-collapse) | finalizes the 0 BUG/RULING cases.