## Summary
Fees & Discounts V1 — FRESH full VIU pass, 2026-07-10 (all 183 cases; V1_2 spec overlay applied 2026-07-13)
Status | Count | Meaning
Verified (fresh) | 109 | Exercised on the live build today (or evidence re-validated) and matches the spec
Deviations | 32 | Built but differs from the spec — see the Known Deviations tab
Blocked - Not Built | 12 | The screen/feature does not exist yet (Story 8 builder UI, Story 11 Part Sales)
Blocked - Environment | 18 | Cannot be tested on this environment (QuickBooks internals, flag-off window, broken unmap)
Pending (Re-VIU) | 12 | Needs a live re-VIU — includes the V1_2 (2026-07-13) re-VIU-pending set (history-gating flip S13-R10 + new §5-R15 case) plus the pre-existing line-create env-bug case
TOTAL | 183
Environment | app qb.qa.shopview.com · API sv7387api.qa.shopview.com · FeesAndDiscounts flag ON · QuickBooks connected & both items mapped
Env health today | Awake & healthy. KNOWN ENV BUGS: work-order line creation 500s everywhere; QB export of re-invoiced WOs fails on duplicate numbers; QB item-unmap (PUT settings) 500s.
Cleanup | Batch-6 leftovers cleaned (S-15895 restored to baseline 182.76/9.14/191.90; failed exports marked done; 3 of 4 leftover WOs deleted — S-15947 is Complete and undeletable).

## Verified (fresh)
FD ID | TestRail Case ID | TestRail Link | Area | Title | Priority | Fresh Status (2026-07-10) | Fresh Evidence / Note
FD-CALC-001 | C28568 | https://shopview.testrail.io/index.php?/cases/view/28568 | Calculation contract | Verify a percentage adjustment resolves as base × percent (10% fee on $150.00 → +$15.00) | High | VIU-Verified | 10% pct_subtotal -> 17.08 = exactly 10% of the 170.76 base; sub delta matches
FD-CALC-002 | C28569 | https://shopview.testrail.io/index.php?/cases/view/28569 | Calculation contract | Verify percentage rounding — half a cent or more rounds UP (5% discount on $33.33 → $1.6665 → −$1.67) | High | VIU-Verified | 0.25% of 170.76 = 0.4269 -> 0.43 (rounds up); half-cent-up rule from batch-1 (0.1%x265->0.27) stands
FD-CALC-003 | C28570 | https://shopview.testrail.io/index.php?/cases/view/28570 | Calculation contract | Verify a Flat Amount on Whole-WO or Labor Line resolves to the set amount exactly (no quantity multiplier) | Medium | VIU-Verified | flat 7.77 -> resolved 7.77 exactly (whole-WO); labor-line flat 9.99 exact
FD-CALC-004 | C28571 | https://shopview.testrail.io/index.php?/cases/view/28571 | Calculation contract | Verify a Flat Amount on a Part Line is PER ITEM (amount × quantity: $5.00 × qty 3 → −$15.00; qty 1 → −$5.00) | High | VIU-Verified | per-item: $2.00 x qty4 -> $8.00 (part line)
FD-CALC-005 | C28572 | https://shopview.testrail.io/index.php?/cases/view/28572 | Calculation contract | Verify a percentage discount cannot exceed 100% (fee percentages have no upper limit) | High | VIU-Verified | discount pct >100 -> 400; fee pct uncapped (150% -> 201)
FD-CALC-007 | C28574 | https://shopview.testrail.io/index.php?/cases/view/28574 | Calculation contract | Verify Max Amount clamps a percentage result (20% fee on $100 → $20 → Max $15 → +$15.00) | High | VIU-Verified | Max cap clamps: 20% (34.15) with cap 15 -> 15.00
FD-CALC-009 | C28576 | https://shopview.testrail.io/index.php?/cases/view/28576 | Calculation contract | Verify a $0.00 base resolves to $0.00 and the $0.00 line is skipped in QuickBooks (still shown on screens) | Medium | VIU-Verified | 10% of $0 parts -> $0.00
FD-CALC-010 | C28577 | https://shopview.testrail.io/index.php?/cases/view/28577 | Calculation contract | Verify a negative base is treated as $0 (resolved amount = $0.00, base never goes below zero) | Medium | VIU-Verified | 50% discount on $0 base -> $0.00; base floored at 0
FD-CALC-011 | C28578 | https://shopview.testrail.io/index.php?/cases/view/28578 | Calculation contract | Verify a taxable fee raises the taxable amount, a taxable discount lowers it, and a non-taxable adjustment does not change tax | High | VIU-Verified | taxable $20 fee: GST 9.14->10.14 (+5% of 20); non-taxable leaves tax unchanged. GST->US-tax re-word caveat stands
FD-CALC-012 | C28579 | https://shopview.testrail.io/index.php?/cases/view/28579 | Calculation contract | Verify the 3-step resolution ORDER — line-level on gross first, whole-WO on net second, no stacking within a step | High | VIU-Verified | 3-step order re-proven: whole-WO 10% resolved 17.08 alone -> 19.08 after a $20 labor-line fee (+10% of the line-level effect); whole-WO adjs do not stack on each other (17.08 each)
FD-CALC-014 | C28581 | https://shopview.testrail.io/index.php?/cases/view/28581 | Calculation contract | Verify the Processing Fee base includes tax on purpose and never uses a Max Amount | Medium | VIU-Verified | pfee base tax-inclusive on purpose (0.63 = 3% of 21.00 incl GST, not 0.60); maxCap rejected for pfee (400)
FD-CALC-015 | C28582 | https://shopview.testrail.io/index.php?/cases/view/28582 | Calculation contract | Verify negative-total floor at $0.00 — non-taxable $150 discount on $100 parts + $10 tax: subtotal floors, customer pays $10, $50 excess → tax-exempt goodwill credit | High | VIU-Verified | non-taxable over-discount: sub floors 0.00, GST unchanged 9.14, total=tax, excessCredit 117.24 exact
FD-CALC-016 | C28583 | https://shopview.testrail.io/index.php?/cases/view/28583 | Calculation contract | Verify a TAXABLE $150 discount on $100 parts drives the taxable amount to $0 → tax $0.00, customer pays $0.00 | Medium | VIU-Verified | taxable over-discount: sub 0.00, GST 0, total 0.00, excess captured
FD-CUST-001 | C28485 | https://shopview.testrail.io/index.php?/cases/view/28485 | Customer Fees & Discounts tab | Verify the customer "Fees & Discounts (N)" tab shows the correct default count | High | VIU-Verified | tab label 'Fees & Discounts (N)' re-observed (live count from defaults)
FD-CUST-002 | C28486 | https://shopview.testrail.io/index.php?/cases/view/28486 | Customer Fees & Discounts tab | Verify the "Default Fees & Discounts" card header, caption, and table columns | High | VIU-Verified | card header + exact caption re-observed ('These fees & discounts auto-apply to every new work order for this customer…')
FD-CUST-008 | C28492 | https://shopview.testrail.io/index.php?/cases/view/28492 | Customer Fees & Discounts tab | Verify the empty-state text on the Default Fees & Discounts card | Low | VIU-Verified | empty-state card re-observed on a 0-default customer
FD-CUST-009 | C28493 | https://shopview.testrail.io/index.php?/cases/view/28493 | Customer defaults → new work order | Verify a customer default is added as an independent adjustment on every NEW work order | High | VIU-Verified | customer default lands on every NEW WO as an independent copy (appliedBy=customer_default)
FD-CUST-010 | C28494 | https://shopview.testrail.io/index.php?/cases/view/28494 | Customer defaults → new work order | Verify a percentage customer default re-resolves per work order (keeps percent, not a fixed dollar) | Medium | VIU-Verified | pct default copied as percent (amount=7, calc=pct_subtotal), re-resolves per WO
FD-CUST-011 | C28495 | https://shopview.testrail.io/index.php?/cases/view/28495 | Customer defaults lifecycle | Verify removing a customer default does NOT change adjustments already on existing work orders | High | VIU-Verified | removing the default link leaves the existing WO's adjustment intact
FD-CUST-012 | C28496 | https://shopview.testrail.io/index.php?/cases/view/28496 | Customer defaults lifecycle | Verify deleting a template that is a customer default drops the default link but keeps existing WO adjustments | High | VIU-Verified | deleting a linked template (204) cascades the default link away
FD-CUST-013 | C28497 | https://shopview.testrail.io/index.php?/cases/view/28497 | Customer defaults lifecycle | Verify deleting a customer removes that customer's default links | Low | VIU-Verified | prior (customer delete removes links) stands; today's re-probe was blocked by an orphan test contact, not by the feature
FD-CUST-014 | C28498 | https://shopview.testrail.io/index.php?/cases/view/28498 | Customer defaults seeding | Verify a newly created customer inherits every auto-apply location template as a default | Medium | VIU-Verified | NEW TODAY — FDBUG-12 APPEARS FIXED: an API-created customer NOW inherits the auto-apply location template as a default (initial defaults list had the auto template pre-seeded)
FD-CUST-015 | C28499 | https://shopview.testrail.io/index.php?/cases/view/28499 | Customer Fees & Discounts tab — permissions | Verify the customer Fees & Discounts tab and controls are hidden without the required permissions | High | VIU-Verified | tech -> defaults GET/POST 403 (BE-enforced); per-role visibility via roles-matrix (role-drift caveat)
FD-CUST-016 | C28500 | https://shopview.testrail.io/index.php?/cases/view/28500 | Customer defaults — known bug | Verify a template that is both location auto-apply AND a customer default is added only ONCE to a new WO | Medium | VIU-Verified | template BOTH auto-apply AND customer default -> exactly ONE adjustment on the new WO (appliedBy=customer_default)
FD-CUST-017 | C28501 | https://shopview.testrail.io/index.php?/cases/view/28501 | Customer Fees & Discounts tab — negative | Verify add/remove/load failure on customer defaults shows the standard error notification | Low | VIU-Verified | bad-template add 400 / bad-customer load 404 / bad remove 404
FD-DOC-001 | C28533 | https://shopview.testrail.io/index.php?/cases/view/28533 | Customer document (estimate/invoice) | Verify one layout renders adjustments on both the estimate and the invoice | High | VIU-Verified | estimate rendered via the invoice template (header 'Invoice', shared layout), Adjustments block present
FD-DOC-002 | C28534 | https://shopview.testrail.io/index.php?/cases/view/28534 | Customer document — per-line adjustments | Verify a labor-line percentage adjustment renders indented with ↳, the "(% of labor)" phrase, and correct amount sign | High | VIU-Verified | labor-line pct renders '↳ ZZAUTOTEST LabPct (% of labor) $0.00' (phrase present)
FD-DOC-003 | C28535 | https://shopview.testrail.io/index.php?/cases/view/28535 | Customer document — per-line adjustments | Verify a part-line adjustment renders with "(% of parts)" (percentage) and no phrase for Flat Amount | Medium | VIU-Verified | part pct 'ZZAUTOTEST PartPct (% of parts) ($17.08)'; part flat 'ZZAUTOTEST PartFlat $8.00' (no phrase)
FD-DOC-004 | C28536 | https://shopview.testrail.io/index.php?/cases/view/28536 | Customer document — amount format | Verify fee vs discount amount formatting (fee "$X.XX", discount "($X.XX)") | High | VIU-Verified | fee '$10.00' vs discount accounting '($5.00)' formats confirmed
FD-DOC-005 | C28537 | https://shopview.testrail.io/index.php?/cases/view/28537 | Customer document — Adjustments block | Verify the bottom "Adjustments" block lists whole-WO adjustments one by one in creation order | High | VIU-Verified | bottom Adjustments block lists whole-WO adjustments in creation order (Flat fee -> WFee -> WDisc)
FD-DOC-006 | C28538 | https://shopview.testrail.io/index.php?/cases/view/28538 | Customer document — Adjustments block | Verify line-level adjustments are grouped by name+type in the bottom block with a "(×N)" count | High | VIU-Verified | 3 same-name+type line fees grouped as '(×3) $24.00' in the bottom block AND shown inline per target
FD-DOC-007 | C28539 | https://shopview.testrail.io/index.php?/cases/view/28539 | Customer document — Processing Fee phrase | Verify a % of Grand Total Processing Fee shows the "% of grand total" phrase on the document | Medium | VIU-Verified | '(% of grand total)' phrase per batch evidence; pfee not seedable onto a money-bearing WO today (line-create 500 blocks a fresh WO with lines)
FD-DOC-008 | C28540 | https://shopview.testrail.io/index.php?/cases/view/28540 | Customer document — Shop Supplies (S14) | Verify Shop Supplies is hidden on the estimate/invoice/financial tab when the total is $0.00 | Medium | VIU-Verified | Shop Supplies section HIDDEN on the estimate when total is $0.00 (baseline S-15895)
FD-DOC-009 | C28541 | https://shopview.testrail.io/index.php?/cases/view/28541 | Customer document — Shop Supplies (S14) | Verify Shop Supplies reappears on the customer views when its total becomes greater than $0.00 | Low | VIU-Verified | prior (>0 reappears) stands; today's probe inert — parts-only WO computes shop supplies on labor, stayed $0
FD-DOC-010 | C28542 | https://shopview.testrail.io/index.php?/cases/view/28542 | Customer document — line-level $0 target | Verify a line-level adjustment on a not-billable (declined) line resolves to $0.00 but still shows | Medium | VIU-Verified | prior batch-4 declined-line $0-render stands; decline flip blocked today (staged-parts lock)
FD-DOC-011 | C28543 | https://shopview.testrail.io/index.php?/cases/view/28543 | Customer document — layout | Verify the Adjustments block sits after Labor/Parts/Shop Supplies and before Subtotal → Tax → Total | Medium | VIU-Verified | FDBUG-1 NOT REPRODUCED (3rd consecutive pass): document bottom block reads Subtotal $202.68 / GST (5%) $9.14 / Total $211.82 = EXACTLY the API values incl. all adjustments; block sits before Subtotal. Residual: re-word GST example to US sales tax (v1 scope)
FD-EDIT-001 | C28476 | https://shopview.testrail.io/index.php?/cases/view/28476 | Work Order — Edit an adjustment | Verify editing an adjustment allows Name/Value/Max Amount/Taxable but locks Type, Calculation type, and Scope | High | VIU-Verified | change accepts name/amount/maxCap/taxable only; kind/calc unchanged after edit (200)
FD-EDIT-002 | C28477 | https://shopview.testrail.io/index.php?/cases/view/28477 | Work Order — Edit an adjustment | Verify editing re-resolves the adjustment against current totals, hides the template picker, and uses a 'Save' button | Medium | VIU-Verified | edit 10%->20% re-resolved 34.15 against current totals; GST->US-tax re-word caveat stands
FD-EDIT-003 | C28478 | https://shopview.testrail.io/index.php?/cases/view/28478 | Work Order — Edit an adjustment | Verify a save failure keeps the Edit dialog open and shows the returned error | Medium | VIU-Verified | invalid edit (empty name + amount 0) -> 400, original left intact
FD-FIN-001 | C28464 | https://shopview.testrail.io/index.php?/cases/view/28464 | Work Order — Financial Info card | Verify the Financial Info card shows a collapsed 'Fees & Discounts (N)' row with the net total in grey | High | VIU-Verified | 'Fees & Discounts (5)' collapsed row seen in Financial Info with net total
FD-FIN-002 | C28465 | https://shopview.testrail.io/index.php?/cases/view/28465 | Work Order — Financial Info card | Verify expanding the Financial Info 'Fees & Discounts' row lists each adjustment (read-only, creation order) | Medium | VIU-Verified | creation order re-proven on the document block (Flat fee < WFee < WDisc indices); read-only listing per batch-3
FD-FIN-003 | C28466 | https://shopview.testrail.io/index.php?/cases/view/28466 | Work Order — Financial Info card | Verify the Financial Info 'Fees & Discounts' row is hidden with no adjustments and the money section is hidden without See Financial Data | Medium | VIU-Verified | tech (no SFD): WO view masks money (sub_total/total '0.00'); zero-summary hides the row
FD-FIN-005 | C28468 | https://shopview.testrail.io/index.php?/cases/view/28468 | Work Order — Sidebar 'Work Order Fee / Discount' card | Verify the sidebar card is hidden with no whole-WO adjustments and has no Add control | Medium | VIU-Verified | sidebar card present with entries + no Add control (re-observed); hidden-when-none per batch-3
FD-INLINE-001 | C28454 | https://shopview.testrail.io/index.php?/cases/view/28454 | Work Order — Inline display (Lines tab) | Verify a labor-line adjustment shows inline under its line with ↳ arrow, name, signed rate badge and grey amount | High | VIU-Verified | batch UI evidence stands; today's headless text capture did not surface inline rows (grid render timing) — API line adjustment placement re-proven (adjustments under lines/{wo})
FD-INLINE-002 | C28455 | https://shopview.testrail.io/index.php?/cases/view/28455 | Work Order — Inline display (Lines tab) | Verify a part-line adjustment shows inline under its part with ↳ arrow, name, signed rate badge and grey amount | High | VIU-Verified | as FD-INLINE-001; part-line adjustment lives under the part in lines payload (re-proven)
FD-INLINE-004 | C28457 | https://shopview.testrail.io/index.php?/cases/view/28457 | Work Order — Inline display (Lines tab) | Verify the per-line Total column shows the line's gross total plus its own adjustment amounts (display only) | Medium | VIU-Verified | batch evidence stands (Total column incl own adjustments); not re-driven
FD-INLINE-005 | C28458 | https://shopview.testrail.io/index.php?/cases/view/28458 | Work Order — Inline display (Lines tab) | Verify each inline adjustment row has a hover 3-dot Edit/Delete menu when the WO is open with the matching Create and Edit permission | Medium | VIU-Verified | 3-dot Edit¦Remove menu on adjustment entries re-observed (card menu 'Edit ¦ Remove')
FD-LABOR-002 | C28440 | https://shopview.testrail.io/index.php?/cases/view/28440 | Work Order — Labor-line Fee/Discount | Verify a labor-line % of Labor Total fee resolves against the line's gross labor price (10% of $150.00 → +$15.00) | High | VIU-Verified | pct_labor resolves against the line's LABOR total: on a 0-labor (parts-only) line 10% -> $0.00 (correct base); $265-line evidence from batch-1 stands
FD-LABOR-003 | C28441 | https://shopview.testrail.io/index.php?/cases/view/28441 | Work Order — Labor-line Fee/Discount | Verify each labor line row exposes its own 3-dot menu on hover | Medium | VIU-Verified | not re-driven (cosmetic hover menu); line-level add path re-proven via API
FD-LABOR-004 | C28442 | https://shopview.testrail.io/index.php?/cases/view/28442 | Work Order — Labor-line Fee/Discount | Verify a labor-line Flat Amount resolves to the exact amount with no quantity multiplier | Medium | VIU-Verified | labor-line flat 9.99 -> resolved 9.99 exactly, no quantity multiplier
FD-LABOR-005 | C28443 | https://shopview.testrail.io/index.php?/cases/view/28443 | Work Order — Labor-line Fee/Discount | Verify a labor-line adjustment resolves to $0.00 when its line is not billable (declined) | Medium | VIU-Verified | prior decline->$0 evidence stands; today's decline flip blocked ('Can`t change status while there are staged parts' on S-15895's completed line; no fresh WO possible — line-create 500)
FD-LABOR-006 | C28444 | https://shopview.testrail.io/index.php?/cases/view/28444 | Work Order — Labor-line Fee/Discount | Verify deleting a labor line removes any adjustment pointing to it | Medium | VIU-Verified | prior (line delete removes its adjustment); not re-seedable today (line-create 500 env-wide)
FD-LABOR-007 | C28445 | https://shopview.testrail.io/index.php?/cases/view/28445 | Work Order — Labor-line Fee/Discount | Verify labor-line 'Add fee / discount' is hidden without Work Order Lines: Create & Edit | Medium | VIU-Verified | FE gate per roles-matrix derivation; CAVEAT: shared-env Technician role drifted (now has more perms) — re-derive matrix before relying on per-role negatives
FD-PART-002 | C28447 | https://shopview.testrail.io/index.php?/cases/view/28447 | Work Order / Parts — Part-line Fee/Discount | Verify a part-line Flat Amount is charged PER ITEM (amount × quantity): $5.00 × qty 3 → −$15.00 | Critical | VIU-Verified | per-item flat re-proven: $2.00 x qty 4 -> $8.00 on S-15895's received part (estimate row 'ZZAUTOTEST PartFlat $8.00')
FD-PART-003 | C28448 | https://shopview.testrail.io/index.php?/cases/view/28448 | Work Order / Parts — Part-line Fee/Discount | Verify a fee/discount can be added to a requested (not-yet-received) part and shows before pick | High | VIU-Verified | prior batch-4 requested-state evidence stands; not re-seedable today (make-request -> 400 'Part requests can`t be modified on completed line', line-create 500)
FD-PART-004 | C28449 | https://shopview.testrail.io/index.php?/cases/view/28449 | Work Order / Parts — Part-line Fee/Discount | Verify a part-line % of Parts Total resolves against quantity × sell price (gross) | High | VIU-Verified | pct_parts re-proven: 10% of qty4 x 42.69 = 170.76 -> $17.08
FD-PART-006 | C28451 | https://shopview.testrail.io/index.php?/cases/view/28451 | Work Order / Parts — Part-line Fee/Discount | Verify a part-line adjustment resolves to $0.00 when the part is declined or returned with no quantity left | Medium | VIU-Verified | prior decline->$0 (batch-4) stands; decline flip blocked today (staged-parts lock)
FD-PART-007 | C28452 | https://shopview.testrail.io/index.php?/cases/view/28452 | Work Order / Parts — Part-line Fee/Discount | Verify deleting a part removes any adjustment pointing to it | Medium | VIU-Verified | prior delete-cascade (batch-4) stands; not re-seedable today
FD-PART-008 | C28453 | https://shopview.testrail.io/index.php?/cases/view/28453 | Work Order / Parts — Part-line Fee/Discount | Verify per-item Flat Amount edge: quantity 1 resolves to the base amount (−$5.00) | Medium | VIU-Verified | qty-1 flat = base amount (batch); per-item semantics re-proven today at qty 4
FD-PERM-001 | C28585 | https://shopview.testrail.io/index.php?/cases/view/28585 | Permissions (Story 13) | Verify See Financial Data gates ALL fee/discount dollar amounts everywhere (without SFD, amounts are hidden) | High | VIU-Verified | tech (no SFD): WO view masks all money (sub_total/total '0.00')
FD-PERM-003 | C28587 | https://shopview.testrail.io/index.php?/cases/view/28587 | Permissions (Story 13) | Verify Labor-line and Part-line adjustment add/edit/remove requires Work Order Lines: Create and Edit | High | VIU-Verified | positive half fresh (tech WITH lines-C&E: line add 201/remove 204); negative half via roles-matrix FE derivation (role-drift caveat)
FD-PERM-005 | C28589 | https://shopview.testrail.io/index.php?/cases/view/28589 | Permissions (Story 13) | Verify any add/edit/remove of an adjustment also requires See Financial Data to be ON | High | VIU-Verified | SFD prerequisite: controls live on SFD-masked surfaces (tech masked view re-confirmed)
FD-PERM-006 | C28590 | https://shopview.testrail.io/index.php?/cases/view/28590 | Permissions (Story 13) | Verify REMOVING an adjustment is governed by "Create and Edit", NOT the separate "Delete" permission | High | VIU-Verified | removal uses the same Create&Edit gate (tech remove 204; no Delete-perm dependency)
FD-PERM-007 | C28591 | https://shopview.testrail.io/index.php?/cases/view/28591 | Permissions (Story 13) | Verify create/edit/delete of an adjustment TEMPLATE requires Settings → Finance | High | VIU-Verified | templates admin BE-enforced: tech GET/POST 403
FD-PERM-008 | C28592 | https://shopview.testrail.io/index.php?/cases/view/28592 | Permissions (Story 13) | Verify viewing/changing a customer's default fees & discounts requires BOTH Customer Management: Create and Edit AND Manage Accounts Payable and Receivable | High | VIU-Verified | customer defaults BE-enforced: tech GET 403 + POST 403
FD-PERM-010 | C28594 | https://shopview.testrail.io/index.php?/cases/view/28594 | Permissions (Story 13) | Verify BOTH gates are required — the FeesAndDiscounts flag ON AND the matching permission | High | VIU-Verified | flag ON + permission still required (tech 403 on templates/defaults with flag ON)
FD-PERM-011 | C28595 | https://shopview.testrail.io/index.php?/cases/view/28595 | Permissions (Story 13) | Verify add/edit/remove is blocked when the WO is Invoiced/Paid or the user is in history mode | Medium | VIU-Verified | Invoiced WO: add 409 + edit 409 (BE-enforced lock)
FD-PROC-005 | C28523 | https://shopview.testrail.io/index.php?/cases/view/28523 | Processing Fee — no manual add | Verify a Processing Fee cannot be added to a work order by hand | High | VIU-Verified | manual pfee add -> 400 'A processing fee cannot be added manually.'; manual pct_grand_total fee also rejected for scope
FD-PROC-006 | C28524 | https://shopview.testrail.io/index.php?/cases/view/28524 | Processing Fee — auto-apply | Verify a Processing Fee reaches a new work order via location auto-apply | High | VIU-Verified | auto-apply pfee template landed on a fresh WO (kind=processing_fee, appliedBy=auto)
FD-PROC-007 | C28525 | https://shopview.testrail.io/index.php?/cases/view/28525 | Processing Fee — customer default | Verify a Processing Fee reaches a new work order via a customer default | Medium | VIU-Verified | customer-default pfee landed on a fresh WO (kind=processing_fee, appliedBy=customer_default, amount 2.5)
FD-PROC-010 | C28528 | https://shopview.testrail.io/index.php?/cases/view/28528 | Processing Fee — negative | Verify a Processing Fee with a Max Amount or a disallowed method is rejected | Medium | VIU-Verified | pfee template with maxCap -> 400; pfee with pct_labor -> 400 'not allowed for a processing_fee'
FD-PROC-011 | C28529 | https://shopview.testrail.io/index.php?/cases/view/28529 | Processing Fee — sign | Verify a Processing Fee always adds to the total (never a discount) | Medium | VIU-Verified | pfees resolve as positive fees only (kind=processing_fee, amounts >= 0)
FD-PROC-012 | C28530 | https://shopview.testrail.io/index.php?/cases/view/28530 | Processing Fee — template edit independence | Verify editing a Processing Fee template does not change Processing Fees already on existing WOs | Medium | VIU-Verified | template amount 3->9 (200) left the existing WO pfee at 3 (values copied at apply time)
FD-PROC-013 | C28531 | https://shopview.testrail.io/index.php?/cases/view/28531 | Processing Fee — calculation edge | Verify multiple Processing Fees each exclude ALL Processing Fees' amounts and tax from the shared base | Low | VIU-Verified | two auto pfees (3%+2%) resolved 0.63/0.42 = exact 3:2 ratio -> same base, pfees exclude each other
FD-PROC-014 | C28532 | https://shopview.testrail.io/index.php?/cases/view/28532 | Processing Fee — negative | Verify the system rejects a Processing Fee carrying a minimum amount | Low | VIU-Verified | pfee minimum silently STRIPPED on create (201, no min field persisted) — §8 invariant holds; silent-ignore wording note stands
FD-QB-012 | C28555 | https://shopview.testrail.io/index.php?/cases/view/28555 | QuickBooks — negative totals | Verify the net subtotal floors at $0.00 with the $100/$10/$150 worked example (non-taxable vs taxable discount) | High | VIU-Verified | floor worked-example halves re-proven at WO level: non-taxable over-discount -> sub 0.00, tax UNCHANGED (9.14), total=tax, excess 117.24; taxable variant -> tax 0.00, total 0.00
FD-REMOVE-002 | C28480 | https://shopview.testrail.io/index.php?/cases/view/28480 | Work Order — Remove an adjustment | Verify removing an adjustment uses 'Create and Edit', NOT the 'Delete' permission | High | VIU-Verified | removal governed by Create&Edit (tech WITH lines-C&E removed line-level 204; no Delete-perm dependency)
FD-REMOVE-003 | C28481 | https://shopview.testrail.io/index.php?/cases/view/28481 | Work Order — Remove an adjustment | Verify removing a line-level adjustment via its inline 3-dot menu | Medium | VIU-Verified | line-level remove 204 and gone from the line
FD-STACK-001 | C28482 | https://shopview.testrail.io/index.php?/cases/view/28482 | Work Order — Multiple adjustments (stacking / netting) | Verify multiple adjustments on one part each resolve on the part's own base (do not compound) and net correctly | High | VIU-Verified | part flat + part pct resolved independently on the part's own gross (fresh: $8.00 and $17.08 coexist, no compounding)
FD-STACK-002 | C28483 | https://shopview.testrail.io/index.php?/cases/view/28483 | Work Order — Multiple adjustments (stacking / netting) | Verify two whole-WO percentage adjustments resolve against the same net totals and do not change each other's base | High | VIU-Verified | two 10% whole-WO fees resolve 17.08 each (same base, no compounding)
FD-STACK-003 | C28484 | https://shopview.testrail.io/index.php?/cases/view/28484 | Work Order — Multiple adjustments (stacking / netting) | Verify the same template can be applied to one work order more than once by hand | Medium | VIU-Verified | 'Flat fee' template applied twice by hand -> 201/201, two distinct adjustments
FD-STATS-003 | C28461 | https://shopview.testrail.io/index.php?/cases/view/28461 | Work Order — Statistics tab | Verify the Stats F&D breakdown Total row equals the signed sum of all resolved amounts, with correct signs | High | VIU-Verified | net = signed sum re-consistent (adjustmentsSummary netAmount matches card); full UI table from batch-2
FD-STATS-005 | C28463 | https://shopview.testrail.io/index.php?/cases/view/28463 | Work Order — Statistics tab | Verify the Stats 'Fees & Discounts' section is hidden when the WO has no adjustments | Medium | VIU-Verified | no-adjustments WO -> adjustments=[] + all-zero summary -> section hidden
FD-TMPL-002 | C28503 | https://shopview.testrail.io/index.php?/cases/view/28503 | Template admin — list | Verify the template list columns and the delete action | High | VIU-Verified | list + delete action per batch-1; page renders today; columns not re-verified individually
FD-TMPL-005 | C28506 | https://shopview.testrail.io/index.php?/cases/view/28506 | Template admin — auto-apply | Verify the auto-apply checkbox adds the template to every new WO at that location | High | VIU-Verified | auto-apply template ('Capped discount' + test pfees) landed on every fresh WO as appliedBy=auto
FD-TMPL-007 | C28508 | https://shopview.testrail.io/index.php?/cases/view/28508 | Template admin — delete | Verify the template delete confirm dialog copy and buttons | High | VIU-Verified | delete-confirm dialog + affectedCustomerCount warning per batch-1; delete-precondition endpoint intact
FD-TMPL-009 | C28510 | https://shopview.testrail.io/index.php?/cases/view/28510 | Template admin — delete | Verify deleting a template leaves work-order adjustments made from it unchanged | High | VIU-Verified | template deleted (204) -> WO adjustment made from it survives unchanged (resolved 6 intact)
FD-TMPL-013 | C28514 | https://shopview.testrail.io/index.php?/cases/view/28514 | Template admin — validation | Verify a percentage-discount template is capped at 100% while a percentage-fee template is uncapped | Medium | VIU-Verified | discount template 150% -> 400; fee template 150% -> 201
FD-TMPL-014 | C28515 | https://shopview.testrail.io/index.php?/cases/view/28515 | Template admin — dialog fields | Verify a Fee/Discount template offers the four whole-WO methods and no scope field | Medium | VIU-Verified | builder offers exactly 4 whole-WO methods (Flat, % Labor, % Parts, % Subtotal), no scope field, no legacy '% Labor+Parts'
FD-TMPL-015 | C28516 | https://shopview.testrail.io/index.php?/cases/view/28516 | Template admin — negative | Verify the template save-failure toast | Low | VIU-Verified | template empty name -> 400; amount 0 -> 400 (save-failure surfaced)
FD-TMPL-016 | C28517 | https://shopview.testrail.io/index.php?/cases/view/28517 | Template admin — permissions | Verify the admin Fees & Discounts page is gated by Settings → Finance | High | VIU-Verified | BE-enforced: tech templates GET/POST -> 403; page FE-gated settingsFinance
FD-TMPL-017 | C28518 | https://shopview.testrail.io/index.php?/cases/view/28518 | Template admin — dialog fields | Verify template Name enforces the 100-character limit | Low | VIU-Verified | name 100ch -> 201; 101ch -> 400
FD-VAL-002 | C28600 | https://shopview.testrail.io/index.php?/cases/view/28600 | Validation / Edge | Verify a blank or 0 Amount/Percent blocks save with an inline error | High | VIU-Verified | amount 0 -> 400 (API); UI inline error on submit
FD-VAL-003 | C28601 | https://shopview.testrail.io/index.php?/cases/view/28601 | Validation / Edge | Verify an empty Name blocks save with an inline error (Name required, up to 100 characters) | Medium | VIU-Verified | UI blocks empty name (inline required error). NEW FDBUG-16: raw API now ACCEPTS empty-name adds (201; regression vs batch-3 400) — FE-only guard; name 101ch -> 400, 100ch -> 201
FD-VAL-004 | C28602 | https://shopview.testrail.io/index.php?/cases/view/28602 | Validation / Edge | Verify a percentage discount > 100% is invalid while a percentage fee has no upper cap | High | VIU-Verified | discount >100% invalid (400), fee uncapped (201)
FD-VAL-005 | C28603 | https://shopview.testrail.io/index.php?/cases/view/28603 | Validation / Edge | Verify negative Amount/Percent values are rejected (values must be > 0) | Medium | VIU-Verified | negative amount -> 400
FD-VAL-007 | C28605 | https://shopview.testrail.io/index.php?/cases/view/28605 | Validation / Edge | Verify a template that is BOTH location auto-apply and a customer default yields ONE adjustment on a new WO | Medium | VIU-Verified | auto+default template -> exactly ONE adjustment on the new WO
FD-WO-002 | C28425 | https://shopview.testrail.io/index.php?/cases/view/28425 | Work Order — Whole-WO Fee/Discount | Verify adding a whole-WO Flat Amount fee saves and shows the success toast | Critical | VIU-Verified | whole-WO flat fee add 201 + visible in WO view (flat 7.77 resolved exactly)
FD-WO-003 | C28426 | https://shopview.testrail.io/index.php?/cases/view/28426 | Work Order — Whole-WO Fee/Discount | Verify the live preview computes and displays a whole-WO percentage discount (8% of $10,715.39 → −$857.23) | High | VIU-Verified | dialog live preview re-driven ($5 flat -> '+$5.00 / New work-order subtotal $187.76'); pct preview math not re-driven, API pct resolution re-proven (10%->17.08)
FD-WO-004 | C28427 | https://shopview.testrail.io/index.php?/cases/view/28427 | Work Order — Whole-WO Fee/Discount | Verify 'Apply from template' auto-fills the dialog fields with the template's values | High | VIU-Verified | not re-driven today (Apply-From-Template combobox present in dialog); templateId add path re-proven via API (FD-STACK-003)
FD-WO-006 | C28429 | https://shopview.testrail.io/index.php?/cases/view/28429 | Work Order — Whole-WO Fee/Discount | Verify Max Amount (Max cap) caps a percentage adjustment (20% fee on $100 → +$15 with Max $15) | Medium | VIU-Verified | 20% of 170.76 (=34.15) capped at Max 15 -> resolved exactly 15
FD-WO-007 | C28430 | https://shopview.testrail.io/index.php?/cases/view/28430 | Work Order — Whole-WO Fee/Discount | Verify the add confirm button label follows the Type (Add Fee vs Add Discount) | Medium | VIU-Verified | confirm label 'Add Fee' observed; Type-flip re-observed in batch-1 (not re-driven)
FD-WO-008 | C28431 | https://shopview.testrail.io/index.php?/cases/view/28431 | Work Order — Whole-WO Fee/Discount | Verify an empty Name blocks saving a whole-WO adjustment | Medium | VIU-Verified | UI BLOCKS empty name (inline 'Name' required, dialog stays open, nothing saved). NOTE NEW FDBUG-16: the RAW API now ACCEPTS an empty-name adjustment (201; was 400 in batch-3) — BE validation regression, FE still guards
FD-WO-009 | C28432 | https://shopview.testrail.io/index.php?/cases/view/28432 | Work Order — Whole-WO Fee/Discount | Verify an empty or zero Amount blocks saving a whole-WO adjustment | Medium | VIU-Verified | amount 0 -> 400 at API; UI validates on submit
FD-WO-010 | C28433 | https://shopview.testrail.io/index.php?/cases/view/28433 | Work Order — Whole-WO Fee/Discount | Verify a percentage discount over 100% is rejected while a percentage fee has no upper limit | Medium | VIU-Verified | discount 150% -> 400 'A percentage discount cannot exceed 100%.'; fee 150% -> 201
FD-WO-011 | C28434 | https://shopview.testrail.io/index.php?/cases/view/28434 | Work Order — Whole-WO Fee/Discount | Verify whole-WO percentage methods resolve against the correct base (% of Subtotal example) | High | VIU-Verified | pct_subtotal resolves on the WO subtotal EXCLUDING whole-WO adjustments (10% of 182.76-sub -> 17.08 = 10% of 170.76 line total)
FD-WO-012 | C28435 | https://shopview.testrail.io/index.php?/cases/view/28435 | Work Order — Whole-WO Fee/Discount | Verify 'Add Fee / Discount' is hidden and rejected on an Invoiced or Paid work order | High | VIU-Verified | add on Invoiced WO -> 409 'Adjustments cannot be changed on an invoiced or paid work order.'; edit also 409
FD-WO-014 | C28437 | https://shopview.testrail.io/index.php?/cases/view/28437 | Work Order — Whole-WO Fee/Discount | Verify the live preview shows the empty-amount prompt before an amount is entered | Medium | VIU-Verified | 'Enter an amount to see the impact.' prompt present in the re-driven dialog
FD-WO-015 | C28438 | https://shopview.testrail.io/index.php?/cases/view/28438 | Work Order — Whole-WO Fee/Discount | Verify the preview adjustment row is signed and colored (fee vs discount) | Medium | VIU-Verified | preview row '+$5.00' with new-subtotal line re-observed; color/sign convention from batch-1 (not re-checked)

## Deviations
FD ID | TestRail Case ID | TestRail Link | Area | Title | Priority | Fresh Status (2026-07-10) | Fresh Evidence / Note
FD-CALC-006 | C28573 | https://shopview.testrail.io/index.php?/cases/view/28573 | Calculation contract | Verify minimum values — Flat Amount smallest is $0.01, Percentage smallest is 0.01% | Medium | VIU-Deviation | FDBUG-10 CONFIRMED AGAIN: pct 0.005% accepted (201) and silently coerced to 0.01 (resolved 0.02); flat 0.005 accepted -> stored 0.01. Spec: below-minimum must be rejected
FD-CALC-008 | C28575 | https://shopview.testrail.io/index.php?/cases/view/28575 | Calculation contract | Verify Max Amount = $0 forces resolve to $0.00, while blank/empty Max Amount means no cap | Medium | VIU-Deviation | FDBUG-9 CONFIRMED AGAIN: maxCap 0 -> resolved 34.15 (treated as NO cap; spec: $0 forces $0.00)
FD-CALC-013 | C28580 | https://shopview.testrail.io/index.php?/cases/view/28580 | Calculation contract | Verify a Processing Fee resolves LAST on the tax-inclusive Grand Total (3% of $324 → +$9.72) | High | VIU-Deviation | FDBUG-2 CONFIRMED AGAIN (clean discriminator): pfee base INCLUDES whole-WO adjustments + their tax (3% -> 0.63 where spec expects 0.00). Structural defect is tax-model independent
FD-CUST-003 | C28487 | https://shopview.testrail.io/index.php?/cases/view/28487 | Customer Fees & Discounts tab | Verify adding a single template as a customer default via the picker | High | VIU-Deviation | single-select add works (API 201, UI single picker) — PO Q6=A accepted; case text still needs the single-select re-wording (case-update)
FD-CUST-004 | C28488 | https://shopview.testrail.io/index.php?/cases/view/28488 | Customer Fees & Discounts tab | Verify several templates are added as customer defaults one at a time (no multi-select) | Medium | VIU-Deviation | one-at-a-time picker accepted per PO Q6=A; case-update pending
FD-CUST-005 | C28489 | https://shopview.testrail.io/index.php?/cases/view/28489 | Customer Fees & Discounts tab | Verify the picker lists only unlinked templates and shows Processing Fee templates as type "Fee" | Medium | VIU-Deviation | accepted deviation (PO Q6=A); list assertions hold; case-update pending
FD-CUST-006 | C28490 | https://shopview.testrail.io/index.php?/cases/view/28490 | Customer Fees & Discounts tab | Verify the empty picker message when there are no templates left to add | Low | VIU-Deviation | 'No results' empty picker message per batch-1 (spec wording differs); case-update pending; not re-driven
FD-CUST-007 | C28491 | https://shopview.testrail.io/index.php?/cases/view/28491 | Customer Fees & Discounts tab | Verify removing a customer default via the row's remove action needs no confirm and toasts | High | VIU-Deviation | remove = direct trash, no toast (batch-1); API remove -> 204 re-proven; case-update pending
FD-FIN-004 | C28467 | https://shopview.testrail.io/index.php?/cases/view/28467 | Work Order — Sidebar 'Work Order Fee / Discount' card | Verify the sidebar 'Work Order Fee / Discount' card lists whole-WO adjustments with name, signed rate badge, grey amount and hover Edit/Delete | High | VIU-Deviation | card renders 'WO Fees & Discounts / Flat fee $12.00 +$12.00' — label/name drift vs spec wording persists (case-update)
FD-INLINE-003 | C28456 | https://shopview.testrail.io/index.php?/cases/view/28456 | Work Order — Inline display (Lines tab) | Verify a line/part with 2+ adjustments shows only the first plus a 'Show N more' toggle | High | VIU-Deviation | CONFIRMED AGAIN: 2 adjustments on one part render with NO 'Show N more' collapse — PO Q5=B defect persists
FD-LABOR-001 | C28439 | https://shopview.testrail.io/index.php?/cases/view/28439 | Work Order — Labor-line Fee/Discount | Verify a labor line's 3-dot menu opens the Add dialog locked to that Labor Line scope | Critical | VIU-Deviation | label drift (subtitle 'Applying to: {line}' without 'Line {N} Labor —' prefix) per batch-1; not re-driven today
FD-PART-001 | C28446 | https://shopview.testrail.io/index.php?/cases/view/28446 | Work Order / Parts — Part-line Fee/Discount | Verify a part's menu opens the Add dialog locked to that Part Line scope | Critical | VIU-Deviation | FDBUG-14 label defects (missing 'Line {N} Part —' prefix, raw enum 'Pct_parts', part-% option mislabeled '% of Labor Total') per batch-4; part dialog not re-driven today
FD-PERM-002 | C28586 | https://shopview.testrail.io/index.php?/cases/view/28586 | Permissions (Story 13) | Verify Whole-WO adjustment add/edit/remove requires Work Orders: Create and Edit | High | VIU-Deviation | BUG-FD-3 stands on batch evidence; NOT re-testable today — Technician role drifted on the shared env (now HAS workOrdersCreateAndEdit, so its 201 is legitimate); enforcement-depth question unchanged (dev decision)
FD-PROC-008 | C28526 | https://shopview.testrail.io/index.php?/cases/view/28526 | Processing Fee — WO behavior | Verify a Processing Fee on a WO can be removed but not edited | High | VIU-Deviation | BE re-proven: pfee change -> 409 'cannot be edited through this endpoint', remove -> 204; card still offers Edit per batch-1 (S8-N5 UI drift)
FD-PROC-009 | C28527 | https://shopview.testrail.io/index.php?/cases/view/28527 | Processing Fee — calculation | Verify a % of Grand Total Processing Fee resolves last on a tax-inclusive base (3% of $324 → +$9.72) | High | VIU-Deviation | FDBUG-2 CONFIRMED AGAIN with a clean discriminator: on a WO whose ONLY money is a whole-WO $20 taxable fee, 3% pfee resolved 0.63 (=3% of 21.00 incl the whole-WO fee + its tax); spec base must EXCLUDE whole-WO adjustments -> expected 0.00
FD-QB-014 | C28557 | https://shopview.testrail.io/index.php?/cases/view/28557 | QuickBooks — negative totals | Verify a mandatory warn/confirm before saving when discounts exceed the net subtotal | High | VIU-Deviation | FDBUG-15 CONFIRMED AGAIN (API half): over-discount saves 201 with NO warning payload; excess carried silently (117.24). Batch-6 UI shots show no warn/confirm dialog. Violates S6-R12
FD-REMOVE-001 | C28479 | https://shopview.testrail.io/index.php?/cases/view/28479 | Work Order — Remove an adjustment | Verify removing a whole-WO adjustment shows the 'Remove Fee / Discount' confirm and a success toast | High | VIU-Deviation | remove-confirm wording drift per batch-1 (case-update); not re-driven today
FD-STATS-001 | C28459 | https://shopview.testrail.io/index.php?/cases/view/28459 | Work Order — Statistics tab | Verify the Stats tab shows a 'Fees & Discounts (N)' breakdown with Value/% and Amount columns | High | VIU-Deviation | CONFIRMED AGAIN: Stats shows aggregate 'Fees & Discounts (5) $25.00' style block, NOT the per-row Value/%+Amount table — PO Q1=B design regression persists (shot 07-stats)
FD-STATS-002 | C28460 | https://shopview.testrail.io/index.php?/cases/view/28460 | Work Order — Statistics tab | Verify each Stats F&D row shows a scope hyperlink naming its target | Medium | VIU-Deviation | per-row scope hyperlink impossible while the layout is aggregate (dep. FD-STATS-001)
FD-STATS-004 | C28462 | https://shopview.testrail.io/index.php?/cases/view/28462 | Work Order — Statistics tab | Verify the Stats F&D rows are listed in creation order (oldest first) | Medium | VIU-Deviation | creation-order rows blocked by aggregate layout (dep. FD-STATS-001)
FD-TMPL-001 | C28502 | https://shopview.testrail.io/index.php?/cases/view/28502 | Template admin — location | Verify the location template library lives at Administration → Service → Fees & Discounts, below Canned Lines | High | VIU-Deviation | admin library lives under Administration -> FINANCE (route /administration/adjustment-templates), not Service-below-Canned-Lines; page re-loaded today (case-update per S13-R8 target)
FD-TMPL-003 | C28504 | https://shopview.testrail.io/index.php?/cases/view/28504 | Template admin — create | Verify creating a Fee template (dialog fields, confirm button, success toast) | High | VIU-Deviation | PARTIAL IMPROVEMENT: create-dialog title NOW 'New Fee / Discount' (matches spec; was 'Add new fee/discount'); confirm button still 'Create' (spec 'Add Fee / Discount') and toast 'Template created' per batch-1 — drift remains
FD-TMPL-004 | C28505 | https://shopview.testrail.io/index.php?/cases/view/28505 | Template admin — create | Verify creating a Discount template shows the "Discount added" toast | Medium | VIU-Deviation | generic 'Template created' toast vs spec 'Discount added' per batch-1; not re-driven
FD-TMPL-006 | C28507 | https://shopview.testrail.io/index.php?/cases/view/28507 | Template admin — edit | Verify editing a template (open by row click, "Save" button, update toast) | Medium | VIU-Deviation | edit locks Type+Calc on template edit (spec locks only in WO dialog) per batch-1; not re-driven
FD-TMPL-008 | C28509 | https://shopview.testrail.io/index.php?/cases/view/28509 | Template admin — delete | Verify the delete confirm adds a warning when the template is a default for one or more customers | Medium | VIU-Deviation | standardized 'Delete Template' dialog wording = intended per epic; case-update to adopt live wording still pending
FD-TMPL-010 | C28511 | https://shopview.testrail.io/index.php?/cases/view/28511 | Template admin — scoping | Verify template scoping — labour-method templates only appear in labour modals, parts-method only in parts modals | High | VIU-Deviation | FDBUG-13 (line-scope Add dialog has no template picker) per batch-1/4; not re-driven today
FD-TMPL-011 | C28512 | https://shopview.testrail.io/index.php?/cases/view/28512 | Template admin — dialog fields | Verify Max Amount appears only for percentage methods and 0 is treated as empty | Medium | VIU-Deviation | maxCap 0 accepted and STORED as 0 on the template (201) and WO resolve treats 0 as NO cap (34.15) — FDBUG-9 persists
FD-VAL-001 | C28599 | https://shopview.testrail.io/index.php?/cases/view/28599 | Validation / Edge | Verify the Add button stays DISABLED until Name AND Type AND Calculation type AND Amount > 0 are all set | High | VIU-Deviation | CONFIRMED AGAIN: Add button enabled on empty form (validates on submit) — PO Q4=B defect persists
FD-VAL-006 | C28604 | https://shopview.testrail.io/index.php?/cases/view/28604 | Validation / Edge | Verify Max cap edge behavior — 0 or empty = no maximum, and Max Amount shows only for percentage methods | Medium | VIU-Deviation | FDBUG-9: maxCap 0 behaves as NO cap (not 'no maximum' spec reading matches build for empty, but 0 disagrees w/ §5-R6 $0-forces-$0) — persists
FD-WO-001 | C28424 | https://shopview.testrail.io/index.php?/cases/view/28424 | Work Order — Whole-WO Fee/Discount | Verify the whole-work-order Add dialog opens from the WO toolbar more (⋯) menu at Whole Work Order scope | Critical | VIU-Deviation | dialog title still 'Add new fee/discount' (spec 'New Fee / Discount'), menu item 'Add Fee/Discount' — label drift persists (UI re-driven, shot 10-wo-add-dialog)
FD-WO-005 | C28428 | https://shopview.testrail.io/index.php?/cases/view/28428 | Work Order — Whole-WO Fee/Discount | Verify the Add button is disabled until Name, Type, Calculation type and Amount>0 are all set | Critical | VIU-Deviation | CONFIRMED AGAIN: 'Add Fee' button ENABLED on an empty form (disabled-on-empty=false) — PO Q4=B defect persists
FD-WO-013 | C28436 | https://shopview.testrail.io/index.php?/cases/view/28436 | Work Order — Whole-WO Fee/Discount | Verify whole-WO starting places are hidden without Work Orders: Create & Edit | Medium | VIU-Deviation | BUG-FD-3 stands on prior evidence; NOT re-testable today: the shared-env Technician role was CHANGED (now includes workOrdersCreateAndEdit+workOrdersDelete, 8 perms vs matrix 6) so tech's 201 is now legitimate; no login lacking the perm exists

## Blocked - Not Built
FD ID | TestRail Case ID | TestRail Link | Area | Title | Priority | Fresh Status (2026-07-10) | Fresh Evidence / Note
FD-PCOL-001 | C28469 | https://shopview.testrail.io/index.php?/cases/view/28469 | Parts page — 'FEES & DISCOUNTS' column | Verify the Parts page 'Fees & Discounts' column shows a single adjustment's name and rate | High | VIU-Blocked-NotBuilt | RE-CHECKED TODAY on a freshly created part sale (P3-127): NO 'Fees & Discounts' column on the part-sale page; API add against a part-sale id -> 400 needs-target (no part-sale adjustment surface). Story 11 still NOT BUILT (shot 12-part-sale)
FD-PCOL-002 | C28470 | https://shopview.testrail.io/index.php?/cases/view/28470 | Parts page — 'FEES & DISCOUNTS' column | Verify the 'Fees & Discounts' column shows a '+N' badge when a part has multiple adjustments | High | VIU-Blocked-NotBuilt | Story 11 surface absent (re-checked today)
FD-PCOL-003 | C28471 | https://shopview.testrail.io/index.php?/cases/view/28471 | Parts page — 'FEES & DISCOUNTS' column | Verify the 'Fees & Discounts' column shows a '+ Add' button on a part with no adjustments | Medium | VIU-Blocked-NotBuilt | Story 11 surface absent (re-checked today)
FD-PCOL-004 | C28472 | https://shopview.testrail.io/index.php?/cases/view/28472 | Parts page — breakdown modal | Verify clicking a populated 'Fees & Discounts' cell opens the per-part breakdown modal with the correct columns | High | VIU-Blocked-NotBuilt | Story 11 surface absent (re-checked today)
FD-PCOL-005 | C28473 | https://shopview.testrail.io/index.php?/cases/view/28473 | Parts page — breakdown modal | Verify the breakdown modal 'Net adjustment' row equals the signed sum of the part's adjustments | Medium | VIU-Blocked-NotBuilt | Story 11 surface absent (re-checked today)
FD-PCOL-006 | C28474 | https://shopview.testrail.io/index.php?/cases/view/28474 | Parts page — breakdown modal | Verify a per-row Remove (trash) on the breakdown modal removes the adjustment and closes the modal when the last is removed | High | VIU-Blocked-NotBuilt | Story 11 surface absent (re-checked today)
FD-PCOL-007 | C28475 | https://shopview.testrail.io/index.php?/cases/view/28475 | Parts page — 'FEES & DISCOUNTS' column | Verify the '+ Add' button is disabled on a part when the sale/WO cannot be edited | Medium | VIU-Blocked-NotBuilt | Story 11 surface absent (re-checked today)
FD-PERM-004 | C28588 | https://shopview.testrail.io/index.php?/cases/view/28588 | Permissions (Story 13) | Verify Part-Sale adjustment add/edit/remove (whole sale or part line) requires Part Sales: Create and Edit + See Financial Data | High | VIU-Blocked-NotBuilt | Part Sales adjustment surface absent (Story 11 re-checked today)
FD-PROC-001 | C28519 | https://shopview.testrail.io/index.php?/cases/view/28519 | Processing Fee — template builder | Verify "Processing Fee" is a third type in the template builder (template-only) | High | VIU-Blocked-NotBuilt | RE-CHECKED TODAY: template-builder Type options are exactly [Fee, Discount] — Processing Fee STILL MISSING from the builder UI (PO Q3=B says in-scope; FDBUG-8; shot 02-template-dialog)
FD-PROC-002 | C28520 | https://shopview.testrail.io/index.php?/cases/view/28520 | Processing Fee — methods | Verify a Processing Fee offers only Flat Amount (default) and % of Grand Total, with a tax-inclusive base | High | VIU-Blocked-NotBuilt | builder UI absent (re-checked today); BE method constraint re-proven separately (pct_labor rejected for processing_fee)
FD-PROC-003 | C28521 | https://shopview.testrail.io/index.php?/cases/view/28521 | Processing Fee — no Max Amount | Verify the Max Amount field is hidden for every Processing Fee (both methods) | Medium | VIU-Blocked-NotBuilt | builder UI absent (re-checked today); BE rejects pfee maxCap (400)
FD-PROC-004 | C28522 | https://shopview.testrail.io/index.php?/cases/view/28522 | Processing Fee — taxable + jurisdiction note | Verify the Processing Fee Taxable control defaults Yes and shows the §5-R15 jurisdiction note | High | VIU-Blocked-NotBuilt (expected rewritten to §5-R15 jurisdiction note per S8-R13; re-check when Story-8 builder ships) | builder UI absent (re-checked today)

## Blocked - Environment
FD ID | TestRail Case ID | TestRail Link | Area | Title | Priority | Fresh Status (2026-07-10) | Fresh Evidence / Note
FD-CALC-017 | C28584 | https://shopview.testrail.io/index.php?/cases/view/28584 | Calculation contract | Verify multiple discount lines are penny-capped via largest-remainder so capped discounts sum exactly to the floored net subtotal (no negative, whole-cent) | Medium | VIU-Blocked-Env | floor half RE-PROVEN (stacked 120+100 on 182.76 -> sub 0.00, excess 37.24 exact); QB penny-cap half needs QB-side line view
FD-FLAG-001 | C28596 | https://shopview.testrail.io/index.php?/cases/view/28596 | Feature-flag gating | Verify with the FeesAndDiscounts flag OFF, all F&D UI and behavior are hidden everywhere | High | VIU-Blocked-Env | org flag toggling deliberately NOT done: shared env, manual tester active today
FD-FLAG-003 | C28598 | https://shopview.testrail.io/index.php?/cases/view/28598 | Feature-flag gating | Verify with the flag ON, the matching permission is still required to use F&D | Medium | VIU-Blocked-Env | as FD-FLAG-001; the flag-ON half of the AND-gate is fresh-proven (FD-PERM-010)
FD-QB-001 | C28544 | https://shopview.testrail.io/index.php?/cases/view/28544 | QuickBooks sync | Verify each fee/discount exports to QuickBooks as its own invoice line item (fee +, discount −) | High | VIU-Blocked-Env | QB invoice line internals unobservable (no read API; export of re-invoiced WOs fails on duplicate doc numbers) — needs QB-UI eyeball of a cleanly synced invoice
FD-QB-002 | C28545 | https://shopview.testrail.io/index.php?/cases/view/28545 | QuickBooks sync | Verify the QuickBooks line description equals the adjustment name and the item is the mapped Fee/Discount item | High | VIU-Blocked-Env | as FD-QB-001 — needs QB UI (generic Fee/Discount item + description=name)
FD-QB-003 | C28546 | https://shopview.testrail.io/index.php?/cases/view/28546 | QuickBooks sync — edge | Verify a $0.00 resolved adjustment is skipped when sent to QuickBooks | Medium | VIU-Blocked-Env | as FD-QB-001 — $0-line skip only visible QB-side
FD-QB-004 | C28547 | https://shopview.testrail.io/index.php?/cases/view/28547 | QuickBooks — mapping guard | Verify adding a fee is blocked when the Fee item is unmapped (exact message) | High | VIU-Blocked-Env | unmap not achievable today: PUT bookkeeping/settings {settings:{feeItemId:null}} -> 500 (requestId 4bd14847); flat payload -> 400 'settings missing'. Mapping stayed connected+mapped (verified). Guard cycle needs a working unmap (dev/QB-side)
FD-QB-005 | C28548 | https://shopview.testrail.io/index.php?/cases/view/28548 | QuickBooks — mapping guard | Verify adding a discount is blocked when the Discount item is unmapped (exact message) | High | VIU-Blocked-Env | as FD-QB-004 (unmap 500)
FD-QB-006 | C28549 | https://shopview.testrail.io/index.php?/cases/view/28549 | QuickBooks — mapping guard scope | Verify the mapping guard blocks adds on every add surface (WO, labor line, part, part sale, template-apply) | Medium | VIU-Blocked-Env | as FD-QB-004 (unmap 500)
FD-QB-007 | C28550 | https://shopview.testrail.io/index.php?/cases/view/28550 | QuickBooks — mapping guard (auto-apply) | Verify an auto-apply default cannot be saved while the matching QuickBooks item is unmapped | Medium | VIU-Blocked-Env | as FD-QB-004 (unmap 500)
FD-QB-008 | C28551 | https://shopview.testrail.io/index.php?/cases/view/28551 | QuickBooks — mapping guard exceptions | Verify creating/editing a non-auto-apply template is always allowed and no block exists when QuickBooks is not connected | Medium | VIU-Blocked-Env | as FD-QB-004; positive half (template create while MAPPED) works throughout
FD-QB-009 | C28552 | https://shopview.testrail.io/index.php?/cases/view/28552 | QuickBooks — unmap recovery | Verify unmapping an in-use item routes affected invoices to Unexported Items (recoverable, no data lost) | Medium | VIU-Blocked-Env | unexported-items list + retry + mark-done endpoints re-exercised (mark-done 200 on my entries); the unmap-in-flight repro blocked by the unmap 500
FD-QB-010 | C28553 | https://shopview.testrail.io/index.php?/cases/view/28553 | QuickBooks — Class | Verify a single QuickBooks Class applies to every synced line including fee/discount lines | Low | VIU-Blocked-Env | Class application only visible QB-side
FD-QB-011 | C28554 | https://shopview.testrail.io/index.php?/cases/view/28554 | QuickBooks — Class validation | Verify a deleted/deactivated Class aborts the entire invoice sync (no substitution) | Low | VIU-Blocked-Env | stale-Class abort only reproducible QB-side
FD-QB-013 | C28556 | https://shopview.testrail.io/index.php?/cases/view/28556 | QuickBooks — negative totals | Verify discount lines to QuickBooks are capped with largest-remainder whole-cent penny allocation | Medium | VIU-Blocked-Env | penny-cap allocation of discount LINES only visible on QB invoice lines
FD-QB-015 | C28558 | https://shopview.testrail.io/index.php?/cases/view/28558 | QuickBooks — negative totals | Verify the excess is recorded as a customer credit and posts to QuickBooks as a tax-exempt goodwill credit memo | Medium | VIU-Blocked-Env | IN-APP HALF VERIFIED TODAY: invoicing the over-discounted WO recorded a CUSTOMER CREDIT (unpaid-transactions 2->4; 'current' bucket -11.63 -> -119.73 = +9.14 invoice & -117.24 credit exactly). QB goodwill-memo half unobservable: invoice export fails on the duplicate-doc-number env bug, no credit_memo export fired, no QB read API — needs QB UI on a cleanly synced org
FD-QB-016 | C28559 | https://shopview.testrail.io/index.php?/cases/view/28559 | QuickBooks sync — tax | Verify a synced line's tax follows the adjustment's taxable setting | Medium | VIU-Blocked-Env | tax code on the QB line unobservable in-app; in-app taxable base shifts re-proven (FD-CALC-011)
FD-TMPL-012 | C28513 | https://shopview.testrail.io/index.php?/cases/view/28513 | Template admin — list | Verify the template list empty-state message | Low | VIU-Blocked-Env | empty-state needs deleting ALL location templates — not acceptable on the shared env (3 real templates present; manual tester active)

## Pending (Re-VIU)
FD ID | TestRail Case ID | TestRail Link | Area | Title | Priority | Fresh Status (2026-07-10) | Fresh Evidence / Note
FD-FLAG-002 | C28597 | https://shopview.testrail.io/index.php?/cases/view/28597 | Feature-flag gating | Verify the WO history log STILL shows fee/discount entries even when the feature flag is OFF | Medium | Pending / Retest — expected changed by V1_2 S13-R10, needs live re-VIU | as FD-FLAG-001 ¦ V1_2 (2026-07-13): history-log gate updated per S13-R10 — WO-level history requires Work Orders: Create and Edit; line-level history requires Work Order Lines: Create and Edit (was View History Logs). Expected/preconditions updated; needs live re-VIU. NOTE: the Technician role has DRIFTED on the shared qb env — re-derive the roles matrix before the history re-VIU.
FD-HIST-001 | C28560 | https://shopview.testrail.io/index.php?/cases/view/28560 | History log | Verify one history entry per add/edit/remove with the correct bold event labels | High | Pending / Retest — expected changed by V1_2 S13-R10, needs live re-VIU | FDBUG-3 CONFIRMED AGAIN: auto-applied adjustments (auto template + auto pfees) write NO history entry (fresh WO: 1 auto adjustment, 0 adjustment events); manual add/edit/remove ARE logged (added=15/updated=1/removed=15 in today's battery) ¦ V1_2 (2026-07-13): history-log gate updated per S13-R10 — WO-level history requires Work Orders: Create and Edit; line-level history requires Work Order Lines: Create and Edit (was View History Logs). Expected/preconditions updated; needs live re-VIU. NOTE: the Technician role has DRIFTED on the shared qb env — re-derive the roles matrix before the history re-VIU.
FD-HIST-002 | C28561 | https://shopview.testrail.io/index.php?/cases/view/28561 | History log | Verify the history detail block shows Name, Type, Amount (set rate), and Applied-to label | High | Pending / Retest — expected changed by V1_2 S13-R10, needs live re-VIU | FDBUG-11 (details omit 'Type:' line) per batch-1; entry payload captured today (eventType/eventName/user fields); UI detail block not re-driven ¦ V1_2 (2026-07-13): history-log gate updated per S13-R10 — WO-level history requires Work Orders: Create and Edit; line-level history requires Work Order Lines: Create and Edit (was View History Logs). Expected/preconditions updated; needs live re-VIU. NOTE: the Technician role has DRIFTED on the shared qb env — re-derive the roles matrix before the history re-VIU.
FD-HIST-003 | C28562 | https://shopview.testrail.io/index.php?/cases/view/28562 | History log | Verify an adjustment entry leaves the saved-state icon empty and the Line column shows "−" | Medium | Pending / Retest — expected changed by V1_2 S13-R10, needs live re-VIU | adjustment entries carry lineId=null -> Line column '−'; saved-state icon empty per batch ¦ V1_2 (2026-07-13): history-log gate updated per S13-R10 — WO-level history requires Work Orders: Create and Edit; line-level history requires Work Order Lines: Create and Edit (was View History Logs). Expected/preconditions updated; needs live re-VIU. NOTE: the Technician role has DRIFTED on the shared qb env — re-derive the roles matrix before the history re-VIU.
FD-HIST-004 | C28563 | https://shopview.testrail.io/index.php?/cases/view/28563 | History log — visibility | Verify fee/discount history stays visible when the F&D UI is hidden by the feature flag | High | Pending / Retest — expected changed by V1_2 S13-R10, needs live re-VIU | feature-flag OFF window deliberately not taken on the shared env (manual tester active today) ¦ V1_2 (2026-07-13): history-log gate updated per S13-R10 — WO-level history requires Work Orders: Create and Edit; line-level history requires Work Order Lines: Create and Edit (was View History Logs). Expected/preconditions updated; needs live re-VIU. NOTE: the Technician role has DRIFTED on the shared qb env — re-derive the roles matrix before the history re-VIU.
FD-HIST-005 | C28564 | https://shopview.testrail.io/index.php?/cases/view/28564 | History log — visibility | Verify F&D history stays visible when the F&D UI is hidden by See Financial Data being off | Medium | Pending / Retest — expected changed by V1_2 S13-R10, needs live re-VIU | tech (no SFD): history GET 200 incl. F&D entries with SET rate — history independent of SFD ¦ V1_2 (2026-07-13): history-log gate updated per S13-R10 — WO-level history requires Work Orders: Create and Edit; line-level history requires Work Order Lines: Create and Edit (was View History Logs). Expected/preconditions updated; needs live re-VIU. NOTE: the Technician role has DRIFTED on the shared qb env — re-derive the roles matrix before the history re-VIU.
FD-HIST-006 | C28565 | https://shopview.testrail.io/index.php?/cases/view/28565 | History log — permission | Verify fee/discount history entries are gated by Work Orders: Create and Edit (line history by Work Order Lines: Create and Edit) | High | Pending / Retest — expected changed by V1_2 S13-R10, needs live re-VIU | View History Logs is an FE display gate (tech got 200 + 56 adjustment entries); documented enforcement model ¦ V1_2 (2026-07-13): history-log gate updated per S13-R10 — WO-level history requires Work Orders: Create and Edit; line-level history requires Work Order Lines: Create and Edit (was View History Logs). Expected/preconditions updated; needs live re-VIU. NOTE: the Technician role has DRIFTED on the shared qb env — re-derive the roles matrix before the history re-VIU.
FD-HIST-007 | C28566 | https://shopview.testrail.io/index.php?/cases/view/28566 | History log — Processing Fee | Verify a Processing Fee is logged as a fee with "Full invoice" applied-to and no "updated" entry | Medium | Pending / Retest — expected changed by V1_2 S13-R10, needs live re-VIU | extends FDBUG-3: auto-added pfee NOT logged on add; REMOVAL logged; no 'updated' entries (manual base fee logged correctly) ¦ V1_2 (2026-07-13): history-log gate updated per S13-R10 — WO-level history requires Work Orders: Create and Edit; line-level history requires Work Order Lines: Create and Edit (was View History Logs). Expected/preconditions updated; needs live re-VIU. NOTE: the Technician role has DRIFTED on the shared qb env — re-derive the roles matrix before the history re-VIU.
FD-HIST-008 | C28567 | https://shopview.testrail.io/index.php?/cases/view/28567 | History log — edit entry | Verify an edit that changes the rate records the new set rate (not the resolved total) | Low | Pending / Retest — expected changed by V1_2 S13-R10, needs live re-VIU | work_order.adjustment.updated entry written on edit (set rate carried) ¦ V1_2 (2026-07-13): history-log gate updated per S13-R10 — WO-level history requires Work Orders: Create and Edit; line-level history requires Work Order Lines: Create and Edit (was View History Logs). Expected/preconditions updated; needs live re-VIU. NOTE: the Technician role has DRIFTED on the shared qb env — re-derive the roles matrix before the history re-VIU.
FD-PART-005 | C28450 | https://shopview.testrail.io/index.php?/cases/view/28450 | Work Order / Parts — Part-line Fee/Discount | Verify a part-line adjustment stays attached when the part changes from requested to received | Medium | VIU-Pending | STILL PENDING: requested->received transition unreachable — line-create 500s env-wide, make-request rejected on completed lines, receiving subsystem needs a fresh order
FD-PERM-009 | C28593 | https://shopview.testrail.io/index.php?/cases/view/28593 | Permissions (Story 13) | Verify seeing fee/discount entries in the WO history log requires Work Orders: Create and Edit (line history requires Work Order Lines: Create and Edit) | Medium | Pending / Retest — expected changed by V1_2 S13-R10, needs live re-VIU | history entries: BE serves them regardless (tech 200) — FE display gate per enforcement model; entries carry set rate ¦ V1_2 (2026-07-13): history-log gate updated per S13-R10 — WO-level history requires Work Orders: Create and Edit; line-level history requires Work Order Lines: Create and Edit (was View History Logs). Expected/preconditions updated; needs live re-VIU. NOTE: the Technician role has DRIFTED on the shared qb env — re-derive the roles matrix before the history re-VIU.
FD-WO-016 | (pending-create) |  | Work Order — Whole-WO Fee/Discount | Verify the Add/Edit fee-or-discount dialog shows the §5-R15 taxable jurisdiction note below the Taxable dropdown | Medium | Pending — new case (V1_2 §5-R15 / S2-R26a); not yet checked live | NEW 2026-07-13 for V1_2 §5-R15 / S2-R26a. UI string check (advisory) — belongs in a FUNCTIONAL section, NOT an API section (standing rule 4). Assert the exact string verbatim.

## Known Deviations & Blocked
# | Area / Issue | What you will SEE on the build | What the SPEC says should happen | Related cases | Type / Owner
1 | Over-discount saves silently | If you add a discount bigger than the work-order total, it saves immediately. The subtotal just becomes $0.00 and the extra amount is kept as a customer credit — you are never warned. | A warning must appear first, telling you the total will floor at $0.00, that tax may still be owed, and how much extra will be carried as credit. You must confirm before it saves. (FDBUG-15) | FD-QB-014 | Bug — dev fix
2 | Processing Fee cannot be created in the admin screen | The template builder only offers 'Fee' and 'Discount' as types. There is no way to create a Processing Fee from the screen (re-checked today). | 'Processing Fee' should be a third type in the template builder. The PO confirmed this belongs in this release. (FDBUG-8) | FD-PROC-001..004 | Missing feature — dev
3 | Part Sales has no fees & discounts at all | The Part Sales page has no 'Fees & Discounts' column, no Add button, and no breakdown popup (re-checked today on a fresh part sale). | Story 11: part sales should support fees/discounts per part with a column + popup. | FD-PCOL-001..007, FD-PERM-004 | Missing feature — dev
4 | Automatic fees/discounts leave no history trail | When a fee or discount is added automatically (from a location template or customer default), NOTHING is written to the work-order history. Only manual add/edit/remove are logged. | Every adjustment that lands on a work order should be logged. (FDBUG-3) | FD-HIST-001, FD-HIST-007 | Bug — dev fix
5 | Processing Fee is calculated on the wrong base | A % Processing Fee includes other whole-work-order fees/discounts (and their tax) in its base. Example today: with only a $20 fee on the WO, a 3% processing fee charged $0.63 instead of $0.00. | The Processing Fee base must EXCLUDE all whole-work-order fees/discounts. (FDBUG-2) | FD-PROC-009, FD-CALC-013 | Bug — dev fix
6 | 'Max $0' does not force the amount to zero | Setting Max Amount to 0 on a percentage adjustment is accepted but behaves like NO cap at all (today: 20% resolved to $34.15 with Max 0). | Max $0 should force the resolved amount to $0.00. (FDBUG-9) | FD-CALC-008, FD-VAL-006, FD-TMPL-011 | Bug — dev fix
7 | Too-small percentages are silently rounded up | Typing 0.005% is accepted and silently becomes 0.01% instead of being rejected. | Values below the minimum (0.01%) should be rejected with an error. (FDBUG-10) | FD-CALC-006 | Bug — dev fix
8 | Add buttons are never greyed out | In the add fee/discount dialog (and the template builder), the Add/Create button is clickable even when the form is empty; errors only appear after you click. | The button should stay disabled until Name, Type, Calculation type and Amount are all filled in. PO confirmed: grey it out. (BUG-FD-4) | FD-WO-005, FD-VAL-001 | Bug — dev fix
9 | No 'Show more' on stacked line fees | A line/part with 2+ fees shows every row at once — there is no 'Show N more' collapse (re-checked today). | Only the first row should show, with a 'Show N more' toggle. PO confirmed this was in the design. (BUG-FD-5) | FD-INLINE-003 | Bug — dev fix
10 | Stats tab shows only totals, not a table | The Stats tab shows one combined 'Fees & Discounts (N) $X' figure instead of a table listing each fee/discount with its % and amount (re-checked today). | Each adjustment should be its own row with Value/% and Amount columns. PO confirmed: per-row was the design. (BUG-FD-2 / FDBUG-6) | FD-STATS-001, FD-STATS-002, FD-STATS-004 | Bug — dev fix
11 | Part fee/discount dialog labels are wrong | On a part, the add dialog works but: the subtitle doesn't name the line/part number the spec way, the calculation shows a raw 'Pct_parts' value, and the part-percentage option is mislabeled '% of Labor Total' (it still calculates on the part total). | Labels should read 'Line {N} Part — {name} ({number})' and '% of Parts Total'. (FDBUG-14) | FD-PART-001 | Bug — dev fix (labels only)
12 | Empty name accepted by the back door | NEW TODAY: the raw API accepts a fee/discount with an EMPTY name (the screen still blocks it, so normal users won't hit this). | The server should reject empty names like it used to. (FDBUG-16 — API-only regression) | FD-WO-008, FD-VAL-003 (note) | Bug — dev fix (low)
13 | Creating work-order lines is broken on this test environment | STILL BROKEN TODAY: adding any line to any work order fails with a server error (500) — from the screen or the API, plain or canned. You cannot build a fresh invoiceable work order. | Line creation should work. This blocks: fresh part flows (requested→received), a Processing Fee on a money-bearing new WO, and clean QuickBooks export tests. | FD-PART-005 (+ blocks re-tests) | ENV bug — dev/env
14 | QuickBooks export of re-invoiced work orders fails | Re-invoicing a work order that was invoiced before makes the QuickBooks export fail with a duplicate-document-number error (seen again today; entries land in Unexported Items). | Export should succeed (or handle the number collision). | FD-QB-001..003, FD-QB-015 (QB half) | ENV/dev bug
15 | QuickBooks line-level checks can't be verified from ShopView | What each invoice line looks like INSIDE QuickBooks (item, description, tax code, class, penny-capped discount lines, goodwill credit memo) cannot be read from ShopView — there is no read API. The item-unmapping switch also errors (500) so the 'blocked add' messages can't be triggered. | Needs someone to eyeball the synced invoice inside the QuickBooks UI on a cleanly connected org. | FD-QB-001..011, FD-QB-013, FD-QB-016, FD-CALC-017 (QB half), FD-QB-015 (memo half) | Blocked — needs QB UI access
16 | Feature-flag OFF tests not run | Turning the Fees & Discounts feature OFF for the whole org was deliberately NOT done today because other testers (including you) share this environment. | Flag-off behavior (everything hidden, history preserved) still needs a private window. | FD-FLAG-001..003, FD-HIST-004, FD-TMPL-012 | Blocked — env window
17 | Whole-WO permission only enforced by the screen | Hiding 'add fee/discount' for users without Work-Order edit rights is only done by the UI; the server accepts the write anyway (per earlier testing; today the shared Technician role was changed so this could not be re-tested). | Dev decision needed: should the server also enforce it? (BUG-FD-3) | FD-PERM-002, FD-WO-013 | Dev decision
18 | Good news — two old bugs look FIXED | 1) The old 'totals exclude adjustments' money bug (FDBUG-1) did NOT reproduce again today — document Subtotal/Tax/Total all include adjustments and match the app exactly (3rd clean pass). 2) Customers created via the API now DO inherit auto-apply defaults (FDBUG-12 fixed). | Keep an eye out during manual testing but treat both as fixed on this build. | FD-DOC-011, FD-CUST-014 | FYI — verify in passing