## Bug Drafts
Simple Mode - Bug Drafts (plain-English)
Four issues found while testing Simple Mode, written in plain English. Each row explains what happens now, what should happen instead, and simple steps to see it. (These are defects for the dev team - not questions for the product owner.)
# | Title | What happens now | What should happen | How to see it (simple steps) | Severity
1 | Permission to finish or review a work order is only enforced on the screen, not behind the scenes | Some staff are not supposed to be able to finish a work order or sign off a review. The screen correctly hides those buttons from them - so through normal use they can't do it. But the check is only on the screen: the system behind the screen does NOT block the action, so someone technical could still finish a work order or sign off a review even without the permission. (It has been agreed the on-screen block is good enough for the first version; this is logged so the deeper block can be added later.) | The block should also happen behind the screen, not just on it - so a person without the permission is refused even if they try to go around the normal screen. | 1. Sign in as a role that is NOT allowed to finish work orders (for example a Technician). 2. Confirm the Finish / Mark-Reviewed buttons are hidden on the screen - good. 3. Have someone technical trigger the same "finish" or "sign off" action directly (not through the normal screen). 4. Notice the action still goes through - it should have been refused. | Medium
2 | Required fields at finish time (mileage, VIN, engine hours) are only enforced on the screen | When settings say fields like mileage, VIN or engine hours are required to finish a work order, the finish screen correctly stops you until you fill them in. But the system behind the screen does NOT check for them - so a work order can still be finished with those required fields left empty if the action is triggered outside the normal screen. | The system behind the screen should also refuse to finish a work order when a required field (mileage / VIN / engine hours) is missing - the same way the on-screen finish step already does. | 1. In Work Order settings, turn on "require mileage" (and/or VIN, engine hours). 2. Confirm the finish screen blocks you until those fields are filled - good. 3. Have someone technical trigger the "finish" action directly, leaving those fields empty. 4. Notice the work order finishes anyway with the fields blank - it should have been refused. | Medium
3 | Receiving a work-order part on the OLDER receiving screen fails with an error (the newer bulk screen works) | When a part was ordered from a work order, trying to receive it on the older single-order "Accept Delivery" screen fails - the app shows a generic error and nothing is received. The SAME part receives fine on the newer "bulk receive" screen, and ordinary (non-work-order) parts receive fine on the older screen too. So it only breaks for work-order parts on that one older screen - and a working alternative already exists, which is why this is low urgency. | Receiving a work-order part on the older Accept Delivery screen should succeed and record the delivery, exactly like it already does on the newer bulk receive screen and for ordinary parts. | 1. Create a work order and add a part from a supplier, typing the part number in by hand. 2. Finish the work order so the part becomes an order waiting to be received. 3. Open the older "Accept Delivery" screen for that order. 4. Enter an invoice number and a received quantity, then click Receive. 5. Notice it fails with an error - the newer bulk receive screen would have accepted it. | Low
4 | A brand-new company starts with the wrong default settings | When a company first starts using Simple Mode, two settings come out of the box set the wrong way: "auto-approve lines" is turned ON (it should be OFF) and the supplier invoice number is set to optional (it should be required). So a new company gets the wrong behaviour until someone notices and changes it by hand. | Out of the box, a new company should have "auto-approve lines" turned OFF and the supplier invoice number set to REQUIRED, matching the agreed defaults. | 1. On a brand-new company (or first use of Simple Mode), open Work Order settings. 2. Look at "auto-approve lines" and the "supplier invoice" setting. 3. Notice auto-approve is ON and the invoice is optional - they should be OFF and required. | Medium

## QA Internal Mapping
INTERNAL - for QA / dev only. The reader-facing "Bug Drafts" tab carries no IDs or codes.
Bug # | Internal code / Jira draft | Case (internal ID) | TestRail Case ID | TestRail link | Refs & current status
1 | BUG-6 + BUG-7. Jira draft: TICKET 2. Milos R2 Q5: UI gating = v1 PASS; this is the OPEN fix ticket for the behind-the-screen (API) gap. | SF-PERM-06 | C29410 | https://shopview.testrail.io/index.php?/cases/view/29410 | Refs: SV-8183 backend-enforcement claim vs SV-7864 atom-collapse (workOrderLinesCreateAndEdit collapses to ROLE_WORK_ORDER::VIEW+CREATE_AND_EDIT). Tech simple-complete -> 201; tech change-status->complete -> 201; by contrast tech settings/change -> 403 (settings atom IS enforced). Status: OPEN — CONFIRMED bug (API gap kept open per Milos R2 Q5). Medium. SF-PERM-06 = API section (4090). Results recorded "UI pass / API fail".
|  | SF-PERM-02 | C29406 | https://shopview.testrail.io/index.php?/cases/view/29406
|  | SF-PERM-07 | C29411 | https://shopview.testrail.io/index.php?/cases/view/29411
|  | SF-REV-09 | C29394 | https://shopview.testrail.io/index.php?/cases/view/29394
2 | BUG-8. Jira draft: TICKET 3. | SF-VAL-01 | C29415 | https://shopview.testrail.io/index.php?/cases/view/29415 | Refs: SV-8183 backend-enforcement claim / SV-7864 atom-collapse. Evidence viu-evidence/VIU2-02-mileage-gate.png (wizard blocks) vs simple-complete {} -> 201 with mileage empty. Status: OPEN — CONFIRMED bug, expected NOT rewritten. Medium. Required-field gates (mileage/VIN/engine hours) are UI-only; backend-checked blockers (tech story, line approval) ARE enforced.
|  | SF-VAL-02 | C29416 | https://shopview.testrail.io/index.php?/cases/view/29416
|  | SF-VAL-03 | C29417 | https://shopview.testrail.io/index.php?/cases/view/29417
|  | SF-COMP-05 | C29294 | https://shopview.testrail.io/index.php?/cases/view/29294
|  | SF-COMP-16 | C29305 | https://shopview.testrail.io/index.php?/cases/view/29305
|  | SF-REV-03 | C29388 | https://shopview.testrail.io/index.php?/cases/view/29388
3 | BUG-11. Jira draft: TICKET 4. DOWNGRADED 2026-07-09 (RE-VIU BATCH 7): confined to the LEGACY single-PO Accept-Delivery path; the new Bulk Receive pipeline works (receive-requested-parts -> 200). | SF-COMP-13 | C29302 | https://shopview.testrail.io/index.php?/cases/view/29302 | Refs: SV-7301 / Story 10 (receive creates/links catalog+inventory part) / Story 8 (Bulk Receive = the working path). Legacy POST /api/inventory/orders/accept -> 500 for WO POs (free-text/non-catalog part; manufacturer_id null). Evidence viu-evidence/R7-01-wo-po-accept-delivery.png, R7-06-received-full.png. Status: OPEN — Low (downgraded). Affected cases now largely testable via the Bulk Receive path; this ticket only blocks the legacy single-PO Accept-Delivery surface.
|  | SF-COMP-19 | C29308 | https://shopview.testrail.io/index.php?/cases/view/29308
|  | SF-VAL-05 | C29419 | https://shopview.testrail.io/index.php?/cases/view/29419
|  | SF-VAL-06 | C29420 | https://shopview.testrail.io/index.php?/cases/view/29420
|  | SF-PNFIX-02 | C29364 | https://shopview.testrail.io/index.php?/cases/view/29364
|  | SF-PNFIX-03 | C29365 | https://shopview.testrail.io/index.php?/cases/view/29365
|  | SF-PNFIX-04 | C29366 | https://shopview.testrail.io/index.php?/cases/view/29366
|  | SF-PNFIX-05 | C29367 | https://shopview.testrail.io/index.php?/cases/view/29367
|  | SF-PNFIX-06 | C29368 | https://shopview.testrail.io/index.php?/cases/view/29368
|  | SF-RCV-08 | C29376 | https://shopview.testrail.io/index.php?/cases/view/29376
|  | SF-VPART-07 | C29337 | https://shopview.testrail.io/index.php?/cases/view/29337
|  | SF-REV-04 | C29389 | https://shopview.testrail.io/index.php?/cases/view/29389
|  | SF-REV-14 | C29399 | https://shopview.testrail.io/index.php?/cases/view/29399
|  | SF-CORE-03 | C29315 | https://shopview.testrail.io/index.php?/cases/view/29315
|  | SF-CORE-04 | C29316 | https://shopview.testrail.io/index.php?/cases/view/29316
|  | SF-CORE-05 | C29317 | https://shopview.testrail.io/index.php?/cases/view/29317
|  | SF-CORE-07 | C29319 | https://shopview.testrail.io/index.php?/cases/view/29319
4 | GAP-B. Jira draft: TICKET 5. | SF-SET-08 | C29282 | https://shopview.testrail.io/index.php?/cases/view/29282 | Refs: §4 / S1 first-use defaults (confirmed Milos Q3): Auto-approve OFF, Create POs ON, Vendor Invoice REQUIRED. Live GET /api/organizations/settings shows autoApproveLines:true, requireVendorInvoiceNumber:false. Status: OPEN — CONFIRMED bug, SF-SET-08 expected stays (authoritative spec default). Medium. Wrong first-use org defaults.
Notes: Source of truth = jira-bug-drafts.md (4 active tickets TICKET 2-5, post-Milos-Round-2, updated 2026-07-10). TestRail IDs sourced from testrail-id-map.csv (standing rule 8). These are DEFECTS for the dev team (Jira TICKET 2-5 under epic SV-7301, Product Area Work Orders) - NOT filed yet (no Atlassian MCP here; file from the chat app). Kept OUT of any PO-facing deliverable (standing rule 7). DROPPED as expected: BUG-5/TICKET 1 (reviewer != completer descoped v1, Milos 2026-07-10). CLOSED / not filed: BUG-3 (review-note descoped, Milos R2 Q1), BUG-9/GAP-A (vendorless category-req/sell-optional intended, Milos R2 Q4), BUG-1/2/4/10.