## Question for Chris
Work Orders: Board View and Tech View — one follow-up question for Chris (12 Oct 2026)
Dear Sir, thank you for your answers. Your answer about imported work orders differs from what was agreed earlier on the requirements page, so we want to be sure before we raise anything with the developer. Could you please pick one option in the last column ("Your answer")? Thank you, Sir.
# | Topic | What happens now | The question | Options | Your answer
1 | Work Orders page, Board View and Tech View — work orders with the status "Imported" (follow-up to question 2) | When "Imported" is ticked in the Status filter in the List, the Board View and Tech View buttons are greyed out with the message "Not available while Imported is selected." Inside Board View and Tech View, "Imported" is greyed out in the Status filter with the message "Imported work orders open in List." This was agreed on 24 Sep 2026 in the comments on the requirements page. The developers asked, and Sasha replied: "that works. Also 'Imported' should be disabled as an option on the Status filter on Tech and Board view." | Sir, your answer to question 2 says imported work orders should appear in Board View and Tech View. Should that replace what Sasha agreed on 24 Sep? | A) Yes, imported work orders must appear in Board View and Tech View. We will raise it with the developer (Slavcho) and test it once it is fixed. B) No, keep what Sasha agreed: imported work orders stay in the List only. We will close this check and raise nothing.

## QA internal - not for the PO
This sheet is for us. It is the traceability the PO does not need to read.
Question # | Cases it decides | Requirement | Why it is a question and not a defect
1 | C154887 and C154648 (run 498) | PRD Confluence 845185030 v47: Story 1 overview ("Switching display option never changes which work orders are shown"), S4-N2, S4-N9; PRD footer reply 886374410 (24 Sep 2026, SG); tech plan 1.4 / 3.26 (follow-up A3) | Two product decisions disagree: Chris's 12 Oct answer vs Sasha's 24 Sep approval. The build matches Sasha. No ticket until Chris confirms (QA lead, 12 Oct 2026).