## Global Search
Global Search — please confirm what is actually in this release
Global Search. A few pieces are still fully described in the written requirements but have just been marked as dropped in the build team's task list, so we cannot tell what is really in this release. Please tick one option per row. Your answers decide which tests we keep and which we set aside. Nothing here is a bug — it is a mismatch between the two documents.
# | Topic | What happens now | The question | Options | Your answer
1 | The row of type tabs in search (All, Work Orders, Customers, and so on) | The written requirements still describe a row of tabs across the top of the search results that lets you narrow the results to a single type of record. The build team's task list now marks this piece as dropped. | Is the row of type tabs still part of this release? | Keep it in this release / Drop it from this release / Changed — please describe
2 | Grouping the results by type, each with a count, e.g. 'Work orders (5)' | The written requirements still describe results grouped under headings with a count, and a 'show all' link when there are more. The build team's task list now marks this piece as dropped. | Are the grouped headings and their counts still part of this release? | Keep it in this release / Drop it from this release / Changed — please describe
3 | Using the new search on the list pages (Work Orders, Parts, Customers) | The written requirements still describe the Work Orders, Parts and Customers list pages using the same new search. The build team's task list now marks this piece as dropped. | Should the list pages use the new search in this release? | Keep it in this release / Drop it from this release / Changed — please describe
4 | The quick action buttons that appear when you hover over a search result | The written requirements still describe buttons appearing on each result on hover (for example 'New work order' on a customer). The build team's task list now marks this piece as dropped, moved to a later release. | Are the hover quick action buttons still part of this release? | Keep it in this release / Drop it from this release / Changed — please describe

## QA internal - not for the PO
This sheet is for us. It is the traceability the PO does not need to read.
Question # | Cases it decides | Requirement | Why it is a question and not a defect
1 | Scope Tabs (12 cases) | PRD 576978945 v1.5 §5.2 vs epic story SV-9169 | PRD still specifies the tab strip; SV-9169 flipped OBSOLETE 2026-09-17. Scope conflict, not a defect.
2 | Grouped Results and Counts (9 cases) | PRD §5.2 vs SV-9169 | Same story SV-9169 (grouped results + counts + Show all). PRD keeps it; epic marks it obsolete.
3 | In-Page WO List Search (2) + Page-Search Cutover v2 (2) | PRD §8 vs epic story SV-9306 | SV-9306 (page-search cutover) flipped OBSOLETE 2026-09-17; PRD still has list-page search on the same engine.
4 | Quick Actions on Hover (8 cases) | PRD §5.4 vs epic story SV-9173 | SV-9173 OBSOLETE (later release); PRD §5.4 still lists quick actions in v1. Already parked as Not-on-Build.