## Executive Summary
Custom Roles & Permissions — Release Readiness
Production vs Staging (new roles model) — Executive Summary — 16 July 2026
Scope
All 14 production roles compared against all 11 new-model staging roles; every permission/function verified LIVE on-screen in both environments with captured evidence (screenshots + saved responses); 176 role-capability comparisons; zero unverified items.
The verdict
The new roles model is overwhelmingly faithful to both production behavior and the specification: 130 of 176 comparisons (74%) match production exactly, and 95% of all spec-conformance checks (283 of 297) are per-spec. Every one of the 46 differences was verified live, and 41 of the 46 are intended by the specification. What remains: 6 spec deviations (three of them one shared card-terminal configuration issue) and 3 spec self-contradictions that need decisions before release.
Key numbers
Role-capability comparisons (both environments, live) | 176
… match production exactly | 130
… staging grants more than production | 26
… staging grants less than production | 20
Spec-conformance checks (every verified row judged against the specification) | 297
… agree with the specification (per-spec) | 283
… deviation rows (= 6 distinct findings) | 9
… rows where the specification contradicts itself (= 3 distinct items) | 5
Decisions needed before release
Risk | Decision / status
RED | Service Advisor loses the ability to reverse an invoice — In production this role can reverse an invoice; in the new model it cannot (the button is gone). This is exactly what the specification prescribes (invoice reversal now requires work-order delete rights, which this role no longer has) — but it is customer-billing-facing, so confirm it is intended before release.
RED | Taking customer payments is newly granted to 6 roles — Service Manager, Senior Service Advisor, Foreman, Parts Manager, Parts Technician and Office User can all take a customer payment in the new model; none of them can in production. This matches the specification — but it is money-handling, so confirm it is intended before release.
RED | Senior Service Advisor: AR/AP aging reports promised but not delivered — The specification grants this role the receivables/payables aging reports, but the build hides them (verified in both environments). This is an unimplemented spec grant — needs a dev fix or a spec change.
AMBER | Office User still sees work-order notes and part returns — The 14-July spec update removed ALL work-order access for Office User, yet the build still shows the notes tab (in both environments) and the part-return control (in staging). Both are small-surface over-grants versus the spec — decide: enforce the spec or amend it.
AMBER | "Send to Terminal" shows for three roles the spec would hide it from — Foreman, Office User and Parts Technician see the card-terminal payment button on staging because the staging organization has a card terminal configured. The spec says these roles (Customer Portal switched off) should not see it. This is a difference in HOW the button is gated (organization device vs role setting), not a data risk — decide which gating rule should win.
AMBER | The specification contradicts itself in three places — Product Owner to resolve — (1) Service Manager invoice reversal: one spec table says the role can reverse, another says it cannot — the build follows the "cannot" table. (2) Technician declining a work-order line: one section grants it, another blocks only approving — unresolvable as written; both environments hide it. (3) "Send to Portal" for Office User, Parts Technician and Sales Representative: one section grants it to every full-view role, an answered open question restricts it to line-approvers — the build follows the stricter reading.
GREEN | Card-terminal access is safe through the migration — Verified: "Send to Terminal" depends on whether the organization has a card terminal device, not on the roles migration. Moving to the new roles model does NOT change anyone's terminal access.
GREEN | Parts ordering and receiving match production exactly — All 22 live parts-module checks (create purchase orders, receive deliveries) match production for every role — no change for the parts workflow.
GREEN | Work-order deletion correctly tightened — Only Admin, Service Manager and Senior Service Advisor can delete a work order in the new model — exactly as the specification prescribes (verified live for all 11 roles).
How much to trust this
Every result was observed live on-screen in both environments (screenshots and captured responses are archived); nothing was inferred from documents, role definitions or code. Spec conformance was derived from a verbatim, citation-backed truth table of the v2 specification.

## Migration Deltas (by role)
What each role gains or loses moving from production to the new roles model (46 differences out of 176 live comparisons: 26 gains / 20 losses)
Role | What changes for them | Direction | Per Spec? | Risk | Suggested action
Admin | Can send a payment to the card terminal (only because the staging organization has a terminal device — the production organization has none) | Gains | Yes — expected | Low | None — intended by the specification.
Service Manager | Can take a customer payment | Gains | Yes — expected | High | Confirm with the Product Owner that this is intended (it matches the specification), then release.
Service Manager | Can send a payment to the card terminal (only because the staging organization has a terminal device — the production organization has none) | Gains | Yes — expected | Low | None — intended by the specification.
Service Manager | Can delete a work order | Gains | Yes — expected | Low | None — intended by the specification.
Service Manager | Can change the customer on a work order | Gains | Yes — expected | Low | None — intended by the specification.
Service Manager | Can change the vehicle on a work order | Gains | Yes — expected | Low | None — intended by the specification.
Senior Service Advisor | Can take a customer payment | Gains | Yes — expected | High | Confirm with the Product Owner that this is intended (it matches the specification), then release.
Senior Service Advisor | Can send a payment to the card terminal (only because the staging organization has a terminal device — the production organization has none) | Gains | Yes — expected | Low | None — intended by the specification.
Service Advisor | Can send a payment to the card terminal (only because the staging organization has a terminal device — the production organization has none) | Gains | Yes — expected | Low | None — intended by the specification.
Service Advisor | Can delete a work order | Loses | Yes — expected | Low | None — intended by the specification.
Foreman | Can take a customer payment | Gains | Yes — expected | High | Confirm with the Product Owner that this is intended (it matches the specification), then release.
Foreman | Can send a payment to the card terminal (only because the staging organization has a terminal device — the production organization has none) | Gains | DEVIATION | Medium | Decide before release: align the build to the spec rule (payment terminal should follow the Customer Portal setting) or update the spec. Org-configuration item, not a data risk.
Foreman | Can delete a work order | Loses | Yes — expected | Low | None — intended by the specification.
Technician | Can send a work order to the customer's online portal | Loses | Yes — expected | Low | None — intended by the specification.
Technician | Can open the finance / invoicing area of a work order | Loses | Yes — expected | Low | None — intended by the specification.
Technician | Can see a work order's change history | Loses | Yes — expected | Low | None — intended by the specification.
Technician | Can order parts from a work order | Loses | Yes — expected | Low | None — intended by the specification.
Technician | Can see the timesheets area | Loses | Yes — expected | Low | None — intended by the specification.
Technician | Can delete a work order | Loses | Yes — expected | Low | None — intended by the specification.
Technician | Can change the customer on a work order | Loses | Yes — expected | Low | None — intended by the specification.
Technician | Can change the vehicle on a work order | Loses | Yes — expected | Low | None — intended by the specification.
Parts Manager | Can mark a work order as reviewed | Gains | Yes — expected | Low | None — intended by the specification.
Parts Manager | Can take a customer payment | Gains | Yes — expected | High | Confirm with the Product Owner that this is intended (it matches the specification), then release.
Parts Manager | Can send a payment to the card terminal (only because the staging organization has a terminal device — the production organization has none) | Gains | Yes — expected | Low | None — intended by the specification.
Parts Manager | Can see the timesheets area | Loses | Yes — expected | Low | None — intended by the specification.
Parts Manager | Can change the customer on a work order | Gains | Yes — expected | Low | None — intended by the specification.
Parts Manager | Can change the vehicle on a work order | Gains | Yes — expected | Low | None — intended by the specification.
Parts Manager | Can approve a work order line that is waiting for authorization | Gains | Yes — expected | Medium | Confirm intended — it matches the specification.
Parts Manager | Can decline a work order line that is waiting for authorization | Gains | Yes — expected | Medium | Confirm intended — it matches the specification.
Parts Technician | Can send a work order to the customer's online portal | Loses | Spec inconsistent | Medium | Product Owner to resolve the contradictory spec wording, then re-check this role.
Parts Technician | Can add or edit work order lines | Loses | Yes — expected | Low | None — intended by the specification.
Parts Technician | Can take a customer payment | Gains | Yes — expected | High | Confirm with the Product Owner that this is intended (it matches the specification), then release.
Parts Technician | Can send a payment to the card terminal (only because the staging organization has a terminal device — the production organization has none) | Gains | DEVIATION | Medium | Decide before release: align the build to the spec rule (payment terminal should follow the Customer Portal setting) or update the spec. Org-configuration item, not a data risk.
Parts Technician | Can see a work order's change history | Loses | Yes — expected | Low | None — intended by the specification.
Sales Representative | Can see financial data (rates and margins) | Gains | Yes — expected | Medium | Confirm intended — it matches the specification.
Sales Representative | Can see and add work order notes | Gains | Yes — expected | Low | None — intended by the specification.
Office User | Can send a work order to the customer's online portal | Loses | Spec inconsistent | Medium | Product Owner to resolve the contradictory spec wording, then re-check this role.
Office User | Can take a customer payment | Gains | Yes — expected | High | Confirm with the Product Owner that this is intended (it matches the specification), then release.
Office User | Can send a payment to the card terminal (only because the staging organization has a terminal device — the production organization has none) | Gains | DEVIATION | Medium | Decide before release: align the build to the spec rule (payment terminal should follow the Customer Portal setting) or update the spec. Org-configuration item, not a data risk.
Office User | Can see a work order's change history | Loses | Yes — expected | Low | None — intended by the specification.
Office User | Can order parts from a work order | Loses | Yes — expected | Low | None — intended by the specification.
Office User | Can delete a work order | Loses | Yes — expected | Low | None — intended by the specification.
Office User | Can change the customer on a work order | Loses | Yes — expected | Low | None — intended by the specification.
Office User | Can change the vehicle on a work order | Loses | Yes — expected | Low | None — intended by the specification.
Time Clock User | Can see and add work order notes | Gains | Yes — expected | Low | None — intended by the specification.
Time Clock User | Can see the timesheets area | Gains | Yes — expected | Low | None — intended by the specification.

## Spec Deviations & Open Qs
Spec deviations (6 distinct findings, covering 9 verified rows), spec self-contradictions (3 items, 5 rows) and spec-silent components
# | Finding | Evidence (environment + what was observed) | Spec citation | Recommended owner | Suggested next step
D1 | Foreman sees "Send to Terminal" though the spec role-rule would hide it | Staging: button SHOWN for Foreman (staging org has a card terminal). Production: hidden for all roles (prod org has no terminal device; verified — no way to add one in the app, all terminal endpoints absent). Live-observed both environments, 15–16 July 2026. | Spec §1i (06-Jul change): Send to Terminal requires Invoicing Create & Edit + "Customer Portal: ON"; Foreman has Customer Portal OFF. | PO decision | Decide the gating rule: role-based (per spec) or organization-device-based (as built). Org-configuration item, not a data risk.
D2 | Parts Technician sees "Send to Terminal" though the spec role-rule would hide it | Same observation as D1, for Parts Technician (Customer Portal OFF). Live-observed both environments. | Spec §1i (06-Jul change): Invoicing Create & Edit + Customer Portal ON. | PO decision | Same decision as D1.
D3 | Office User sees "Send to Terminal" though the spec role-rule would hide it | Same observation as D1, for Office User (Customer Portal OFF). Live-observed both environments. | Spec §1i (06-Jul change): Invoicing Create & Edit + Customer Portal ON. | PO decision | Same decision as D1.
D4 | Senior Service Advisor: AR/AP aging reports granted by the spec but hidden by the build | Both environments hide the receivables/payables aging reports for this role (staging live-observed; production live-observed for all three legacy roles that merge into it). The build does not implement the spec grant. | Spec toggles matrix: Reports = ON for Senior Service Advisor; §2a: aging reports follow the Reports toggle (Manage AP/AR is also ON). | Dev fix | Implement the grant (show the aging reports to this role) or amend the spec.
D5 | Office User can still open work-order notes though the 14-July spec removed all its work-order access | BOTH environments show the notes tab to Office User (live-observed). The 14-July "Updated Office Role definition" sets Office's Work Orders access to none, so the notes tab should be unreachable. | Spec permission matrix (14-Jul row): Office / Work Orders = "—"; notes are gated by Work Orders → View (§1a). | PO decision | Decide: enforce the 14-July Office definition (hide the tab) or amend the spec. Small surface.
D6 | Office User can still use part return though the 14-July spec removed all its work-order access | Staging shows the part-return control to Office User (production hides it — its part menu offers Move only). Live-observed both environments. The return control itself is ungated, but reaching it requires work-order view, which the 14-July matrix no longer gives Office. | Spec §1a + 29-Jun note: returning a part needs no permission, but requires work-order view in practice; 14-Jul matrix: Office / Work Orders = "—". | PO decision | Same decision as D5 (same root cause: Office's residual work-order visibility).
Q1 | Spec self-contradiction — Service Manager invoice reversal | Staging shows Service Manager New Payment + Issue Credit but NO invoice-reverse (live-observed). One spec table says the role CAN reverse; the migration table says it cannot. The build follows the migration table. | Permission matrix (SM Work Orders = V/E/D) + 28-Jun rule (reverse = Work Orders Delete) vs migration behavior-changes table ("Loses Invoicing Delete (cannot reverse)"). | PO decision | Resolve which table wins; if the matrix wins, the build needs a change.
Q2 | Spec self-contradiction — Technician declining a work-order line | Both environments hide Approve AND Decline from Technician (live-observed on a genuine needs-approval line). The spec both grants ("authorize lines") and, in its Tech-View section, blocks only Approve — the intended treatment of Decline is unresolvable as written. | §1b Work Order Lines Create & Edit ("authorize lines") vs §4 Tech View (blocks Approve only, silent on Decline). | PO decision | Clarify the spec; current build (hidden) is the conservative reading.
Q3 | Spec self-contradiction — "Send to Portal" for Office User, Parts Technician, Sales Representative | Staging hides the button for all three (live-observed; for Office User and Parts Technician production shows it, so they lose it in the migration; for Sales Representative both environments hide it). One spec section grants the button to every full-view role; an answered open question restricts it to anyone who can approve a work-order line (which these roles cannot). | §3/§4 "Full View has access to Send to Portal" vs Open Q6 answer: "can be anyone who can approve a WOL". | PO decision | Resolve the wording; the build follows the stricter (approver-only) reading.
S1 | Spec-silent component — "Issue Credit" | The Issue Credit button appears in the finance area for invoicing-capable roles (live-observed). The spec nowhere defines which permission should control issuing a credit (it covers only the credits-tab visibility), so conformance was deliberately NOT judged for this component. | No issuance gate anywhere in the v2 spec; §5b covers tab visibility only. | PO decision | Add an explicit gate for Issue Credit to the spec, then re-check.

## Coverage & Method
Coverage & Method
Environments | Production: the live ShopView production organization on the current (legacy) roles model. Staging: app.staging.shopview.com on the new custom-roles model.
Roles covered | All 14 production roles (Administrator; Service Manager; Service Advisor; SA Technician; SA No Reports; SA Limited View; Foreman; Technician; Parts Manager; Parts Technician; Sales Representative; Reporting; Office; Time Clock) compared against all 11 new-model staging roles, using the confirmed role-migration mapping (three SA variants merge into Senior Service Advisor; Sales Representative absorbs Reporting; legacy SA Limited View becomes the new Service Advisor).
How each result was obtained | Live login as each role, in each environment, and direct on-screen observation of each control/behavior (production: admin self-login + per-role switch-user or a role-swapped test staff member; staging: quick-login + real-holder switch-user for all 11 roles). Where a needed data state did not exist (e.g. a work-order line waiting for approval, an invoiced work order), it was seeded, observed, and cleaned up afterwards. No result was inferred from role definitions, permission data, documents or source code.
Zero unverified items | All 176 role-capability comparisons carry a live-observed verdict. The single non-plain-observed item — "Send to Terminal" on production — is a fully characterized organization-configuration finding (the production organization has no card-terminal device and the app offers no way to add one), not an unverified gap.
Spec conformance | Every one of the 297 verified rows was additionally judged against the v2 specification using a verbatim, citation-backed truth table rebuilt from the canonical spec document; where the spec is silent or contradicts itself this is flagged, never resolved by guesswork.
Evidence archive | build/custom-roles-run/live-ui-2026-07-15/ and build/custom-roles-run/live-ui-2026-07-16/ (full-page screenshots + captured per-role responses, both environments), plus build/custom-roles-run/compare-evidence-2026-07-14/.
Full detail | The complete row-by-row matrix behind this summary is in the detailed workbook: Prod-vs-Staging-LIVE-VERIFIED-2026-07-14.xlsx (tabs: Full Dual Matrix, Spec-Standing Conformance, per-capability live tabs, READ ME).