## Change list (29)
Custom Roles spec-recheck — cases that need a change or a decision (29 of 269).
The other 240 cases are fine as-is. Orange rows = waiting on a ticket that is NOT yet done. Nothing pushed to TestRail yet.
Case ID | TestRail link | Area | What needs to change | Driving ticket | Ticket status | Action
C26339 | https://shopview.testrail.io/index.php?/cases/view/26339 | Create Role | Build does NOT hard-block a duplicate role NAME (only a soft 'similar role' warning on identical name+permissions). Case says a duplicate name is blocked. | — | no ticket | DECISION
C26355 | https://shopview.testrail.io/index.php?/cases/view/26355 | Permission Summary | Permission Summary lists a 3rd cross-cutting toggle 'View History Logs' — the build has only TWO (See Financial Data + View and Manage AP/AR Data). Drop the History toggle. | SV-8202 | NOT DONE (Ready to Fix) | Apply update
C26359 | https://shopview.testrail.io/index.php?/cases/view/26359 | Permission Summary | Same as C26355 — remove the non-existent 'View History Logs' cross-cutting toggle from the summary list. | SV-8202 | NOT DONE (Ready to Fix) | Apply update
C26387 | https://shopview.testrail.io/index.php?/cases/view/26387 | Work Orders | In the New Work Order flow the 'Add Customer' button IS shown and works without Customers Create&Edit. Case wrongly expects it hidden. | SV-8002 | DONE | Apply update
C26388 | https://shopview.testrail.io/index.php?/cases/view/26388 | Work Orders | Same for 'Add Asset' in the New Work Order flow — shown & works without Customers Create&Edit. Case wrongly expects it hidden. | SV-8002 | DONE | Apply update
C26418 | https://shopview.testrail.io/index.php?/cases/view/26418 | Parts Dept | Vendor Delete + reverse: the gate for REVERSING a vendor transaction is unsettled (old tickets went back and forth). Confirm the exact gate; vendor/PO delete part is correct. | SV-7871 / SV-7912 | OBSOLETE | Apply update
C26419 | https://shopview.testrail.io/index.php?/cases/view/26419 | Parts Dept | Spec is self-contradictory on which permission gates 'Return to Inventory' (Catalog&Inventory Edit vs Vendor&Order Mgmt Edit). Needs a decision. | — | no ticket | DECISION
C26424 | https://shopview.testrail.io/index.php?/cases/view/26424 | Invoicing & Payments | Case expects a prompt to enable AP/AR when ticking Invoicing Delete — that prompt is now BUILT, so the old 'Deviation' is resolved. Re-run should pass. | SV-8170 | DONE | Apply update
C26427 | https://shopview.testrail.io/index.php?/cases/view/26427 | Invoicing & Payments | 'Send to Terminal' needs Invoicing Create&Edit AND Customer Portal ON. Case only requires Invoicing Create&Edit (would false-pass a Portal-OFF role). | SV-8087 | DONE | Apply update
C26459 | https://shopview.testrail.io/index.php?/cases/view/26459 | View Mode | Does Tech View hide labor rates when See Financial Data is ON? Spec says hidden; SV-8107 (closed 'not a bug') says visible. Conflict — needs a decision. | SV-8107 | OBSOLETE (no fix) | DECISION
C26464 | https://shopview.testrail.io/index.php?/cases/view/26464 | View Mode | Same labor-rate-in-Tech-View conflict as C26459 (only the labor-rate sentence). Needs the same decision. | SV-8107 | OBSOLETE (no fix) | DECISION
C26488 | https://shopview.testrail.io/index.php?/cases/view/26488 | View Part History | 'View History Logs' was renamed 'View Part History' and now controls ONLY the inventory Part History icon. WO/line audit log follows WO Create&Edit; line story follows WO Lines View. Rewrite the case. | SV-7989 / SV-8202 | NOT DONE (Ready to Fix) | Apply update
C26489 | https://shopview.testrail.io/index.php?/cases/view/26489 | View Part History | Same rename/repurpose as C26488 (the OFF case). | SV-7989 / SV-8202 | NOT DONE (Ready to Fix) | Apply update
C26495 | https://shopview.testrail.io/index.php?/cases/view/26495 | Per-Role sets | Admin role summary lists 'View History Logs' — drop it (no such editor toggle). Permission set otherwise correct. AP/AR label stays as build. | SV-8202 | NOT DONE (Ready to Fix) | Apply update
C26496 | https://shopview.testrail.io/index.php?/cases/view/26496 | Per-Role sets | Service Manager DOES have Work Orders Delete (LIVE-confirmed). Case says 'no Delete'. Fix to V/E/D. | SV-8297 | DONE | Apply update
C26497 | https://shopview.testrail.io/index.php?/cases/view/26497 | Per-Role sets | Senior Service Advisor has Reports OFF in the build but spec says Reports ON. Editable role on a shared org — confirm on clean defaults / may need a bug. | — | no ticket | DECISION
C26498 | https://shopview.testrail.io/index.php?/cases/view/26498 | Per-Role sets | Service Advisor Invoicing is View/Create&Edit in the build (no Delete) but spec/case say full. Confirm on clean defaults / may need a bug. | — | no ticket | DECISION
C26500 | https://shopview.testrail.io/index.php?/cases/view/26500 | Per-Role sets | Technician shows WO Create&Edit, Customers Create&Edit and See Financial Data ON in the build vs spec View/View/off. Technician role is known-drifted on this shared org — re-derive on clean defaults. | — | no ticket (env drift) | DECISION
C26502 | https://shopview.testrail.io/index.php?/cases/view/26502 | Per-Role sets | Parts Technician summary references 'View History Logs' — relabel to 'View Part History'. Permission set correct. | SV-8202 | NOT DONE (Ready to Fix) | Apply update
C26503 | https://shopview.testrail.io/index.php?/cases/view/26503 | Per-Role sets | Office User: Invoicing changed to View/Create&Edit/Delete (LIVE-confirmed). NOTE: the 7/14 spec that REMOVES Office Work Orders + Part Sales is NOT deployed (build still grants both); how Office makes payments without creating invoices is still open. | SV-7993 | NOT DONE (Open) | Apply update
C26504 | https://shopview.testrail.io/index.php?/cases/view/26504 | Per-Role sets | Sales Representative is NOT 'Reports only' — it has Work Orders View, WO Lines View, Customers View+Create&Edit, Part Sales View (LIVE-confirmed). Rewrite the case. | SV-8061 | DONE | Apply update
C27736 | https://shopview.testrail.io/index.php?/cases/view/27736 | Cross-Cutting (AP/AR) | AP/AR toggle label is correct as-is ('View and Manage AP/AR Data'), but the case also says it sits next to a 'View History Logs' toggle — remove that (only 2 cross-cutting toggles exist). | SV-8202 | NOT DONE (Ready to Fix) | Apply update
C27870 | https://shopview.testrail.io/index.php?/cases/view/27870 | Work Order Lines | Marking a core OK/Not-OK is gated by Work Orders VIEW (everyone), and a line's story history by WO Lines VIEW — not 'controlled by WO Lines Create&Edit' as the case says. | SV-8130 / SV-7989 | DONE | Apply update
C27873 | https://shopview.testrail.io/index.php?/cases/view/27873 | Work Orders | Customer notes follow the CUSTOMER permission, not Work Orders Delete: View lets you edit anyone's note (delete own); Delete lets you delete others'. Rewrite the stubbed case. | SV-8003 | DONE | Apply update
C29435 | https://shopview.testrail.io/index.php?/cases/view/29435 | Work Orders | Can a Pick/Order-Parts role (WO Lines View only) edit a part's quantity? SV-8136 says it needs WO Lines Create&Edit; SV-8055 suggests a Parts-tab exception. Conflict — needs a decision. | SV-8136 / SV-8055 | DONE (conflicting) | DECISION
C29457 | https://shopview.testrail.io/index.php?/cases/view/29457 | API — Time Clock | Time Clock user reading org Settings via API returns 200, not 403. PO confirmed backend leaks are EXPECTED (not enforced by design). Flip the 'BUG/403' expectation to the accepted 200. | SV-7958 | DONE | Apply update
C29458 | https://shopview.testrail.io/index.php?/cases/view/29458 | API — Time Clock | Time Clock user reading Taxes via API returns 200, not 403 — accepted per PO. Flip expectation. | SV-7958 | DONE | Apply update
C29459 | https://shopview.testrail.io/index.php?/cases/view/29459 | API — Time Clock | Time Clock user creating a Customer via API returns 201, not 403 — PO accepted this write-leak. Flip expectation (note: it IS a create-leak the PO knowingly accepted). | SV-7958 | DONE | Apply update
C29460 | https://shopview.testrail.io/index.php?/cases/view/29460 | API — Time Clock | Time Clock user Work Order create is not gated with 403 — accepted per PO. Flip expectation. | SV-7958 | DONE | Apply update

## Waiting on open tickets
Cases whose change depends on a ticket that is NOT yet done
These should NOT be finalised until the ticket ships; keep the case tracking the target and re-verify after the fix.
Case ID | TestRail link | Area | What needs to change | Driving ticket | Ticket status | Action
C26355 | https://shopview.testrail.io/index.php?/cases/view/26355 | Permission Summary | Permission Summary lists a 3rd cross-cutting toggle 'View History Logs' — the build has only TWO (See Financial Data + View and Manage AP/AR Data). Drop the History toggle. | SV-8202 | NOT DONE (Ready to Fix) | Apply update
C26359 | https://shopview.testrail.io/index.php?/cases/view/26359 | Permission Summary | Same as C26355 — remove the non-existent 'View History Logs' cross-cutting toggle from the summary list. | SV-8202 | NOT DONE (Ready to Fix) | Apply update
C26488 | https://shopview.testrail.io/index.php?/cases/view/26488 | View Part History | 'View History Logs' was renamed 'View Part History' and now controls ONLY the inventory Part History icon. WO/line audit log follows WO Create&Edit; line story follows WO Lines View. Rewrite the case. | SV-7989 / SV-8202 | NOT DONE (Ready to Fix) | Apply update
C26489 | https://shopview.testrail.io/index.php?/cases/view/26489 | View Part History | Same rename/repurpose as C26488 (the OFF case). | SV-7989 / SV-8202 | NOT DONE (Ready to Fix) | Apply update
C26495 | https://shopview.testrail.io/index.php?/cases/view/26495 | Per-Role sets | Admin role summary lists 'View History Logs' — drop it (no such editor toggle). Permission set otherwise correct. AP/AR label stays as build. | SV-8202 | NOT DONE (Ready to Fix) | Apply update
C26502 | https://shopview.testrail.io/index.php?/cases/view/26502 | Per-Role sets | Parts Technician summary references 'View History Logs' — relabel to 'View Part History'. Permission set correct. | SV-8202 | NOT DONE (Ready to Fix) | Apply update
C26503 | https://shopview.testrail.io/index.php?/cases/view/26503 | Per-Role sets | Office User: Invoicing changed to View/Create&Edit/Delete (LIVE-confirmed). NOTE: the 7/14 spec that REMOVES Office Work Orders + Part Sales is NOT deployed (build still grants both); how Office makes payments without creating invoices is still open. | SV-7993 | NOT DONE (Open) | Apply update
C27736 | https://shopview.testrail.io/index.php?/cases/view/27736 | Cross-Cutting (AP/AR) | AP/AR toggle label is correct as-is ('View and Manage AP/AR Data'), but the case also says it sits next to a 'View History Logs' toggle — remove that (only 2 cross-cutting toggles exist). | SV-8202 | NOT DONE (Ready to Fix) | Apply update