## Deviation Review
Case ID | Area (TestRail section) | Title | Original tracker status | Verdict | Action | Ticket / Spec ref | TestRail edited? | Notes
28450 | Work Order / Parts — Part-line Fee/Discount | Part-line fee/discount stays attached when part changes requested → received | BLOCKED — VIU PENDING (QA) | PASS — no change | Flip to READY | spec S5-R13 | N/A | Was blocked on environment/data only (couldn't move part requested→received). Now tested; fee/discount stays attached per S5-R13. Never a deviation.
28456 | Work Order — Inline display (Lines tab) | Line/part with 2+ fees/discounts shows first + 'Show N more' toggle | BLOCKED — DEVIATION | PASS — no change | Flip to READY | spec S3-R15/R16 | N/A | App matches all 4 expected results (default 1 row, 'Show 2 more', expand shows 2, toggle→'Show less'). Tracker note (dev must build collapse) was stale.
28460 | Work Order — Statistics tab | Each Stats fee/discount row names its target | BLOCKED — DEVIATION | UPDATE test case | Edit expected result | spec S4 / S9 | YES — edited | Observable Stats behavior passes. Dropped zero-value precondition + expected line (untestable: $0 now blocked everywhere). Updated in TestRail.
28462 | Work Order — Statistics tab | Stats fees/discounts listed oldest-first (A, B, C) | BLOCKED — DEVIATION | PASS — no change | Flip to READY | spec S5-R9 | N/A | App shows A→B→C top-to-bottom, matching expected result. Was blocked as dependency on 28460 per-row layout; layout now exists & works.
30618 | Work Order — Labor-line Fee/Discount | Labor fee/discount entry point — three-dot menu placement + 'Add Labor Fee / Discount' | BLOCKED — DEVIATION | UPDATE test case | Edit steps + expected result + References | Jira SV-8479 (Done) | YES — edited | App shows ⋮ menu RIGHT of 'Unassigned'. PO (Chris Ward) accepted right-side placement in SV-8479; ticket Done 22 Jul. Rewrite placement LEFT→RIGHT. Menu label + dialog title QA-verified in ticket.
28489 | Customer Fees & Discounts tab | Customer picker lists only not-yet-added templates; Processing Fee shows as 'Fee' | BLOCKED — DEVIATION | UPDATE test case | Edit expected result #1 | spec S9-R20/R21; SV-8280 | YES — edited | App shows multi-select picker. Spec S9-R20 confirms multi-select intended → single-select in case was a defect. #2-#4 spec-confirmed correct. Edited in TestRail.
28490 | Customer Fees & Discounts tab | Picker message when no templates left to add | BLOCKED — DEVIATION | PASS — no change | Flip to READY | spec S9-R22 | N/A | App shows 'No results'; test case already expects 'No results'. Note: diverges from spec S9-R22 ('No templates available to add') but team accepted build as-is. Tracker 'update wording' note stale.
28511 | Template admin — scoping | Template scoping — labour-method templates only in labour pickers, parts-method only in parts pickers | BLOCKED — DEVIATION | PASS — no change | Flip to READY | spec S2-R14/R15/R16 | N/A | All 3 expected results verified (labor=Flat+%Labor; part=Flat+%Parts; no Processing Fee). Original blocker (line-level 'Apply From Template' picker missing) now cleared. SV-8479 labels don't affect this case.
28526 | Processing Fee — WO behavior | Processing Fee on WO can be removed but not edited | BLOCKED — DEVIATION | UPDATE test case | Edit expected result #1 | spec S8-R17/S8-N5 | YES — edited | App now shows Remove-only (spec-correct). Dev removed the old dead 'Edit' control (Processing Fee only; regular fee/discount keeps Edit per S3-R9). Case still describes old Edit+Remove menu → rewrite to Remove-only. Confirm dialog + removal verified.
28527 | Processing Fee — calculation | % of Grand Total Processing Fee works out last on tax-included grand total | BLOCKED — DEVIATION (FDBUG-2) | PASS — no change | Flip to READY; SV-8421 Done | Jira SV-8421 (Done, PR #2220) | N/A | Fix CONFIRMED with live data (5% tax): base 530.23+26.51=556.74; 3%=$16.70 = app. Base correctly excludes $121 flat Processing Fee. SV-8421 resolved $37.12-vs-$37.17-vs-$38.27 ambiguity via §5-R4 note; QA-passed 22 Jul.
28580 | Calculation contract | Processing Fee works out last on tax-included grand total (calc-contract twin) | BLOCKED — DEVIATION (FDBUG-2) | PASS — no change | Flip to READY | Jira SV-8421 (Done) | N/A | Same SV-8421 fix as 28527. Canonical example verified: $300+$24=$324 base; 3%=+$9.72; matches spec §5-R5 worked example. Caveat: on-app execution against exact $300/$24 figures is the click-through tick.

## Summary
Fees & Discounts — QA Deviation Review Summary
Total cases reviewed | 11
PASS — no change (flip to READY) | 7
UPDATE test case | 4
New bug tickets created | 0
PASS cases: | 28450, 28456, 28462, 28490, 28511, 28527, 28580
UPDATE cases: | 28460, 30618, 28489, 28526
Open follow-ups
• | All 4 test-case updates applied in TestRail (28460, 30618, 28489, 28526).
• | SV-8421 downstream: smaller Processing Fee gives less padding vs $0 subtotal floor on heavy-discount WOs — spot-check 28582 / 28584 / 28555–28558.
• | SV-8421 QA note: taxable whole-WO DISCOUNT and non-taxable whole-WO fee should also leave the Processing Fee base unchanged — spot-check.