## Filters
*** SUPERSEDED 2026-08-06 — DO NOT SEND THIS FILE. The version to send is Questions-for-Branko-Cicovic_Filters-and-Schedule_Friendly-Version_2026-08-06.xlsx (plain-language twin Questions-for-Branko-Cicovic_Filters-and-Schedule_Friendly-Version_2026-08-06.md) in this same folder: same substance, reordered by what to do first and rewritten to read easily. This file is kept only as the record of what was verified and when.
Filters - questions for Branko Cicovic - 2026-08-06
PLEASE START WITH QUESTION 1 - four tests are on hold on it, and it is the one where your own answer and your written description disagree. Question 2 is the biggest single blocker on this project: ten tests are waiting on it. Nothing here is a complaint, and one of these is honestly our own fault for not sending it sooner. It covers TWO of your projects, so every question says which one it belongs to - Filters or Schedule - and the tabs are split the same way. It is gathered into one place so you can go through it in a single sitting rather than getting a trickle of separate messages.
# | Topic | What happens now | The question | Options | Your answer
SEVEN FILTERS ITEMS - FOURTEEN TESTS ARE ON HOLD ACROSS THEM
1 | Filters (the filter buttons on the Work Orders list) - the Status button on the Estimates and Completed tabs (the story about how filters behave on each tab, SV-8794, under epic SV-8785) | PLEASE START HERE ON THIS TAB - four of our tests are on hold on this one point, and two answers are on record that disagree with each other. The Work Orders list has tabs across the top. Two of them - Estimates and Completed - already show you only one kind of work order. There is also a row of filter buttons below, and one of them is Status. Your written description says the Status button is NOT SHOWN AT ALL on those two tabs. It has said that since 14 May and it still says it in the version you published this morning. You told us on 17 July that the Status button IS SHOWN, greyed out, and already filled in with that tab's own status, and cannot be changed. Our QA lead agreed with that on 30 July, and the design drawing shows it that way too. Why we are asking rather than choosing: we have put the four tests back to your July answer, because that is what you and our QA lead actually decided - but the product currently behaves the way the written description says. So one of the three has to change and it is your call which. | Which is right - is the Status button hidden on the Estimates and Completed tabs, or shown greyed out and already filled in? | A) NOT SHOWN AT ALL on those two tabs - the written description is right, and my July answer is out of date. B) SHOWN, GREYED OUT AND ALREADY FILLED IN - my July answer stands, and the written description needs correcting. (Then we will also raise it so the product can be fixed.) C) Something else - please describe it.
2 | Filters (the filter buttons on the Work Orders list) - the Parts and Reports write-up (under epic SV-8785) | GENTLE STATUS ASK, not a new question - we know this is already with you and we are not chasing. Eight of our tests cover filter buttons on the Parts pages and the Reports pages. They were written from the designs back in July, and they are parked because that part of the product is not built yet and because your write-up for it has not arrived. To be straight with you: the write-up on its own will not unpark them - the feature still has to be built before anybody can run them. What the write-up does is let us finish the tests properly instead of leaving them resting on a design alone. Why we are asking: only so we can tell our own management honestly whether this is weeks away or months. | Roughly when do you expect the Parts and Reports write-up, and is that part of the product still planned for this release? | A) It is coming shortly, and it is still in this release. B) It has moved to a later release - please say roughly when. C) It has been dropped. (Then we will ask about deleting the eight tests.)
3 | Filters (the filter buttons on the report pages) - the date filter and the page's web address (the story about sharing a filtered view by link, SV-8796, under epic SV-8785) | When you pick a date range on a report, the page's web address changes so the view can be shared or bookmarked. Our tests check that the address changes and that a shared link works. They do not check the exact shape of the address, because nothing written down says what that shape should be. An engineering note does suggest a shape, but the product appears to do something different, and part of that same note has already been overtaken by your update of 4 August. Why we are asking: our automation engineer raised this, and we would rather leave the gap open honestly than invent a rule from an engineering note. No test has been written for it. | Is the exact shape of the web address something we should be testing? | A) No - it is enough that the link works when it is shared. Do not test the exact shape. B) Yes, it matters - and here is the shape it must be: ____________________ C) Ask engineering to settle it and write it down; treat it as their documentation rather than as a test.
4 | Filters (the filter buttons on the Work Orders list, on a phone) - the Imported choice (the mobile filter bar story, SV-8797, under epic SV-8785) | Imported sits in the Status list but behaves differently from the others: while it is chosen, the other filters cannot be used. That much is written down, and we have now added a test for it on a phone. There is a second behaviour that is not written down anywhere. We are told the product also does the reverse: if you pick an ordinary status last, Imported is quietly un-picked for you. Why we are asking rather than just testing it: that behaviour exists only in the developers' own code checks. We do not turn something the code happens to do into something the product must do - that has to be your decision, or it stops being a test of the product and becomes a description of it. | Is that reverse behaviour intended - picking an ordinary status last automatically un-picks Imported? | A) Yes - that is intended. We will test it, and it should be written down. B) No - that is not intended. (Then we will raise it.) C) Something else - please describe what should happen.
5 | Filters (the filter buttons on the Work Orders list) - where the filter bar sits (the filter bar layout story, SV-8786, under epic SV-8785) | Your description says the filter bar sits BELOW the row of tabs (All, Estimates, Completed, My Work Orders). The design shows the same thing. In the product the five filter buttons sit ON THE SAME ROW as the tabs. One of our own tests used to wave this away with a note saying the product behaves this way "on purpose for now" - and nothing anywhere backed that up. That note was wrong and it has been removed. Our test now expects what your description says. Since then a developer job has been raised to move the bar below the tabs, on the grounds that the product does not match your description. So somebody is about to change the product on the strength of that reading. Why we are asking: if you actually wanted them on one row, that developer job should be cancelled and your description updated instead. Better to ask you now than after the change has been made. | Should the filter buttons be moved below the tabs, or did you want them on the same row as the tabs? | A) MOVE THEM BELOW - as your description and the design say. The developer job is correct and nothing needs changing in writing. B) SAME ROW IS WHAT I WANTED - then the developer job should be cancelled and the description updated to say so.
6 | Filters (the filter buttons on the Work Orders list) - the wording on the phone button (the mobile filter bar story, SV-8797, under epic SV-8785) | This is a tiny one, and it exists only because our tests have to quote the exact words a tester will see on screen. Your description calls the button "Apply filters", with a small f. On a phone the button actually reads "Apply Filters", with a capital F. Why we are asking: we would rather your description and the screen said the same thing than have our test quietly differ from one of them. | Which spelling is the right one? | A) "Apply Filters" with a capital F - the description can be tidied to match the screen. B) "Apply filters" with a small f - then the button on screen should be corrected.
7 | Filters (the filter buttons on the Work Orders list) - a pointer in your own description that leads to the wrong place (the mobile filter bar story, SV-8797, under epic SV-8785) | NO DECISION NEEDED - this is just a helpful heads-up about a typo-level slip, and it has already cost one round of confusion. In the phone section, the paragraph about the filter buttons says they work like the desktop "with one exception", and then points the reader at a numbered paragraph further down. But the paragraph it points at is the one about the page search box - not an exception at all. The real exception, that a phone only filters when the person taps the apply button, is the very next paragraph after the one it points to. We think we know how it happened: when you tidied the numbering yesterday you moved the apply-button paragraph down one place, and the pointer above it kept pointing at the old number. Why we are telling you: a reader who follows that pointer lands on the wrong paragraph and concludes there is no exception. | Nothing to decide - please just repoint that reference to the apply-button paragraph next time you have the document open. | (No options - noted for your next edit.)

## Schedule - your document
Schedule - your document - questions for Branko Cicovic - 2026-08-06
EIGHT ITEMS, AND AN APOLOGY WITH THE FIRST. Question 1 was written on 22 July and we never actually sent it to you. Two tests have been sitting parked ever since waiting for an answer you were never asked for. That delay is ours, not yours. QUESTIONS 5 AND 6 ARE THE TWO THAT MATTER MOST: each one decides whether a test of ours is right or wrong, and both come out of the changes made to your own description this morning. Nothing here is a complaint, and one of these is honestly our own fault for not sending it sooner. It covers TWO of your projects, so every question says which one it belongs to - Filters or Schedule - and the tabs are split the same way. It is gathered into one place so you can go through it in a single sitting rather than getting a trickle of separate messages.
# | Topic | What happens now | The question | Options | Your answer
EIGHT SCHEDULE ITEMS - FIVE OF OUR TESTS ARE WAITING ON YOUR ANSWERS
1 | Schedule (the technician scheduling calendar) - planning a job across several days (the multi-day spread story, SV-8691, under epic SV-8685) | FIRST, AN APOLOGY: we wrote this question on 22 July and never sent it. Two tests have been parked ever since. That is our delay, not yours. When a job is too big for one day, the schedule spreads it across several working days. Your description tells us two opposite things about days the shop is closed - a public holiday, or an inventory day - and both sentences are still in the current version: One says: "Shop closures and public holidays are NOT SKIPPED in V1." In other words the spread puts shifts on a closed day like any other day. The other says: "Shop closures (holidays, inventory days) are defined at the shop level and BLOCK the spread step from placing shifts on those days." In other words the spread jumps over closed days. Why we are asking: these are two completely different tests and we cannot write both. We have not guessed - the two tests say plainly that the point is undecided and are waiting. | When a job is spread across several days, should the schedule skip days the shop is closed, or place shifts on them anyway? | A) SKIP THEM - closed days are jumped over, the same way weekends already are, and the job runs on to the next open day. B) DO NOT SKIP THEM - closed days get shifts like any other day for this first version, and somebody moves them by hand if needed.
2 | Schedule (the technician scheduling calendar) - the menu on an empty part of the calendar (the events story, SV-8696, and the access-level section of your description) | Nobody had spotted this one before, and no test is wrong because of it - but your description contradicts itself, so a reader who happens to read the wrong half would test the wrong thing. In two places it says: "LEFT-CLICK on empty grid space opens a menu with: Create event, New work order." In two other places, where it lists what each access level unlocks, it twice calls the same thing a "RIGHT-CLICK context menu". Our tests follow left-click, and the product agrees with them, so nothing is broken today. Why we are asking: it is a one-word correction in your description, and until it is made anyone reading only the access-level section will look for the wrong mouse click. | Which is correct - does that menu open on a left-click or a right-click? | A) LEFT-CLICK - as the two earlier places say. The access-level section is the wording that needs correcting. B) RIGHT-CLICK - then the product and our tests are both wrong and it becomes a developer job.
3 | Schedule (the technician scheduling calendar) - weekends for a technician with no hours set (the working hours story, SV-8699, and the conflict story, SV-8697) | This one is a gap rather than a contradiction, and no test is parked on it - we are asking so that we are not quietly relying on our own reading. Three separate parts of your description do not quite add up for a technician who has no working hours of their own set up: - the default working day is given as 7:00 AM to 7:00 PM, with nothing said about which days of the week that covers; - spreading a job "automatically skips weekends"; - but a shift placed on a weekend counts as a clash to be warned about. So we cannot tell whether a weekend is simply an ordinary working day for such a technician, or a day the schedule should push back on. Why we are asking: it decides whether a warning should appear, and a warning that should not be there is just as much a bug as a missing one. | For a technician with no working hours of their own set up, is a weekend a normal working day or a day the schedule should warn about? | A) A DAY TO WARN ABOUT - weekends are outside normal hours for everyone unless someone has set weekend hours for them. B) A NORMAL WORKING DAY - the default 7 to 7 applies to all seven days, and only the spread step avoids weekends.
4 | Schedule (the technician scheduling calendar) - which drawing of the Schedule we should be working from (under epic SV-8685) | This one is about which picture is the real one, and it affects roughly fifty of our tests. Back in July you told us the Schedule prototype we were given was the one to work from, and we pinned about fifty on-screen names and labels from it - button wording, column headings, the words used in warnings. Three Schedule faults raised on 5 August all point at a DIFFERENT drawing instead - a shared link to a live, editable design page that carries no version and no date. Because it can be edited at any moment and has nothing on it to say when it was finished, we cannot compare our tests against it, and we cannot tell whether it is newer or older than the one we hold. You have already noticed the same thing yourself. On one of those three you replied that the button being reported "is not in the design" and asked where it had been found. Why we are asking: if that newer drawing is the finished one, then about fifty of our labels may be out of date and we should go through it properly. If it is not finished, we should carry on from the prototype and leave it alone. We are not going to guess between two pictures. | Which drawing of the Schedule is the one to work from - the prototype you pointed us at in July, or the newer shared design page? | A) THE PROTOTYPE from July is still the one. The newer page is a work in progress and we should ignore it. B) THE NEWER SHARED PAGE is the finished one - please confirm it is final, and we will go through it and update whatever has changed. C) Neither is final yet - please say when a finished drawing will be available.
5 | Schedule (the technician scheduling calendar) - the search box in the toolbar above the calendar grid (not the one in the job list down the left) (the story about the calendar layout, SV-8686, under epic SV-8685) | THIS ONE DECIDES WHETHER ONE OF OUR TESTS IS RIGHT OR WRONG, so it is worth a minute. Your written description used to say that when someone searches, the jobs that do not match go FADED BUT STAY ON SCREEN, so you keep sight of the whole week. That sentence was taken out of the description THIS MORNING, after your team decided the description was wrong and that the drawing shows only the matching jobs. The description now says only WHAT the search looks through - customer name, work order number, unit number, technician name and line name. It no longer says anything at all about what happens to the jobs that do NOT match. Our test still says the non-matching jobs go faded, because that is what was written down when we wrote it. We are not going to quietly change it to match what the software does today, because that would tell us what was built rather than what you wanted. One more thing in the same place: the developer ticket that describes the calendar layout STILL says the non-matching jobs should fade - in two places, in its requirements and again in its acceptance criteria. So your description and that ticket now disagree with each other. If your answer is A, somebody should tidy that ticket up. We have not touched it, because it is not ours. | When someone searches, what should happen to the jobs that do not match? | A) They should disappear from the calendar - only the matching jobs are shown. (This is what your team said the drawing shows.) B) They should stay on screen but faded, and the matching ones stand out. C) Something else - please describe it.
6 | Schedule (the technician scheduling calendar) - the pop-up window that opens when you click a scheduled job (the story about that window, SV-8695, under epic SV-8685) | THIS ONE DECIDES WHETHER A TEST PASSES OR FAILS, which is exactly why we are asking instead of choosing. Earlier today, on the report about that window, you told us the little ESTIMATE BADGE should not be clickable, and that the time is changed in the fields higher up the window instead. That makes sense to us. What we cannot tell is how far your answer reaches. Your written description STILL says the window should let someone type a new estimate straight into it, and the developer ticket for that window still says the same. Both of those are live today. So your sentence might mean the estimate cannot be changed anywhere in that window, or it might mean only that the small badge on the job line should not be clickable. We have one test that says the estimate CAN be typed into. If you mean the first, that test is wrong and we will correct it. If you mean the second, the test is right and the software has something to fix. We are deliberately not settling it by looking at what the software does today. | In that pop-up window, should someone be able to change the ESTIMATED HOURS by typing into them? | A) NO - the estimate cannot be changed in that window at all; only the start and end times can be changed, in the fields above. B) YES - the estimate itself can still be typed into; only the little badge on the job line should not be clickable. C) Something else - please describe it.
7 | Schedule (the technician scheduling calendar) - the list of jobs INSIDE that same pop-up window (the story about that window, SV-8695, under epic SV-8685) | This one is small, and it is only two of your own documents disagreeing with each other. Your written description was changed this morning so that each job line in that pop-up shows an estimate figure and a status label. In your own words earlier today, the lines should show the estimate and the status badge and there should not be any totals. Our test already expects exactly that - the hours and a status label, and no money anywhere in the window - so nothing of ours is stuck. But the developer ticket for that window still says each line shows a labour TOTAL, and it has said so since before your change. You edited that same ticket three days ago and the word is still sitting in it. So your description and that ticket now say different things, and only you can say which one is the one to keep. While you are in that ticket: it also still says the estimate can be typed in, which is the question just above this one. Both would be tidied up in the same visit. | On each job line in that pop-up, should there be a money total, or only the hours and a status label? | A) ONLY the hours and a status label - no money anywhere. Your description is right and the developer ticket needs tidying up. B) A MONEY TOTAL should be shown there - the developer ticket is right and your description needs correcting. (Then our test is wrong and we will change it.) C) Something else - please describe it.
8 | Schedule (the technician scheduling calendar) - how much of the day the timeline shows when the day view opens (under epic SV-8685) | Nothing is stuck on this one and no test of ours is wrong today. We are asking so that we are not quietly relying on a note that disagrees with your own description. Your description says the day view keeps the WHOLE 24 HOURS there and scrollable, and simply scrolls itself so the start of the working day is on the left. A note on one of the design-review reports asks for something different: that the timeline show ONLY THE WORKING HOURS plus a small amount after them, with anything outside that reached by scrolling. That note says it is being tracked as a later improvement rather than for this release, which is why we have left our test alone. If the narrower version is meant for this release, your description needs changing first and then we will change the test to match it. | For THIS release, which is right? | A) Keep the full 24 hours, as your description says today - the narrower version is for later. B) Change it now to show only the working hours plus a small amount after them. C) Something else - please describe it.

## Schedule - engineering only
Schedule - engineering only - questions for Branko Cicovic - 2026-08-06
NOTHING ON THIS TAB IS URGENT AND NO TEST IS WAITING ON IT. These six behaviours are described only in the engineering plan and appear nowhere in your own document. We are not going to turn an engineering note into something the product must do without your word, so each one is either a decision for you or an item we close as out of scope.
# | Topic | What happens now | The question | Options | Your answer
SIX ITEMS THE ENGINEERING PLAN DESCRIBES AND YOUR DOCUMENT DOES NOT
1 | Schedule (the technician scheduling calendar) - shifts and events that already existed (under epic SV-8685) | Six of our tests describe things that only the ENGINEERING plan describes - your own description does not mention them at all. We have kept the tests, because they cover real risks and throwing them away would lose that cover, but each one says openly that it rests on an engineering note rather than on a product decision. We will not present something as a requirement when no product document says it. So until you tell us these are right, those tests stay parked - that is the honest consequence and we would rather you saw it than have us quietly promote an engineering note into a rule. This first one: after this feature goes out, everything that was already on the calendar should still be there - same technician, same day, same time, same job. Why we are asking: it is the difference between a safe release and losing somebody's existing plan. | Should everything already on the calendar survive the release completely unchanged? | A) YES - nothing already scheduled may move, change or disappear. (Please confirm and we will treat it as a requirement.) B) Not quite - please say what is allowed to change.
2 | Schedule (the technician scheduling calendar) - how a multi-day job looks on the Dashboard (under epic SV-8685) | Another one that only the engineering plan describes. When a job is spread over, say, five days, it becomes five separate day-by-day entries on the calendar. The engineering note says the Dashboard should still show that job as ONE line covering the whole stretch, not as five separate lines. Why we are asking: if it is five lines, the Dashboard suddenly looks five times busier than it is, and nobody has written down which is intended. | On the Dashboard, should a job scheduled across several days appear as one line or as one line per day? | A) ONE LINE covering the whole stretch. B) ONE LINE PER DAY.
3 | Schedule (the technician scheduling calendar) - an appointment set while creating a job (under epic SV-8685) | Another one that only the engineering plan describes. When somebody sets an appointment date and time while creating a job, the engineering note says that appointment should turn up on the schedule calendar at that date and time, and behave like anything else on the calendar. Why we are asking: your description does not mention appointments at all, so we cannot tell whether the two things are meant to be connected. | Should an appointment set while creating a job appear on the schedule calendar? | A) YES - it appears at that date and time and behaves like anything else on the calendar. B) NO - appointments and the schedule calendar are separate things.
4 | Schedule (the technician scheduling calendar) - jobs from another branch (under epic SV-8685) | Another one that only the engineering plan describes, and this is the one with the most at stake. The engineering note says a shift should only ever appear on the calendar of the branch the job belongs to - even when the technician doing it also works at another branch - and that somebody looking at one branch should not be able to reach or change another branch's shift at all. It also gives a reason we think you should see: if a shift's branch were worked out from the technician instead of from the job, then moving a technician to another branch would quietly move all of their PAST shifts too - history would rewrite itself. Why we are asking: this is about one branch seeing another branch's work, so it is worth your explicit yes rather than our assumption. | Should a shift only ever appear on the calendar of the branch its job belongs to? | A) YES - the job's branch decides, always, and one branch can never see or change another's shifts. B) Something else - please describe it.
5 | Schedule (the technician scheduling calendar) - the priority on a job (under epic SV-8685) | Another one that only the engineering plan describes. The engineering note says a job offers a priority choice of High, Medium and Low, that a brand-new job has NONE of them picked to begin with, and that the chosen priority then shows on the job. Why we are asking: "nothing picked to start with" is the kind of detail that is easy to get wrong in either direction, and no product document states it. | Is that right - High, Medium, Low, with nothing pre-selected on a new job? | A) YES - three choices, nothing pre-selected. B) Not quite - please say what the choices are and what a new job should start with.
6 | Schedule (the technician scheduling calendar) - a limit on how long a spread can be (the multi-day spread story, SV-8691, under epic SV-8685) | Two of our tests say that spreading a job further than about eight weeks, or into more than about a hundred and twenty separate days, should stop and ask the person to confirm before going ahead. Those two numbers appear ONLY in the engineering plan. We searched your description and neither number is in it anywhere. The product currently does not warn at all - a very long spread just goes through. We have NOT raised that as a fault, precisely because we cannot show a product document that asks for it. Why we are asking: there are three possible answers here and we are not going to guess between them. | Should a very long spread warn the person first, and if so at what point? | A) YES, at those numbers - about eight weeks, or about a hundred and twenty days. Please confirm and we will treat it as a requirement. B) YES, but at different numbers - please say what they should be. C) NO limit at all - a spread of any length just goes ahead. (Then we will delete the two tests.)

## QA internal - not for Branko
QA-ONLY - INTERNAL - NOT FOR BRANKO. Do not send this tab. TestRail C-ids, requirement anchors, live evidence and the corrections to our own records live here so the reader-facing tabs stay plain (Standing Rules 7, 8 and 55).
PER-ITEM MAPPING - EVERY READER-FACING QUESTION
Tab | Item | What it asks | Where the question comes from | Affected internal case IDs (TestRail C-id) | TestRail links | Spec anchors + live evidence | What each answer resolves to
Tab 1 | 1 | Filters - is the Status chip hidden or shown greyed-out on Estimates and Completed? | NEW. Row 1 of Vlad's eleven-row Filters coverage-gap table, worked as Q1 of build/filters/vlad-gap-review-2026-08-06/QUESTIONS-FOR-BRANKO.md. Three sources disagree. | FOUR cases on AUTOMATION: HOLD - FLT-TAB-02 (C29609); FLT-TAB-03 (C29610); FLT-BAR-03 (C29559); FLT-TAB-05 (C29612) | C29609 https://shopview.testrail.io/index.php?/cases/view/29609 · C29610 https://shopview.testrail.io/index.php?/cases/view/29610 · C29559 https://shopview.testrail.io/index.php?/cases/view/29559 · C29612 https://shopview.testrail.io/index.php?/cases/view/29612 | LIVE-VERIFIED 2026-08-06 against Filters Confluence page 572030978 at VERSION 19 (2026-08-06T11:48:47Z, HTTP 200). S9-R2 verbatim: "On the Estimates tab, the Status filter chip is hidden; the remaining four filters are shown and apply on top of the Estimates pre-filter"; S9-R3 says the same for Completed. UNCHANGED by v19 - so the contradiction with Branko's Round-1 Q4=B answer of 2026-07-17 and the QA lead's ruling of 2026-07-30 is still live. All four HOLD reasons read "waiting on Branko to confirm whether the Status chip is hidden or shown greyed out ..." live today. | A -> the 4 cases revert to hidden and Branko's July answer is retired. B -> the 4 stand as written, a spec edit is owed, and a defect is raised against the build. This is the sharpest row in Vlad's table because it alleges a Rule-57-class defect (our cases asserting the REJECTED behaviour), not merely a gap - which is why it leads the tab.
Tab 1 | 2 | Filters - the Parts and Reports product write-up: when, and is the session happening? | CARRIED FORWARD VERBATIM from the 2026-08-05 sheet's Filters item 4, and it is ALSO row 7 of Vlad's table (Q2 of QUESTIONS-FOR-BRANKO.md). Deliberately framed as a STATUS/COMMITMENT ASK, not a re-ask of the list. | TEN cases on AUTOMATION: HOLD naming this write-up - C38880; C38882; C38904; C38905; C38906; C38907; C38908; C38909; C38910; C38911. (An eleventh, C43562, is held because the bar has only reached some Parts views - absent product, not a missing document.) | C38880 https://shopview.testrail.io/index.php?/cases/view/38880 · C38882 https://shopview.testrail.io/index.php?/cases/view/38882 · C38904 https://shopview.testrail.io/index.php?/cases/view/38904 · C38905 https://shopview.testrail.io/index.php?/cases/view/38905 · C38906 https://shopview.testrail.io/index.php?/cases/view/38906 · C38907 https://shopview.testrail.io/index.php?/cases/view/38907 · C38908 https://shopview.testrail.io/index.php?/cases/view/38908 · C38909 https://shopview.testrail.io/index.php?/cases/view/38909 · C38910 https://shopview.testrail.io/index.php?/cases/view/38910 · C38911 https://shopview.testrail.io/index.php?/cases/view/38911 | COUNTED LIVE 2026-08-06: 114 Filters cases under group 4110, all ours (created_by 3), 20 on AUTOMATION: HOLD, of which exactly TEN name Branko's Parts/Reports write-up. Filters spec v19 still defines no chip set for any Parts view or report. | ⚠️ THIS IS NOT A RE-ASK, AND MUST NOT BE SENT AS ONE. He has ALREADY said twice that no list exists - 2026-07-31 Q3 and 2026-08-04 Q8, the latter verbatim: "Same as before, we do not have concrete list. If this is really necessary i suggest Engineering + PO together make a list for remaining 6 Parts pages i Reports, using same format as Work Orders do." build/OUTSTANDING-ITEMS-REGISTER.md row 623 records the standing decision: "We are deliberately NOT re-asking ... a third ask would be the fifth withdrawn question on this project." So the row asks only ROUGHLY WHEN and WHETHER IT IS STILL IN THIS RELEASE - a commitment on the session HE proposed. NOTE FOR THE QA LEAD: arranging that Engineering + PO session is on YOU, not on Branko (register row 636). HONEST CORRECTION: QUESTIONS-FOR-BRANKO.md says these have been paused "for four weeks". The PRD request went to him on 2026-07-17, which is THREE weeks (20 days) today; the cases were authored 2026-07-27. The reader-facing row says neither figure - it says "since 17 July".
Tab 1 | 3 | Filters - is the exact shape of the report page's web address a requirement? | NEW. Row 8 of Vlad's table, Q3 of QUESTIONS-FOR-BRANKO.md. | NO case authored - the gap was left open on purpose. FLT-RPTS-23 (C38882) is the nearest case and is already held on the Parts/Reports write-up above. | C38882 https://shopview.testrail.io/index.php?/cases/view/38882 | Filters v19 §4 and S11-R1 say nothing about the address format. The engineering plan's item D19 proposes one, and part of that plan was already overtaken by his 2026-08-04 update. A 5 August capture showed the product sending a different shape. Verified live 2026-08-06 that v19 adds nothing on this point. | A -> the gap is closed by product decision and stays deliberately untested; record it in the decisions register. B -> one new case becomes authorable against his stated shape. C -> it becomes engineering documentation and we assert only that a shared link works. Rule 30: an engineering plan informs but never overrules product truth, which is exactly why this is a question and not a case.
Tab 1 | 4 | Filters - on a phone, does picking an ordinary status un-pick Imported? | NEW. Row 11 of Vlad's table, Q4 of QUESTIONS-FOR-BRANKO.md. | The documented half is covered by the new FLT-MOB-11 (C43563). The reverse behaviour is ONE added assertion if he says yes. | C43563 https://shopview.testrail.io/index.php?/cases/view/43563 | Filters v19 S2-R7 verbatim: "Imported is an exception to S2-R2 and cannot be combined with anything else ... selecting Imported switches the list to the imported records and disables the other filter chips while it is active". S2-N4 covers the prevented combination. NEITHER describes the reverse. Searched S2-R7, S2-N4, Story 12 and every recorded Branko answer: 0 occurrences. It exists only in the developers' own MobileAllFiltersSheet spec file. | A -> one assertion is added to C43563 and a spec line is owed. B -> a defect is raised. Rule 58 is the reason this is asked rather than settled from the code: an ambiguous or absent source is never resolved by looking at what the build does.
Tab 1 | 5-7 | Filters - the three items carried forward from the unsent 2026-08-05 sheet: where the filter bar sits · "Apply Filters" with a capital F · the wrong cross-reference in his own spec | CARRIED FORWARD VERBATIM (imported from the 2026-08-05 generator, so the wording cannot drift). All three re-verified as still open on 2026-08-06. | The filter-bar position row is the one that matters most: a developer job is about to move the bar on the strength of somebody else's reading of his document. The cross-reference row needs no decision at all. | (no additional held cases beyond those already listed) | THE CROSS-REFERENCE IS STILL WRONG IN v19, verified live 2026-08-06: S12-R2 reads "The filter chips behave like desktop with one exception (see S12-R5)", but S12-R5 is about the page search control - "The page search control is shown on mobile and behaves as it does on desktop". The real exception is S12-R6: "Unlike desktop, mobile does not filter in real time ... the table updates only when the user taps an 'Apply filters' button within the sheet." His own v17 renumbering moved the apply-button requirement down one and the pointer above it was left behind. | The filter-bar row: A -> the developer job proceeds. B -> it is cancelled and the spec is edited. The capital-F row is a one-word choice either way. The cross-reference row is a tick.
Tab 2 | 1-3 | Schedule - the three questions about his own document: shop closures on a multi-day spread · left-click or right-click on empty calendar space · weekends for a technician with no hours set | CARRIED FORWARD VERBATIM from the 2026-08-05 sheet's Schedule tab. Item 1 was drafted on 22 JULY AND NEVER SENT - the delay is OURS and the sheet says so to his face. | THREE cases on AUTOMATION: HOLD waiting on a product-owner answer that has never been sent - SCH-SPREAD-07 (C29983); SCH-EDGE-05 (C30089); SCH-DND-09 (C43555) | C29983 https://shopview.testrail.io/index.php?/cases/view/29983 · C30089 https://shopview.testrail.io/index.php?/cases/view/30089 · C43555 https://shopview.testrail.io/index.php?/cases/view/43555 | RE-VERIFIED LIVE 2026-08-06 against Schedule Confluence page 713031682, which has moved to VERSION 25 (2026-08-06T09:13:51Z, HTTP 200) from the version 23 our records name. BOTH contradictions SURVIVE v25. Shop closures, both sentences still present verbatim: "Shop closures and public holidays are not skipped in V1." and "Shop closures (holidays, inventory days) are defined at the shop level and block the spread step from placing shifts on those days." Click menu, both still present: "Create via left-click on empty grid space, which opens a menu with 'Create event' and 'New work order'." against the access-level section's "shift and event creation (including via right-click context men[u]". | Shop closures: A (skip) -> both cases assert skipping and a developer job follows. B (do not skip) -> both assert placement and the second sentence is deleted. HONEST NOTE CARRIED ON THE READER TAB: for two of these his answer alone will not make the case runnable, because the shop-closure setting does not exist anywhere in the product yet. The click-menu row is a one-word spec fix and no test is wrong today. ⚠️ THE SPEC MOVED 23 -> 25 AND WE HAVE NOT DIFFED IT - that is a genuine outstanding item, recorded below, not glossed.
Tab 2 | 4 | Schedule - which drawing of the Schedule is canonical, and is Sasha Grosman's design final? | NEW, and it is the precondition on a ruling the QA lead has ALREADY given, verbatim: "Yes if Sasha's design is final." We cannot establish that ourselves - it needs a person to confirm. | No case is on hold for it, and that is the point: about 48 Schedule labels were pinned from the July prototype and would silently be stale if the newer drawing is the finished one. SV-8916 could not be verified AT ALL - its button is in his design and in no requirement of the specification. | (no held cases - the exposure is ~48 pinned labels across the Schedule suite) | READ LIVE FROM JIRA 2026-08-06, read-only: SV-8915 = Bug, OBSOLETE/Done, parent SV-8685, reporter Sasha Grosman · SV-8916 = Bug, BLOCKED, parent SV-8685, Sasha Grosman · SV-8917 = Bug, IN PROGRESS, parent SV-8685, Sasha Grosman. All three cite the same source: a claude.ai/design share URL with NO version and NO date, each "Raised in the Schedule design review with Fabian on 5 Aug 2026" - NOT the artefact at build/schedule/design-2026-07-27/ that Branko ruled authoritative at Q0. BRANKO HAS ALREADY PUSHED BACK HIMSELF, on SV-8916 at 2026-08-06T03:30:54-0500, verbatim: "Hey there is no 'Add Existing Work Order' in the design. Can you clarify where you found this?" - which is why the row quotes him back to himself rather than presenting Sasha's claim as fact. | A -> the design baseline stands, C3 in the register closes, and Sasha's three claims are answered from the artefact we hold. B -> the QA lead's conditional authorisation FIRES and we fetch and diff the newer design, re-checking ~48 labels. C -> the design source stays a PARTIAL source under Rule 31 and every design-pinned label carries that caveat. Note the register names Sasha Grosman / Fabian as the people who can say whether it is final; it is asked of Branko because HE made the July ruling and is already engaged on exactly this point.
Tab 2 | 5 | Schedule - what should happen to the calendar blocks that do NOT match the toolbar search? | NEW, from the Schedule spec v23 -> v25 diff: Q1 of build/schedule/spec-v25-2026-08-06/QUESTIONS-FOR-BRANKO.md. Confluence **v24** DELETED the fade/highlight requirement; the PRD is now SILENT on what happens instead. | ONE case, and his answer decides what it should ASSERT - SCH-TOOL-03 (C30041). It is NOT on HOLD today; it carries AUTOMATION: READY - EXPECT FAIL (SV-8874), and a HOLD is PROPOSED pending this answer (spec-v25-2026-08-06/PROPOSED-CHANGES.md §2). | C30041 https://shopview.testrail.io/index.php?/cases/view/30041 | VERIFIED LIVE 2026-08-06, read-only. Schedule Confluence page 713031682 at VERSION 25 (2026-08-06T09:13:51Z, HTTP 200): §6 now reads only "Search - Filters grid blocks by matching against customer name, WO number, unit number, technician name, and line name." Searched the whole v25 body: "non-matching" = 0 hits, "de-emphas" = 0, "dim" = 0; the single "faded" hit is the series "continues" label and is unrelated. SO THE PRD IS SILENT, NOT REVERSED. JIRA READ LIVE: SV-8686 (Story, TESTING QA, parent SV-8685) STILL CARRIES IT TWICE - Requirements verbatim "Non-matching blocks fade; matching blocks highlight. - (PRD: §6)" and Acceptance Criteria verbatim "...then matching blocks highlight and non-matching blocks fade." SV-8874 (Story Defect, parent SV-8686) is OBSOLETE/Done, resolved 2026-08-06T03:32:42-0500 by Milos Vasic, whose comment reads "All good on this one updated the PRD , i will close this ticket as absolute", 81 seconds before v24. TESTRAIL READ LIVE: C30041's title is "Toolbar search highlights matching blocks and fades non-matching ones" and expected item 1 is "Blocks that match the search are highlighted; blocks that do not match fade." - so the deleted requirement is in the title AND the body. | A -> the fade assertion is REMOVED and the case asserts non-matching blocks are gone; marker becomes READY. B -> the build has a real defect and SV-8874 was closed wrongly. EITHER WAY THE MARKER IS ALREADY WRONG, because it names SV-8874 as an open expect-fail and SV-8874 is closed. Rule 57 is why this is asked and not read off the build: the PRD's SILENCE licenses REMOVING our assertion, it does not license asserting the opposite. Stefan Vukovic's "per design we show only shifts/events that are matching the search" (2026-08-06T03:15:35-0500) is an ENGINEER's statement about a design we do not hold, so it is not a PO ruling (Rule 33). SV-8686 is the OWNER's to correct - Rule 38, not ours to edit.
Tab 2 | 6 | Schedule - can the estimated hours still be typed into inside the shift window? | NEW, Q2 of the same file, and THE SHARPEST ROW ON THE SHEET: it is the difference between a case that passes and a case that fails on the same build. Branko's own ruling created the ambiguity 17 minutes after he published v25. | ONE case - SCH-MODAL-05 (C30012). Currently AUTOMATION: READY, i.e. we expect it to PASS, while the PO has closed a report saying the build does not allow the edit. A HOLD is PROPOSED, not applied (PROPOSED-CHANGES.md §5). | C30012 https://shopview.testrail.io/index.php?/cases/view/30012 | VERIFIED LIVE 2026-08-06, read-only. v25 §4.9 STILL READS "Estimated hours with inline edit." - the spec line was NOT changed by v24 or v25. SV-8695 (Story, Ready for QA) Requirements verbatim: "...scope summary with scheduled line(s) and labor/total, estimated hours with inline edit..." - SO TWO WRITTEN SOURCES STILL REQUIRE IT. Against that, SV-8829 (Story Defect, OBSOLETE/Done, parent SV-8695) carries Branko Cicovic's ONLY comment, at 2026-08-06T04:31:05-0500 = 09:31:05Z, SEVENTEEN MINUTES AFTER v25 was published at 09:13:51Z, verbatim: "Estimated badge should not be clickable, you can change time only in the input fields above. I updated PRD, for work order lines we just show estimate and status badge, there shouldn't be totals. Please always check the design as it is single source of truth." THE AMBIGUITY IS SCOPE: SV-8829's own steps distinguish the LINE ROW's badge ("only 1h and an Authorized badge") from the MODAL-level "estimated hours with inline edit", and his sentence names "the Estimated badge". TestRail read live: C30012 = "Estimated hours can be edited inline in the modal", refs SV-8695 (§4.9 (Estimated hours with inline edit)), marker READY. | A -> the case is WRONG, is rewritten, and both the spec line and SV-8695 are stale. B -> the case is RIGHT and SV-8829 was closed wrongly, so a defect is owed. Rule 58 is the whole reason this is a question: an ambiguous source is NEVER resolved by looking at what the build does - and flipping the case off two written sources onto one ambiguous sentence would be the Filters mistake in reverse.
Tab 2 | 7 | Schedule - his own story still says the shift window's job lines show a labour TOTAL, while his own spec now says a labour/status figure | NEW, and it is the row the QA lead asked for explicitly: a small inconsistency between two of HIS OWN documents that he owes. It also carries the second half of item 6's tidy-up. | ONE case, and it does NOT change under answer A - SCH-MODAL-04 (C30011). Marker AUTOMATION: READY. PROPOSED-CHANGES.md §1 proposes a provenance/divergence edit only, no assertion change. | C30011 https://shopview.testrail.io/index.php?/cases/view/30011 | VERIFIED LIVE 2026-08-06, read-only. v25 §4.9 verbatim: "Scope summary and the scheduled line(s) with labor/status figures." SV-8695 Requirements verbatim, STILL: "...scope summary with scheduled line(s) and labor/total..." - and per the v25 diff pass that phrase is present both BEFORE AND AFTER Branko's own description edit of 2026-08-03T08:54:30Z, so the PO edited this story three days ago and left `total` standing, then changed the PRD on 2026-08-06. THREE SOURCES AGREE AND ONE LAGS: his 22 July no-money-on-the-Schedule ruling, PRD v25 (`labor/status`), and his SV-8829 comment ("we just show estimate and status badge, there shouldn't be totals") all say no totals; SV-8695 alone still says `total`. TestRail read live: C30011 = "The modal lists the scheduled line(s) with no money fields", expected items 2-3 verbatim "...each showing its line number, title, hours, and a status pill only. 3. No labor figures and no total dollar amount appear anywhere in the modal." - so under Rules 32/33 the case ALREADY follows the three, which is why nothing is blocked on this row. | A (expected) -> nothing changes in the case; SV-8695 is corrected BY ITS OWNER (Rule 38). B -> C30011 is wrong and item 3 of its expected result must be rewritten, and the PRD needs correcting too. NOTE FOR THE QA LEAD ON WHAT WAS DELIBERATELY *NOT* ASKED: the source file's Q2b asked what the WORD "labor" means in "labor/status figures" - hours or money. That was LEFT OFF, because his SV-8829 comment already answers it in his own words and, on the source file's own admission, NEITHER answer changes the case's substance. Asking it would have re-asked a settled point for zero test consequence. Its one live consequence - that two of his documents now disagree - is THIS row. Our own text using "labor" for both hours and money in C30011 is an internal wording repair, not a product question.
Tab 2 | 8 | Schedule - for this release, does the day view keep the full 24 hours or only the working hours plus a buffer? | NEW, Q3 of the same file. Asked so we are not silently relying on a change-request note that contradicts the live spec - not because any case is wrong today. | ONE case, and NO change is proposed to it - SCH-DAY-01 (C30001). It is correct against v25 as written and already covers the full start-time hierarchy. | C30001 https://shopview.testrail.io/index.php?/cases/view/30001 | VERIFIED LIVE 2026-08-06, read-only. v25 §4.8 verbatim: "The full 24-hour timeline remains intact and scrollable.", and §3.2: "Day view. A 24-hour timeline per technician row with time-positioned blocks." Against that, SV-8915 (Bug, OBSOLETE/Done, parent SV-8685, reporter Sasha Grosman) carries under "Related change requests", verbatim: "Schedule width should render only business hours plus a small trailing buffer rather than the full 24 hours; after-hours scheduling is an edge case reachable by scrolling. Tracked separately on the enhancements list for the Schedule design." TestRail read live: C30001 = "Day view auto-scrolls to the working-day start; manual scrolling stands", refs SV-8694 (§4.8 (Auto-scroll to business hours)), marker AUTOMATION: READY - EXPECT FAIL (SV-8837) - and SV-8837 is live-confirmed STILL OPEN (Story Defect, Ready for QA, parent SV-8694), so that marker is correct and untouched by this question. | A (recommended, and what the spec says today) -> nothing changes; the item closes in the decisions register as out of V1. B -> §4.8 becomes wrong and needs a spec edit BEFORE any case change - the spec is corrected first, never the case. SV-8915 is ALSO the design-authority ticket, which is why its other half sits on Schedule item 4 of this sheet rather than here.
Tab 3 | 1-6 | Schedule - six behaviours only the engineering plan describes: pre-existing shifts and events · a multi-day job on the Dashboard · an appointment set while creating a job · jobs from another branch · the priority on a job · a limit on how long a spread can be | CARRIED FORWARD VERBATIM from the 2026-08-05 sheet's engineering-only tab. All six were re-checked against spec v25 today and all six are STILL absent from it. | No case is held on these six. They are candidate coverage rather than blocked coverage - Rule 30 forbids turning an engineering plan into a product requirement without the PO. | (no held cases) | VERIFIED LIVE 2026-08-06 against Schedule spec v25, searching the whole body: pre-existing shifts/migration = 0 matches · dashboard = 0 · appointment = 0 · another branch / cross-location = 0 · spread length limit (8 weeks / 120 shifts / maximum span) = 0. Only "priority" appears, and only as a bare field name with no behaviour attached. So none of the six was answered by the v23 -> v25 edits. | Each answer either creates authorable coverage or closes the item as out of scope. Nothing here is urgent, which is why it is the last tab - but leaving them off would make six deliberate omissions indistinguishable from six misses (Rule 46).
HONESTY AND METHOD NOTES
ADDENDUM 2026-08-06 - FOUR SCHEDULE ITEMS ADDED, TAKING THE SHEET FROM 17 TO 21. They come from build/schedule/spec-v25-2026-08-06/QUESTIONS-FOR-BRANKO.md, the Schedule spec v23 -> v25 diff. They are APPENDED as Schedule items 5-8 rather than re-ordered into the tab, so the established structure and the carried-forward wording are untouched (Rule 16); the tab note names items 5 and 6 as the decisive ones so their importance is still visible on the reader tab. TWO OF THEM EACH DECIDE A VERDICT: item 5 decides what C30041 should assert, item 6 decides whether C30012 passes or fails. Nothing was applied to TestRail - no case was edited, and the HOLDs those two items imply are PROPOSED in PROPOSED-CHANGES.md, not written.
ONE OF THE FOUR SOURCE QUESTIONS WAS DELIBERATELY LEFT OFF, AND THIS IS THE REASON (Rule 55: ask what is unclear; it does not say invent an ask). The source file's Q2b asked what the word "labor" means in v25's new phrase "labor/status figures" - the number of HOURS or a MONEY amount. It is NOT asked, on two grounds, both checked rather than assumed. FIRST, HE HAS ALREADY ANSWERED IT IN HIS OWN WORDS: SV-8829, 2026-08-06T04:31:05-0500, verbatim "for work order lines we just show estimate and status badge, there shouldn't be totals" - which, with his 22 July no-money-on-the-Schedule ruling, says plainly that no money appears. SECOND, THE SOURCE FILE ITSELF RECORDS THAT NEITHER ANSWER CHANGES THE CASE: "Neither answer changes the case's substance; A confirms it as written." So it would have cost a PO round trip for zero test consequence - and re-asking something a source has already settled is the exact embarrassment this project has had once already. ITS ONE GENUINELY LIVE CONSEQUENCE IS ON THE SHEET as Schedule item 7: that his STORY and his SPEC now disagree (`labor/total` vs `labor/status`), which is a fork with a real answer and a named owner. The residual ambiguity is in OUR OWN text - C30011 uses "labor" for both hours and money in one expected result - and that is an internal wording repair, not a question for a product owner.
THE DESIGN-AUTHORITY QUESTION WAS DELIBERATELY *NOT* ADDED AS A NEW ROW, ON THE QA LEAD'S INSTRUCTION AND BECAUSE IT WOULD HAVE BEEN A DUPLICATE. The source file's Q4 is a two-part item. Its PRODUCT half - which drawing of the Schedule is the one to work from - is ALREADY Schedule item 4 on this very sheet, and asking it twice inside one workbook would be the drip Rule 55 exists to prevent, in miniature. Its PROCESS half - whether a design may outrank the written description in OUR OWN method - is a decision for the QA LEAD, not for Branko, and has been put to him separately. Branko is asked which drawing is canonical; he is not asked to rule on our sourcing rules.
WHY ONE FILE AND NOT TWO (Standing Rule 55). build/branko-questions-2026-08-05/ holds a 13-item Branko sheet that is READY TO SEND and WAS NEVER SENT (register row C4). Producing a second sheet without absorbing it would leave the QA lead holding two unsent sheets for the same person - the exact 'drip of separate asks' Rule 55 exists to prevent. So this workbook CARRIES FORWARD all 13 of its items and adds 8 new ones = 21 (4 added when it was first built, and 4 more Schedule items added later the same day from the spec's move to version 25). ⚠️ ACTION NEEDED FROM THE QA LEAD: the 2026-08-05 workbook should be marked SUPERSEDED so an old one cannot go out by mistake. It was NOT edited by this pass, because this task was scoped to write only inside build/filters/questions-2026-08-06/ and build/report-suite/questions-2026-08-06/.
HOW DRIFT WAS PREVENTED: every carried-forward reader-facing row is IMPORTED from the 2026-08-05 generator's own TAB1/TAB2/TAB3 lists at build time, not retyped. So the 13 carried items are byte-identical to the rows that sheet carried - the same technique the 2026-08-04 Chris consolidation used. Only the 8 new items and the tab notes are new text.
SV-8876 IS DELIBERATELY NOT ON THIS SHEET, AND THE BRIEF FOR THIS TASK WAS WRONG ABOUT IT. The brief listed it as "Ahtasham's clarification question, still his to answer", and CLAUDE.md's Filters section says "Branko owes SV-8876". READ LIVE FROM JIRA 2026-08-06: SV-8876 is a Task, status DONE, resolution Done, resolved 2026-08-05T08:38:16-0500, parent SV-8785, reporter Ahtasham Amjad. He CLOSED IT HIMSELF, with one comment, verbatim: "closing this as it was a gap with test case , I've updated the test case here >>https://shopview.testrail.io/index.php?/cases/view/29557 And created a story defect >> as the build is not behaving as per PRD". Putting it in front of Branko would have re-asked a closed question - the exact embarrassment this project has already had once. THE HALF THAT IS GENUINELY STILL HIS is the narrower one and IS on the sheet, as Filters item 5: did he want the buttons on one row, in which case the developer job should be cancelled? SEPARATE POINT FOR THE QA LEAD, NOT FOR BRANKO: that comment says Ahtasham EDITED OUR CASE C29557. Under Rule 38 we do not touch his cases and he should not be editing ours; this is reported, not acted on.
THE FILTERS SPEC MOVED TO VERSION 19 THIS MORNING AND NO QUESTION WAS MANUFACTURED FROM IT. Page 572030978, version 19, 2026-08-06T11:48:47Z. Its visible change on the filter bar is S1-R3, verbatim: "Each chip displays a leading type-icon identifying the filter, the filter name, and a chevron icon indicating it opens a dropdown". THAT IS CLEAR ENOUGH TO TEST - a tester can check that each chip carries a leading icon plus a chevron, and which specific icon belongs to which chip comes from the design node the spec links. So NO ROW WAS ADDED for it (Rule 55 says ask what is unclear; it does not say invent an ask). What v19 did NOT do is resolve anything on this sheet: S9-R2 and S9-R3 are unchanged, and the S12-R2 cross-reference is still wrong. ⚠️ OWED: a proper v18 -> v19 diff. This pass checked the points the sheet depends on, not the whole document, and does not claim to have diffed it.
THE SCHEDULE v23 -> v25 DIFF HAS SINCE BEEN DONE, AND THIS ADDENDUM IS ITS OUTPUT - so the warning that stood here ("we have not diffed it") IS NOW OUT OF DATE and is corrected rather than deleted. Page 713031682 is at VERSION 25 (2026-08-06T09:13:51Z, re-confirmed live for this addendum); CLAUDE.md and build/OUTSTANDING-ITEMS-REGISTER.md still name version 23, and NEITHER WAS EDITED (out of scope for this pass - the record correction is owed). The diff lives at build/schedule/spec-v25-2026-08-06/SPEC-DIFF.md: 2 requirements changed, 1 governing-source change that is not a page edit, 3 cases affected. Its four reader-facing questions are Schedule items 5-8 of this sheet. Also re-confirmed by that diff and unchanged in v25: both shop-closure sentences survive, both click-menu wordings survive, and all six engineering-only topics are still absent - so items 1-3 and tab 3 stand exactly as written.
WORDING RULES APPLIED (Standing Rules 7 and 55): every reader-facing question row names the PROJECT (Filters or Schedule) and the SCREEN, because Branko owns THREE projects - Filters, Schedule and Global Search - so a row read on its own, days later, on a phone must still be unambiguous. Story and epic keys appear in plain form only where they orient him. No case IDs, no requirement anchors, no technical terms and not the word VIU appear anywhere he reads. Each question is a plain A/B/C with a blank for the answer, and each carries a one-line reason so the consequence is visible.
SOURCE-CURRENCY (Standing Rules 31 and 59), fetched LIVE and re-read immediately before writing, 2026-08-06: Filters spec page 572030978 = VERSION 19, HTTP 200 (in-body field still reads "Version: 1.6" - the Rule-31(a) trap; the CONFLUENCE number is the one used). Schedule spec page 713031682 = VERSION 25, HTTP 200, and STALE against our records at 23. Jira read live for SV-8876, SV-8825, SV-8915, SV-8916, SV-8917. TestRail read live for all 114 Filters cases. Designs = PARTIAL, and which artefact is canonical is Schedule item 4 on this very sheet. ADDENDUM, 2026-08-06: for the four new Schedule items the Schedule spec was RE-FETCHED live (page 713031682, version 25, HTTP 200, by Branko Cicovic at 09:13:51Z) and every sentence they rest on was searched in its body; JIRA was read live and read-only for SV-8686, SV-8695, SV-8829, SV-8874, SV-8837 and SV-8915; and FOUR SCHEDULE CASES WERE PULLED LIVE FROM TESTRAIL - C30041, C30012, C30011 and C30001, all HTTP 200, titles, refs and automation markers read from the live cases rather than from our records. So the earlier line saying "Schedule cases were NOT re-pulled this pass" now holds only for the THREE HELD C-ids on items 1-3 (C29983, C30089, C43555), which still come from committed records and are still cited as such.
THE BUILD WAS NOT OBSERVED (Standing Rules 12, 49, 60). The shared QA sign-in is dead - a read-only probe returned HTTP 401 {"error":"sso_required"} - and quick-login and switch-user were deliberately NOT called, because both rotate the shared session and would sign concurrent workers out of the other branches. BOTH BRANCHES HAVE ALSO REDEPLOYED: sv8785.qa.shopview.com now reads app-version v3.4.2-280ca5a (last-modified Thu 06 Aug 2026 09:37:49 GMT) where the Filters passes ran on v3.4.2-d00239b. So every build-side sentence quoted to Branko - the Status chip behaving as the description says, the filter bar on one row, the capital F - comes from a build that no longer exists, and is worded to him as what the product does rather than as a fresh measurement. All Filters and Schedule verdicts remain PROVISIONAL and the Rule-49 queues are OPEN.
NOTHING HAS BEEN WRITTEN ANYWHERE. This sheet is a draft for the QA lead to send. Read-only on TestRail (get_sections, get_cases), on Confluence (GET content) and on Jira (GET issue). No TestRail write, no Jira write, no case edit, no run write, no application call. CLAUDE.md, build/OUTSTANDING-ITEMS-REGISTER.md and build/APP-ACTIONS-PLAYBOOK.md were not touched, and neither was the 2026-08-05 Branko workbook.