## 1 Start here
Report Suite - questions for Chris Ward - 2026-08-06
Hello Chris - thank you, your last round of answers cleared most of the reporting work straight away. This is the rest of what is genuinely still open on the REPORT SUITE (the six new reports). Thirteen items, and most are one word: about ten minutes if you go straight down the list. SHORT ANSWERS ARE PERFECT - a letter, or one line. Nothing here needs an essay. WHERE TO START. Section 1 is a single yes-or-no and it releases seven tests that are on hold today - that is the only thing we are really waiting on. Section 2 is five ordinary decisions. Section 3 is seven small tidy-ups in your own descriptions: a tick each, nothing to decide. Every question says which project and which report it is about, because we know you look after Fees & Discounts as well as the Report Suite. And to be clear - we have not edited any of your descriptions or anyone's tickets. Where two of your own documents disagree we simply say so and ask which one to keep.
# | Which project and report | What happens now | The question | Options | Your answer
SECTION 1 OF 3 - PLEASE START HERE. ONE YES-OR-NO, AND SEVEN OF OUR TESTS COME OFF HOLD THE SAME DAY.
1 | REPORT SUITE - the Location column - all six reports | This is a one-line confirmation rather than a fresh decision, and it is the only thing holding seven of our tests. You have already decided it. The same note now appears in all six report descriptions: anyone who can see more than one location gets the Location column, it is on by default, and they can switch it on or off themselves from the list of columns. Someone who can see only one location never sees it at all. What is left is only tidying. Older sentences still sit in all six descriptions saying the column appears and disappears on its own depending on how many locations are picked - and in three of them a sentence says flatly that the person cannot switch it. Those six are in Section 3 as ticks, not questions. Why we are asking: we would rather not release seven tests on our own reading of a note. One word from you and they go. | Is this right - anyone who can see more than one location gets the Location column, on by default, and can switch it on or off themselves? | A) Yes, that is the rule. It depends on what someone is allowed to see, not on what they have picked, and they can switch it whenever they like. B) No - the column should appear and disappear on its own depending on how many locations are picked, and the person should not be able to switch it. C) Something else, or it should differ between reports - please describe it.

## 2 Decisions
Section 2 - five decisions we need from you
Five questions, each a plain A or B. Two of them were asked on 5 August and are here again because they are still open, not because we forgot. Short answers are perfect.
# | Which project and report | What happens now | The question | Options | Your answer
SECTION 2 OF 3 - FIVE DECISIONS. SIX OF OUR TESTS ARE WAITING ACROSS THEM.
1 | REPORT SUITE - all six reports - which heading each one sits under in the Reports menu | The six reports are spread across three headings today. Work In Progress, Technician Utilization and Sales By Representative sit under PERFORMANCE. Parts Velocity and Inventory Value sit under PARTS. Sales By Customer sits on its own under SALES. None of the six descriptions says which heading a report belongs under - only that it appears in the Reports menu, which it does. Why we are asking: one of our tests used to expect Sales By Customer under Performance. That came from a walkthrough video last month rather than from any current description, so we have taken it out rather than guess. Today the test only records the heading, which is honest but not much of a test. | Is that arrangement the one you want - three under Performance, two under Parts, and Sales By Customer under Sales? | A) Yes, leave them as they are - and please add the heading to each description so there is something to test against. B) No - all six should sit together under one heading. Please say which. C) Something else - please describe where each one should go.
2 | REPORT SUITE - Sales By Customer - an invoice the person is not allowed to open | Your Sales By Customer description says two different things about the same thing, and both are in the current version. One part says a person who cannot open an invoice gets no link at all - the invoice number is shown as ordinary text. Another part says they do get a link, click it, and land on the standard "you are not allowed in" page, from which they can go back. Why we are asking: three of our tests are on hold on this one point, and the two answers need completely different tests. This went to you on 5 August - it is here again only because it is still open, not because we forgot. | Which one do you want? | A) No link at all. For that person the invoice number is plain text and there is nothing to click. B) A link they can click, which takes them to the "you are not allowed in" page. C) Something else - please describe it.
3 | REPORT SUITE - Sales By Representative - the same link rule, which never reached the numbered requirements | On 5 August you added the rule that a link is only a link when the person is allowed to open what it points at. Thank you - it went into Sales By Customer properly. On Sales By Representative it only reached the opening paragraph. The numbered requirements underneath still say, flatly, that every invoice number and every customer name on a detail row is a clickable link. Why we are asking: a tester reading only those numbered requirements would expect a link for everybody, and would raise a fault against a build that is correct. | Should the numbered requirements on Sales By Representative be updated to match Sales By Customer? | A) Yes, please update them so they say the same as Sales By Customer. B) No - Sales By Representative should keep links for everybody, whether or not they can open what the link points at.
4 | REPORT SUITE - Sales By Representative - what paper size and orientation the printable downloads should use | Your two descriptions disagree with each other. Sales By Representative says its printable downloads are A4 portrait. Sales By Customer says A4 landscape. The Sales By Representative table has sixteen columns, which would not fit across a portrait page at all, and when we last looked both reports came out landscape. Why we are asking: one of our tests says portrait, word for word from your description, and it is queued for the automation team to pick up. If portrait is not what you want, we would much rather fix that test now than after it is automated. | For Sales By Representative, should the printable downloads be A4 landscape or A4 portrait? | A) A4 landscape, the same as Sales By Customer - and please correct the Sales By Representative description to say landscape. B) A4 portrait, as its description says today. (Then we will raise the difference with the developers.)
5 | REPORT SUITE - Sales By Representative - the word "Representative" on the screen and on the customer's card | You confirmed that "Representative" on its own is fine in the downloaded files, and we have matched our tests to that. Two tests are still on hold because they are about the word on the SCREEN and on the customer's card, not in the files. You were only asked about the files, so we did not want to stretch your answer to cover screens you had not been shown. Why we are asking: two tests come off hold the moment you answer, whichever way you answer. Asked on 5 August, still open. | Should the full word "Representative" also be used on the screen and on the customer's card? | A) Yes - use the full word everywhere it appears, not only in the downloaded files. B) No - only the downloaded files matter. The screen can stay as it is.

## 3 Just a tick
Section 3 - seven small tidy-ups in your own descriptions
NOTHING TO DECIDE ON THIS TAB. Six of these are the unfinished half of a decision you have already made, and one is a sentence you have already written for three reports which we are asking for on the other three. A tick is enough on each.
# | Which project and report | What happens now | The question | Options | Your answer
SECTION 3 OF 3 - SEVEN TIDY-UPS, A TICK EACH. NO TEST IS BLOCKED BY THESE.
1 | REPORT SUITE - Parts Velocity - one leftover sentence about the Location column | Your decision note in this description says the person can switch the Location column on and off. A sentence further down still says the column "is not user-toggleable" and is not offered in the column list. That is the strongest of the six leftovers - it says the opposite of your decision, in plain words. | Nothing to decide - please delete or reword that sentence next time you have the description open. | (Nothing to choose - a tick is enough.)
2 | REPORT SUITE - Work In Progress - one leftover sentence about the Location column | Your decision note here says the person can switch the column on and off. A sentence further down still says it is shown automatically and that the user does not toggle it, and two other places describe it as appearing on its own. So this description currently contains both answers, one of them in so many words. | Nothing to decide - please delete or reword those sentences next time you have the description open. | (Nothing to choose - a tick is enough.)
3 | REPORT SUITE - Inventory Value - one leftover sentence about the Location column | Your decision note here says the person can switch the column on and off. A sentence further down still says its visibility follows the location scope automatically, and that it is not one of the columns offered in the column-selection control. So this description also contains both answers. | Nothing to decide - please delete or reword that sentence next time you have the description open. | (Nothing to choose - a tick is enough.)
4 | REPORT SUITE - Sales By Customer - one milder leftover about the Location column | Milder than the three above. This description does not say the person cannot switch the column - it simply still has a summary sentence saying the column shows only when more than one location is in view and hides when a single location is in view. Your newer wording in the same document says the opposite: on by default, and available whatever the person has picked. | Nothing to decide - please tidy that summary sentence next time you have the description open. | (Nothing to choose - a tick is enough.)
5 | REPORT SUITE - Sales By Representative - one milder leftover about the Location column | The same mild leftover. A numbered requirement still says the column shows only when the view spans more than one location, and hides when it is narrowed to a single one. Your newer wording earlier in the same document says it is on by default and can be switched on or off whatever is picked. | Nothing to decide - please tidy that requirement next time you have the description open. | (Nothing to choose - a tick is enough.)
6 | REPORT SUITE - Technician Utilization - one milder leftover about the Location column | The same mild leftover, in two places: the column is described as hidden whenever a single location is in view. Your newer wording in the same document says it is on by default and can be switched on or off regardless of how many locations are picked. | Nothing to decide - please tidy those two sentences next time you have the description open. | (Nothing to choose - a tick is enough.)
7 | REPORT SUITE - Parts Velocity, Technician Utilization and Work In Progress - the download size limit you have already written down elsewhere | All six reports refuse to build a download once the result would run past about ten thousand rows, and show "This report is too large to export. Narrow the date range or filters, then try again." That is deliberate and it is correct. Three of your six descriptions already say so - Sales By Customer, Sales By Representative and Inventory Value. The other three do not mention it at all. So this is not a question about whether there is a limit; it is a request to copy a sentence you have already written into the three that are missing it. Why it matters: on those three a tester who meets that message has nothing to check it against, and the honest thing for them to do is raise it as a fault - against behaviour that is entirely correct. One correction to our own record, so you are not misled: we previously told you that NONE of the six mentioned this limit. That was wrong - three of them do. | Please add the limit to Parts Velocity, Technician Utilization and Work In Progress. | A) Yes, I will add it to those three. B) No - leave it out of those three. (Then please say why they are different, because the product behaves the same on all six.)

## QA internal - not for Chris
QA-ONLY - INTERNAL - NOT FOR CHRIS. Do not send this tab. TestRail case IDs, requirement anchors, live evidence and the corrections to our own records live here so the tabs Chris reads stay plain (Standing Rules 7, 8 and 55).
PER-ITEM MAPPING - EVERY QUESTION CHRIS SEES
Tab | Item | What it asks | Where the question comes from | Affected internal case IDs (TestRail C-id) | TestRail links | Spec anchors + live evidence | What each answer resolves to
Tab 1 | 1 | The Location column - is the access-gate + user-toggleable model the ruling? | Q5 of full-viu-2026-08-06/QUESTIONS-FOR-CHRIS.md. Every one of the six descriptions carries the 2026-08-04 QA-review decision note stating the access-gate + toggleable model, while older requirement text in the same document states the selection-scope / auto-visibility model. He has decided; the edit is unfinished. | SEVEN cases on AUTOMATION: HOLD naming this contradiction - WIP-COL-02 (C30467); IV-COL-01 (C30551); IV-COL-04 (C30554); IV-EXP-02 (C30588); SBC-LOC-04 (C38912); IV-LOC-06 (C38917); WIP-PERS-05 (C43551) | C30467 https://shopview.testrail.io/index.php?/cases/view/30467 · C30551 https://shopview.testrail.io/index.php?/cases/view/30551 · C30554 https://shopview.testrail.io/index.php?/cases/view/30554 · C30588 https://shopview.testrail.io/index.php?/cases/view/30588 · C38912 https://shopview.testrail.io/index.php?/cases/view/38912 · C38917 https://shopview.testrail.io/index.php?/cases/view/38917 · C43551 https://shopview.testrail.io/index.php?/cases/view/43551 | LIVE-VERIFIED 2026-08-06 over the six Confluence page bodies (HTTP 200 on all six): SBC v15 · SBR v17 · PV v5 · TU v6 · WIP v9 · IV v4. HARD contradiction (the text denies the user can toggle it) in PV v5 (near S4-R1, "is not user-toggleable"), WIP v9 S7-R13 ("the user does not toggle it in the column selector") and IV v4 S7-R6 ("not one of the columns offered in the column-selection control"). MILDER contradiction (visibility follows the SELECTION rather than ACCESS) in SBC v15 (overview line), SBR v17 S21-R7 and TU v6 (two lines). The newer model is stated at SBC S4-R12, SBR (near S21-R7's own story), PV (near S3-R3), TU (near S7-R10), WIP and IV in their access-gate paragraphs, all with the phrase "regardless of how many locations are currently selected" on SBC/PV/TU. | A -> the 7 come off hold unchanged in substance, and the 7 tidy-up rows on tab 3 are just spec edits. B -> the 7 are rewritten to the auto-visibility model AND the decision note in all six descriptions has to come out. THE COUNT: 7, not 8, 12 or 16. Counted live from TestRail on 2026-08-06 - 476 of our cases under group 4281, 35 mention the Location column, 43 are on HOLD for any reason, and exactly 7 of those name this contradiction. The brief said 8, build/OUTSTANDING-ITEMS-REGISTER.md C2 says 12, and an earlier draft said 16 - all three are stale; the 2026-08-06 pass released the others.
Tab 2 | 1 | Which heading each of the six reports sits under in the Reports menu | Q1 of QUESTIONS-FOR-CHRIS.md. The specifications are SILENT: SBC v15 Story 1 says only "'Sales By Customer' appears in the Reports left-side navigation". The 'Performance group' claim traced to a 30 July walkthrough video and the spec has been revised twice since without naming a group. | SBC-NAV-01 (C30096) - repaired by the 2026-08-06 pass to assert only what the specification asserts, and now AUTOMATION: READY. NOTHING is on hold for this one. | C30096 https://shopview.testrail.io/index.php?/cases/view/30096 | Spec silence verified live 2026-08-06. Build-side heading observation (SALES / PARTS / PERFORMANCE) comes from the 2026-08-06 pass on build v3.5-16cf83f and was NOT re-verified today - the shared QA sign-in returns HTTP 401 sso_required, and quick-login / switch-user were deliberately not called. | A -> he adds the heading to each description and C30096 regains a real assertion. B -> a developer job plus six description edits. Either way C30096 stops being a record-it-only case. Recorded also in full-viu-2026-08-06/NO-SOURCE-DEFECTS.md item 3 as deliberately not filed, because filing it would assert a requirement no current document contains (Rule 57).
Tab 2 | 2 | Sales By Customer - is a person who cannot open an invoice given a link at all? | Q3 of QUESTIONS-FOR-CHRIS.md, and it was already asked on 2026-08-05. SBC v15 states BOTH: S9-R1a says the number is a link only when the user may open the target and otherwise plain text; S9-N2 says that user is shown the standard access-denied page and can press back. | THREE cases on AUTOMATION: HOLD - SBC-PERM-04 (C30100); SBC-LINK-05 (C43558); SBR-LINK-06 (C43559) | C30100 https://shopview.testrail.io/index.php?/cases/view/30100 · C43558 https://shopview.testrail.io/index.php?/cases/view/43558 · C43559 https://shopview.testrail.io/index.php?/cases/view/43559 | Verified live 2026-08-06 in SBC v15: "Each invoice number on a detail row is a clickable link." sits alongside "The invoice number is rendered as a link only when the user has permission to open the target it links to ... a user without that permission sees the invoice number as plain text." and "If the user lacks permission to open the destination invoice, the destination page shows the application's standard access-denied state." | A -> C43558/C43559 assert plain text and C30100 is retired or rescoped to the direct-URL case only. B -> C30100 stands and the plain-text half of C43558/C43559 is removed. NOTE: all three ALSO need the second non-administrator sign-in (register row C1), so his answer alone does not make them runnable - it makes them writable.
Tab 2 | 3 | Sales By Representative - the link-permission rule is missing from the numbered requirements | Q4 of QUESTIONS-FOR-CHRIS.md. His 2026-08-05 rule reached SBR's introductory §2 but not its numbered requirements. | SBR-LINK-06 (C43559) - already counted above; no additional case is held by this row | C43559 https://shopview.testrail.io/index.php?/cases/view/43559 | Verified live 2026-08-06 in SBR v17: §2 carries "rendered as a link only when the user has permission to open that target, otherwise plain text", while the numbered requirements still read "Each invoice number on a detail row is a clickable link." and "Each customer name on a detail row is a clickable link that navigates the current tab to the customer's record." The 2026-08-05 change-log entry in the same page confirms the rule was applied. | A -> a spec edit only; our cases already follow the conditional rule. B -> SBR diverges from SBC on the same rule and C43559 splits into two cases.
Tab 2 | 4 | Sales By Representative - A4 landscape or A4 portrait for the printable downloads? | Q7 of QUESTIONS-FOR-CHRIS.md (added by the third session). SBR v17 says A4 portrait; SBC v15 says A4 landscape. A sixteen-column table cannot fit portrait. | SBR-EXP-01 (C30278) asserts "The PDF is A4 portrait" word for word and is currently AUTOMATION: READY. Its sibling SBR-EXP-02 (C30279) is READY - EXPECT FAIL (SV-8981) for a different, unrelated fault. | C30278 https://shopview.testrail.io/index.php?/cases/view/30278 · C30279 https://shopview.testrail.io/index.php?/cases/view/30279 | Verified live 2026-08-06. SBR v17, verbatim: "Both PDFs are server-rendered and delivered as a file attachment, in A4 portrait, edge-to-edge ...". SBC v15, verbatim: "The PDF is A4 landscape with 25px margins on all sides ...". PV v5 separately documents "A3 landscape", so A3 is not undocumented across the suite. | A (landscape) -> C30278's orientation line is rewritten AND its marker must move, because a case asserting portrait against a landscape build cannot honestly stay plain READY. B (portrait) -> a developer job, and C30278 becomes READY - EXPECT FAIL. HONEST CORRECTION: QUESTIONS-FOR-CHRIS.md says "the test is on hold for this one point" - it is NOT; C30278 reads AUTOMATION: READY live today. The A3 half is already reported and is not asked here.
Tab 2 | 5 | Does "Representative" in full also apply on screen and on the customer's card? | Carried forward from rulings-2026-08-05 Tab 3 item 2, still unanswered. His answer covered only the download column heading; extending it to the screen would be stretching it past what he wrote (Rule 12). | TWO cases on AUTOMATION: HOLD - SBR-WO-01 (C30310); SBR-WO-06 (C30315) | C30310 https://shopview.testrail.io/index.php?/cases/view/30310 · C30315 https://shopview.testrail.io/index.php?/cases/view/30315 | Both cases read AUTOMATION: HOLD - "waiting on an answer from the product owner" live on 2026-08-06, so the question is demonstrably still open. Their provenance lines cite SBR v17 S19-R1/S19-N1 and S19-R7/S19-E1. | A -> both keep the full-word expectation and a developer job is raised. B -> both are reworded to the short form. Either way 2 cases come off hold.
Tab 3 | 1-6 | Six per-report tidy-ups of the leftover Location-column wording | The unfinished half of his own 2026-08-04 decision. Deliberately one row PER REPORT, because each is a different sentence in a different document and a single combined row would give him nothing to act on. | No case is held by these six rows on their own - they are the spec-side twin of tab 1's single question, whose 7 held cases are listed above. | (see tab 1's row) | Live 2026-08-06, per report. HARD (denies toggling): PV v5 near S4-R1 · WIP v9 S7-R13 · IV v4 S7-R6. MILD (selection-scope wording): SBC v15 overview line · SBR v17 S21-R7 · TU v6, two lines. WIP additionally carries the auto-visibility wording near S9-E1 and in its own change-log entry. | ALL SIX ARE EDITS, NOT DECISIONS - which is why they are ticks. IMPORTANT COUNT CORRECTION: the brief and the register both say FOUR specs still state it both ways (naming SBR S21-R7, WIP S7-R13, IV S7-R6, SBC S13-R4, plus PV as never-touched). Live today it is SIX - all six descriptions still contain both models, three of them in explicit terms. SBC's live contradiction is NOT at S13-R4; it is an overview line. Nothing was taken on trust.
Tab 3 | 7 | The ~10,000-row download limit is missing from three descriptions | Q6 of QUESTIONS-FOR-CHRIS.md, narrowed. It is real and deliberate - epic story SV-8591 "Export contract + 10k row-cap guard". | No case is on hold for this. It is a documentation gap that would make a tester raise a fault against correct behaviour. | (no held cases) | COUNTED LIVE 2026-08-06 over the six spec bodies. PRESENT in three: SBC v15 ("Each CSV is capped at 10,000 data rows" and the same for PDF), SBR v17 ("the export's row cap of 10,000 data rows", S14-E2), IV v4 ("10,000 rows" plus the verbatim message). ABSENT from three: PV v5, TU v6, WIP v9 - zero matches for 10,000 / 10k / "too large to export" in any of them. | A -> three spec edits and the message becomes testable everywhere. B -> he must explain why three reports differ, because the product does not. HONEST CORRECTION CARRIED ON THE READER TAB ITSELF: full-viu-2026-08-06/FINDINGS.md and FILED.md both say "none of the six specifications mentions the cap" - that is WRONG, and the sheet tells him so rather than quietly asking the narrow question.
HONESTY AND METHOD NOTES
THIS IS THE FRIENDLY, FORWARD-AS-IS VERSION of Questions-for-Chris-Ward_Report-Suite_2026-08-06.xlsx, produced on the QA lead's instruction: "Give me the friendly and easy to read and understandable files for Chris and Branko." ALL 13 ITEMS ARE CARRIED OVER - none dropped, none added, no substance changed. What changed: a short warm opening note, ordering by what to do first (the confirmation that releases held tests, then the decisions, then the tick-box tidy-ups) with the headings saying so, and shorter sentences. The three tabs are the same three groups the earlier sheet had, renamed "1 Start here", "2 Decisions" and "3 Just a tick" so the order to work in is visible from the tab strip on a phone.
THE EARLIER WORKBOOK IS SUPERSEDED, NOT DELETED. Both files sit in this folder. Send THIS one; the earlier pair is kept as the record of what was verified and when. Its QA tab and this one carry the same mapping - the rows and notes below are IMPORTED from gen_chris_sheet.py at build time, not retyped, so the two cannot drift.
NO SOURCE WAS RE-FETCHED FOR THIS PASS AND NONE NEEDED TO BE. The content was verified live against the six specifications earlier on 2026-08-06 (Sales By Customer v15, Sales By Representative v17, Parts Velocity v5, Technician Utilization v6, Work In Progress v9, Inventory Value v4) and this pass only rewrote the presentation. NOTHING WAS WRITTEN ANYWHERE: no TestRail call, no Jira call, no Confluence call, no application call.
HOW THE POPULATION WAS SEARCHED (Standing Rule 50): all cases under TestRail group 4281 were pulled LIVE read-only on 2026-08-06 - 481 live, of which 476 are ours and 5 are Vladimir Tomovic's (C38919-C38923, hands off per Rule 38). Every one of the 476 was searched in full across title, preconditions, steps and expected results. No sampling. Counts reported to Chris are the live counts, not the counts in our own notes.
WHAT WAS DELIBERATELY LEFT OFF, AND WHY - (1) Q2 of QUESTIONS-FOR-CHRIS.md, "what should the totals line do when nothing matches?" IS NOT ON THIS SHEET. Its premise is false. SBC v15 answers it TWICE, verbatim: "If an export (CSV or PDF) is triggered while the active filters match no customers ... the export still downloads, containing the column headers and a totals row of zeros, with no data rows and no warning" and "When no customer is selected (every customer cleared), the report shows the empty state (Story 17) and the totals row shows zeros" (both near S18-R10/R11, read live 2026-08-06). So the build showing NO totals line is a DEFECT against his own document, not a product decision - and Rule 7 forbids putting a bug in front of a PO. Asking it would also have re-asked a question his own spec answers, which we have embarrassed ourselves with once already. FOR THE QA LEAD: full-viu-2026-08-06/NO-SOURCE-DEFECTS.md item 2 says "No requirement says what the totals line should do when nothing matches" - that is wrong, and SBC-EXP-11 (C30173) still asserts the zeros row and reads AUTOMATION: READY. This wants a ticket, not a question. Those files were NOT edited - they belong to another pass.
WHAT WAS DELIBERATELY LEFT OFF - (2) the en-dash vs em-dash in the Sales By Customer PDF date heading (NO-SOURCE-DEFECTS.md item 4). It is a defect, it is sourced to S15-R11, and it needs a one-word QA-lead ruling (fold into SV-8937, file separately, or drop) - not a PO question. (3) The Location column not sorting - already filed as SV-8963. (4) The Work In Progress export failing with a server error - already covered by SV-8907. (5) The ~10,000-row refusal as a suspected defect - it is DELIBERATE and in the epic (SV-8591), so only the documentation half is asked.
WHAT WAS DELIBERATELY LEFT OFF - (6) the date-range chooser's Today and Yesterday presets. QUESTIONS-FOR-CHRIS.md records that we nearly asked this and then found he ANSWERED it on 5 August, with our own case already following the answer. Not re-asked. That check - our own newer sources first - is what kept it off the sheet.
WORDING RULES APPLIED (Standing Rules 7 and 55): every reader-facing question row names the PROJECT (Report Suite) and the REPORT, because Chris Ward also owns Fees & Discounts and a bare "the export" or "the date filter" would be genuinely ambiguous to him days later on a phone. Story or epic references appear in plain form only where they orient him. No case IDs, no requirement anchors, no HTTP terms, no endpoint names, no internal names and not the word VIU appear anywhere he reads. Each question carries a one-line "why we are asking" so the consequence is visible, and every question is a plain A/B/C with a blank for the answer.
SOURCE-CURRENCY (Standing Rules 31 and 59), all fetched LIVE at the start of this pass AND re-read immediately before the files were written, on 2026-08-06: the six Confluence page bodies over GET /wiki/rest/api/content/<id>?expand=version,body.storage, HTTP 200 on all six - SBC 577634305 v15 (2026-08-05T17:53:06Z) · SBR 585629698 v17 (2026-08-05T17:53:08Z) · PV 620888066 v5 (2026-08-05T13:21:40Z) · TU 641400833 v6 (2026-08-05T13:33:10Z) · WIP 703660034 v9 (2026-08-05T17:54:07Z) · IV 720142338 v4 (2026-08-05T13:33:13Z). None moved during the pass. The CONFLUENCE version number was used, never the version written inside the document body (Rule 31's trap). Epic SV-8582 was not re-read this pass and no claim rests on it. Designs: ABSENT - spec-only project.
THE BUILD IS A SOURCE AND IT IS STALE FOR US TODAY (Standing Rules 12, 49, 60). The shared QA sign-in is dead - GET /api/auth/me/fe-permissions on sv8582api returns HTTP 401 {"error":"sso_required"} - and quick-login and switch-user were deliberately NOT called, because both rotate the shared session and would sign concurrent workers out. So NO build-side claim on this sheet was re-verified today. Worse, the branch has REDEPLOYED since the pass we are citing: index.html on sv8582.qa.shopview.com now reads app-version v3.5-f77875c, last-modified Thu 06 Aug 2026 10:43:37 GMT, where the 2026-08-06 pass ran on v3.5-16cf83f. Every build observation quoted to Chris (the three menu headings, the landscape rendering, the missing totals line) therefore comes from a build that no longer exists, and is presented to him as "when we last looked" rather than as a current fact. All Report Suite verdicts remain PROVISIONAL; the Rule-49 queues are OPEN and the 2026-08-06 pass opened none (register RS2).
NOTHING HAS BEEN WRITTEN ANYWHERE. This sheet is a draft for the QA lead to send. Read-only on TestRail (get_sections, get_cases) and on Confluence (GET content). No TestRail write, no Jira call at all in the Report Suite half, no case edit, no run write. CLAUDE.md, build/OUTSTANDING-ITEMS-REGISTER.md and build/APP-ACTIONS-PLAYBOOK.md were not touched.
THREE NUMBERS IN OUR OWN RECORDS ARE STALE AND ARE CORRECTED HERE RATHER THAN REPEATED: the held Location count is 7 (the brief said 8, the register says 12, an earlier draft said 16); the number of specs still stating the Location model both ways is 6, not 4; and three of the six specs DO document the export cap, where two of our own 2026-08-06 files say none does. An inflated blocked-count or a wrong "none of them" in front of a PO costs credibility on every other row of the sheet, so each was counted from the live source before it went on.