## Summary
CUSTOM ROLES — QA PRE-RELEASE CHECKLIST (2026-07-16)
Detailed, actionable QA-team companion to the executive file CustomRoles_Release-Readiness_Prod-vs-Staging_EXEC_2026-07-16.xlsx. Every row traces to a LIVE-OBSERVED cell of the spec-annotated prod-vs-staging comparison.
HOW TO USE THIS FILE
Work the tabs in order. P1 = must check before release (spec deviations, spec self-contradictions needing a PO ruling, and customer/money-facing permission changes) — do every row. P2 = intended-per-spec migration changes — regression-confirm each on the release build. P3 = monitor / smoke-only items (org-config gates, spec-silent components, parity already observed). Coverage Gaps = findings with no existing TestRail case (author these) plus two cells to re-observe directly on the release build. Each row carries exact build-accurate steps, the verbatim spec gate with citation, TestRail case links, the evidence path, and the exact source row(s) in the ground-truth workbook. Follow Standing Rule 12: mark a check done only after observing it live with evidence.
COUNTS BY PRIORITY
P1 — Must check before release | 12
P2 — Should check (intended per spec; regression-confirm) | 33
P3 — Monitor / no action | 7
Coverage Gaps (new cases to author + re-observe items) | 9
TOTAL checklist rows | 61
COUNTS BY CATEGORY
Deviation | 6
Spec-contradiction | 4
Intended-loss-to-confirm | 18
Intended-grant-to-confirm | 23
Coverage-gap | 9
Env-config | 1
TESTRAIL MAPPING (Standing Rule 8)
Checklist rows mapped to existing TestRail case(s) | 35
Checklist rows with NO existing case (see Coverage Gaps) | 17
GROUND-TRUTH LINEAGE (every row traces here)
Source workbook | build/custom-roles-run/Prod-vs-Staging-LIVE-VERIFIED-2026-07-14.xlsx (Full Dual Matrix, 176 dual rows + Pass-11/Pass-12/Approve-Decline/Send to Terminal/Parts-Module/New-WO tabs + Spec-Standing Conformance)
Spec truth table | build/custom-roles-run/spec-conformance/spec-truth-table.md
Canonical spec | build/custom-roles-spec-update/current-spec-2026-07-15.md
Evidence | build/custom-roles-run/live-ui-2026-07-15/ and build/custom-roles-run/live-ui-2026-07-16/
TestRail case source | build/custom-roles-run/cases-2026-07-13/ (filename = C<id>)
Generator | build/custom-roles-run/gen_qa_prerelease.py (accuracy gate built in)

## P1 — Must check before release
ID | Category | Role(s) | Capability (plain language) | What we observed (prod vs staging) | Spec says (verbatim + citation) | Why it needs checking | Check steps (manual tester) | Expected result per spec | TestRail Case ID(s) + link(s) | Evidence path | Suggested owner | Source row(s) in the ground-truth workbook
QA-01 | Deviation | Foreman | "Send to Terminal" button (card-terminal payment) shows for Foreman | PROD: hidden (org has no terminal device). STAGING: SHOWN (org has a terminal; any role that can open New Payment sees it). | “To send to terminal use must have this and “Customer Portal: ON” enabled” (spec §1i Invoicing Edit; 7/6 change log; Foreman has Customer Portal = OFF in the Toggles table) | DEVIATION (gating model): the spec role-gate = Invoicing Create & Edit + Customer Portal ON. Foreman has Customer Portal OFF, so per spec the button should be withheld; the build instead gates only on the org having a terminal device and shows it. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Foreman (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open Work Orders and open a work order whose status is Invoiced and that still has a balance due (seed a ZZAUTOTEST work order and invoice it if none exists) 3. Open the "Finance" tab on the work order 4. Click the "New Payment" button 5. In the New Customer Payment dialog, look for the blue "Send to Terminal" button | Per spec the "Send to Terminal" button should NOT appear for Foreman (Customer Portal is OFF for that role), even though the org has a card terminal. | C29434 — Send to Terminal needs Invoicing & payments Create & Edit AND Customer portal ON https://shopview.testrail.io/index.php?/cases/view/29434 C26427 — The Send to Terminal action needs Invoicing & payments Create & Edit https://shopview.testrail.io/index.php?/cases/view/26427 | build/custom-roles-run/live-ui-2026-07-16/ (Pass-12 Send-to-Terminal evidence; SendToTerminal_dialog.png per role) | PO decision (accept org-device gating or enforce Customer Portal ON) + QA retest on release build | Full Dual Matrix ¦ Foreman ¦ Send to Terminal ¦ STAGING-MORE
QA-02 | Deviation | Office User | "Send to Terminal" button (card-terminal payment) shows for Office User | PROD: hidden (org has no terminal device). STAGING: SHOWN (org has a terminal; any role that can open New Payment sees it). | “To send to terminal use must have this and “Customer Portal: ON” enabled” (spec §1i Invoicing Edit; 7/6 change log; Office User has Customer Portal = OFF in the Toggles table) | DEVIATION (gating model): spec role-gate = Invoicing Create & Edit + Customer Portal ON. Office User has Customer Portal OFF, so per spec the button should be withheld; the build shows it whenever the org has a terminal. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Office User (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open Work Orders and open a work order whose status is Invoiced and that still has a balance due (seed a ZZAUTOTEST work order and invoice it if none exists) 3. Open the "Finance" tab on the work order 4. Click the "New Payment" button 5. In the New Customer Payment dialog, look for the blue "Send to Terminal" button | Per spec the "Send to Terminal" button should NOT appear for Office User (Customer Portal is OFF for that role). | C29434 — Send to Terminal needs Invoicing & payments Create & Edit AND Customer portal ON https://shopview.testrail.io/index.php?/cases/view/29434 C26427 — The Send to Terminal action needs Invoicing & payments Create & Edit https://shopview.testrail.io/index.php?/cases/view/26427 | build/custom-roles-run/live-ui-2026-07-16/ (Pass-12 Send-to-Terminal evidence; SendToTerminal_dialog.png per role) | PO decision + QA retest on release build | Full Dual Matrix ¦ Office User ¦ Send to Terminal ¦ STAGING-MORE
QA-03 | Deviation | Parts Technician | "Send to Terminal" button (card-terminal payment) shows for Parts Technician | PROD: hidden (org has no terminal device). STAGING: SHOWN (org has a terminal; any role that can open New Payment sees it). | “To send to terminal use must have this and “Customer Portal: ON” enabled” (spec §1i Invoicing Edit; 7/6 change log; Parts Technician has Customer Portal = OFF in the Toggles table) | DEVIATION (gating model): spec role-gate = Invoicing Create & Edit + Customer Portal ON. Parts Technician has Customer Portal OFF, so per spec the button should be withheld; the build shows it whenever the org has a terminal. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Parts Technician (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open Work Orders and open a work order whose status is Invoiced and that still has a balance due (seed a ZZAUTOTEST work order and invoice it if none exists) 3. Open the "Finance" tab on the work order 4. Click the "New Payment" button 5. In the New Customer Payment dialog, look for the blue "Send to Terminal" button | Per spec the "Send to Terminal" button should NOT appear for Parts Technician (Customer Portal is OFF for that role). | C29434 — Send to Terminal needs Invoicing & payments Create & Edit AND Customer portal ON https://shopview.testrail.io/index.php?/cases/view/29434 C26427 — The Send to Terminal action needs Invoicing & payments Create & Edit https://shopview.testrail.io/index.php?/cases/view/26427 | build/custom-roles-run/live-ui-2026-07-16/ (Pass-12 Send-to-Terminal evidence; SendToTerminal_dialog.png per role) | PO decision + QA retest on release build | Full Dual Matrix ¦ Parts Technician ¦ Send to Terminal ¦ STAGING-MORE
QA-04 | Deviation | Senior Service Advisor | A/R + A/P Aging reports (Reports area) missing for Senior Service Advisor | PROD: hidden. STAGING: hidden. Both environments hide the aging report tiles, but the spec grants them. | “AR/AP aging reports are part of Reports — a user with Reports ON sees all reports, including AR/AP aging, regardless of Manage AP/AR” (spec §2a Reports note; Jul-3 change log (aging decoupled from Manage AP/AR); Senior Service Advisor has Reports = ON in the Toggles table) | DEVIATION: the spec grants the aging reports to Senior Service Advisor (Reports ON; Manage AP/AR also ON) but staging does not implement the grant — an unimplemented spec grant, not a migration loss. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Senior Service Advisor (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open "Reports" from the main navigation 3. Look for the A/R Aging and A/P Aging report tiles in the reports list | Per spec the A/R Aging and A/P Aging report tiles SHOULD be listed for Senior Service Advisor (Reports is ON for that role; aging follows Reports, all-or-nothing). | C26478 — With Reports ON, all 6 AP/AR aging reports are listed (whether or not AP/AR is on) https://shopview.testrail.io/index.php?/cases/view/26478 C26482 — With AP/AR OFF but Reports ON, all 6 AP/AR aging reports are still listed https://shopview.testrail.io/index.php?/cases/view/26482 | build/custom-roles-run/live-ui-2026-07-16/staging + /production (Pass-11 AP/AR captures, e.g. production/apar-per-role.json) | Dev fix + QA retest on release build | Pass-11 LIVE (2026-07-16) ¦ Senior Service Advisor ¦ See AP/AR ¦ MATCH
QA-05 | Deviation | Office User | Work order "Notes" tab reachable for Office User (over-grant vs the 7/14 spec) | PROD: SHOWN. STAGING: SHOWN. Both environments let Office User reach a work order and its Notes tab. | “Updated Office Role definition” (7/14 change log; the CRUD matrix now gives Office User Work Orders = — (no access); Notes ride on Work Orders View: “Users can also see the Notes tab, create notes, and edit any note” (spec §1a View)) | DEVIATION: the 14-Jul spec update removed ALL Work Orders access for Office User, so the work order (and its Notes tab) should be unreachable; both envs still show it. Needs a PO confirm + dev change before customers see it. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Office User (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open Work Orders from the main navigation (if the nav item is hidden, paste a work order detail URL directly into the browser) 3. If a work order opens, open its "Notes" tab 4. Try to add a note and to edit an existing note | Per the 7/14 spec, Office User should NOT be able to open work orders at all, so the work order Notes tab should be unreachable for Office User. | NO EXISTING CASE — coverage gap | build/custom-roles-run/live-ui-2026-07-16/ + build/custom-roles-run/live-ui-2026-07-15/ (Office_User captures) | PO decision (confirm the 7/14 Office lockdown) + Dev fix + QA retest | Full Dual Matrix ¦ Office User ¦ WO Notes (Notes tab) ¦ MATCH
QA-06 | Deviation | Office User | Part "Return" (picked-part menu on a work order) reachable for Office User | PROD: hidden (part menu shows Move only). STAGING: SHOWN (Return appears in the picked-part menu). | “Returning a part from a WOL does not require a permission” (spec §1a; 6/29 change log “Everyone has access to Return a part from a WO”; BUT the 7/14 matrix gives Office User Work Orders = —, so Office cannot reach a work order part) | DEVIATION (reachability): Return itself is ungated, but per the current spec Office User has no Work Orders access so the Return point should be unreachable; staging shows it (STAGING-MORE) — same root cause as QA-05. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Office User (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open a work order that has a picked inventory part on a line (seed a ZZAUTOTEST work order and pick a part if needed) 3. On the picked part, open the ⋮ (three-dot) part menu 4. Look for the "Return" option | Per the 7/14 spec, Office User should not reach a work order part at all, so "Return" should be unreachable for Office User. | NO EXISTING CASE — coverage gap | build/custom-roles-run/live-ui-2026-07-16/ (Pass-11 Part Return captures, e.g. production/_prod-partreturn json under live-ui-2026-07-15) | PO decision + Dev fix + QA retest | Pass-11 LIVE (2026-07-16) ¦ Office User ¦ Part Return ¦ STAGING-MORE
QA-07 | Spec-contradiction | Service Manager | "Reverse" (reverse invoice) on the work order Finance tab — spec contradicts itself for Service Manager | PROD: Finance tab hidden for the legacy role. STAGING: Finance tab SHOWN with "New Payment" + "Issue Credit" but NO "Reverse". | Matrix gives Service Manager Work Orders V/E/D and the 28-Jun rule says Reverse follows WO Delete (“For WO requires Work Order → Delete”) → would GRANT Reverse; but the migration Behavior-Changes table says Service Manager “Loses Invoicing Delete (cannot reverse)” → would WITHHOLD it. (28-Jun change log + migration table; flagged in build/custom-roles-run/spec-conformance/spec-truth-table.md) | The spec self-contradicts: matrix + 28-Jun gate say Service Manager CAN reverse; the migration table says cannot. Staging matches the migration table. Money-facing — must be resolved before release. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Service Manager (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open Work Orders and open a work order whose status is Invoiced (seed and invoice a ZZAUTOTEST work order if needed) 3. Look for the "Finance" tab on the work order detail page 4. If the Finance tab is present, open it and note which buttons appear: "New Payment", "Reverse", "Issue Credit" | PO must rule which spec statement wins. If the matrix + 28-Jun rule win: "Reverse" SHOULD appear for Service Manager (dev change needed). If the migration table wins: current staging behavior (no Reverse) is correct. | C26422 — Invoicing & payments Delete lets the user delete payments and void transactions (but not reverse invoices) https://shopview.testrail.io/index.php?/cases/view/26422 C27740 — The Invoicing & payments delete column is labelled 'Delete / Reverse' https://shopview.testrail.io/index.php?/cases/view/27740 | build/custom-roles-run/live-ui-2026-07-16/ (Pass-11 Finance captures; staging Service_Manager) | PO decision, then QA retest | Pass-11 LIVE (2026-07-16) ¦ Service Manager ¦ Finance ¦ STAGING-MORE
QA-08 | Spec-contradiction | Technician | Red "Decline" button on a "Needs Approval" line — spec ambiguous for Technician | PROD: hidden (line renders, no Approve/Decline). STAGING: hidden (line renders, no Approve/Decline). Both envs hide it. | Spec §1b Work Order Lines Edit includes “authorize lines” (Technician HAS WO Lines Create & Edit) — would grant Decline; but §4 Tech View blocks only Approve (“Cannot approve work order lines (approve action hidden)”) and never mentions Decline — Tech-View treatment of Decline is unresolvable from the spec. | The spec grants Technician WOL Create & Edit ('authorize lines' covers declining) yet Tech View only blocks Approve. Whether Technician should see Decline is a genuine open product question; both envs currently hide it. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Technician (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open a work order that has a line whose Status = "Needs Approval" (seed one via a part request that requires authorization if none exists; delete it after) 3. Look at the line's Action column for the green "Approve" and red "Decline" buttons | PO must state whether Tech View also hides "Decline". Current behavior in both envs: neither "Approve" nor "Decline" is shown to Technician. | NO EXISTING CASE — coverage gap | build/custom-roles-run/live-ui-2026-07-16/staging/approve-decline-TECH-PT.json + production/approve-decline-ALL.json | PO decision, then QA retest | Full Dual Matrix ¦ Technician ¦ Decline line ¦ MATCH
QA-09 | Spec-contradiction | Parts Technician, Office User, Sales Representative | "Send to Portal" button — spec wording contradiction (Full View vs Open Q6) for these 3 roles | Parts Technician: PROD SHOWN / STAGING hidden. Office User: PROD SHOWN / STAGING hidden. Sales Representative: both hidden (MATCH). | §4 Full View “Has access to “Send to Portal” button” + 6/10 change log (Full View required) would GRANT (all three are Full View); Open Q6 answer “Send to Portal button: can be anyone who can approve a WOL” would WITHHOLD (none has WO Lines Create & Edit). Flagged, not resolved. | Customer-facing button with two contradictory spec gates. Staging currently follows the Open-Q6 (approve-a-WOL) reading — Parts Technician and Office User LOSE Send to Portal vs prod. PO must confirm the intended wording before release. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Parts Technician (repeat as Office User, then as Sales Representative) (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open a work order that has a line eligible to send to the portal (an approved/estimate line) 3. Look for the "Send to Portal" button on the work order | PO must pick a reading. Current staging behavior = Open-Q6 reading: "Send to Portal" hidden for Parts Technician, Office User and Sales Representative. | C26466 — Full View: a user who can approve lines sees the 'Send to Portal' button https://shopview.testrail.io/index.php?/cases/view/26466 C26465 — Tech view: the 'Send to Portal' button is hidden https://shopview.testrail.io/index.php?/cases/view/26465 | build/custom-roles-run/live-ui-2026-07-16/ + build/custom-roles-run/live-ui-2026-07-15/ (per-role portal captures) | PO decision, then QA retest | Full Dual Matrix ¦ Parts Technician ¦ Send to Portal ¦ STAGING-LESS Full Dual Matrix ¦ Office User ¦ Send to Portal ¦ STAGING-LESS Full Dual Matrix ¦ Sales Representative (+Reporting) ¦ Send to Portal ¦ MATCH
QA-10 | Intended-loss-to-confirm | Service Advisor | Service Advisor loses "Reverse" (reverse invoice) on the Finance tab — money-facing, confirm before release | PROD (SA Limited View): Finance tab shows "New Payment" + "Reverse" + "Issue Credit". STAGING (Service Advisor): shows "New Payment" + "Issue Credit"; "Reverse" hidden. | “For WO requires Work Order → Delete” (28-Jun change log: Reverse Invoice moved to Work Orders → Delete; Service Advisor has Work Orders = V/E (no Delete) in the CRUD matrix) | Intended per spec (Reverse now follows WO Delete, which Service Advisor lacks) but it is a customer/money-facing REGRESSION vs prod — confirm the loss is intended and holds on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Service Advisor (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open Work Orders and open a work order whose status is Invoiced (seed and invoice a ZZAUTOTEST work order if needed) 3. Look for the "Finance" tab on the work order detail page 4. If the Finance tab is present, open it and note which buttons appear: "New Payment", "Reverse", "Issue Credit" | "New Payment" and "Issue Credit" appear; "Reverse" does NOT appear for Service Advisor. | C26422 — Invoicing & payments Delete lets the user delete payments and void transactions (but not reverse invoices) https://shopview.testrail.io/index.php?/cases/view/26422 C27740 — The Invoicing & payments delete column is labelled 'Delete / Reverse' https://shopview.testrail.io/index.php?/cases/view/27740 | build/custom-roles-run/live-ui-2026-07-16/ (Pass-11 Finance captures; prod SA_Limited_View vs staging Service_Advisor) | QA retest on release build (+ PO ack of the customer-facing loss) | Pass-11 LIVE (2026-07-16) ¦ Service Advisor ¦ Finance ¦ MATCH
QA-11 | Intended-grant-to-confirm | Service Manager, Senior Service Advisor, Foreman, Parts Manager, Parts Technician, Office User | "New Payment" (Take Payment) NEWLY GRANTED to 6 roles — money-facing, confirm each | PROD: hidden for all 6 legacy counterparts. STAGING: SHOWN for all 6 (each can open the New Customer Payment dialog). | “Create invoices, process payments directly from work orders and part sales, manage invoice fields and collect deposits” (spec §1i Invoicing Create & Edit; Open Q4; all 6 roles hold Invoicing C&E in the CRUD matrix; Office explicitly: “Office users are expected to be able to make payments but not create invoices”) | Six roles that could NOT take payments in prod now can. Intended per spec, but money movement by new hands is release-critical — verify each role can take (and only take) a payment, and that Office User still cannot create invoices. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is each of: Service Manager, Senior Service Advisor, Foreman, Parts Manager, Parts Technician, Office User (one at a time) (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open a ZZAUTOTEST work order that is Invoiced with a balance due 3. Open the "Finance" tab 4. Look for the "New Payment" button; click it and take a small test payment on the ZZAUTOTEST invoice | "New Payment" appears and a test payment completes for each of the 6 roles. For Office User additionally confirm the Create Invoice button stays disabled (hard-coded Office rule). | C26421 — Invoicing & payments Create & Edit lets the user create invoices and take payments https://shopview.testrail.io/index.php?/cases/view/26421 C26428 — Taking Deposits on a work order needs Invoicing & payments Create & Edit https://shopview.testrail.io/index.php?/cases/view/26428 C26484 — View and Manage AP/AR Data OFF still lets a user create invoices and take payments if Invoicing & payments allows it https://shopview.testrail.io/index.php?/cases/view/26484 | build/custom-roles-run/live-ui-2026-07-16/ (Pass-11 Finance captures) + Full Dual Matrix Take Payment rows | QA retest on release build | Full Dual Matrix ¦ Service Manager ¦ Take Payment (New Payment) ¦ STAGING-MORE Full Dual Matrix ¦ Senior Service Advisor (+SA Tech,+SA NoRep) ¦ Take Payment (New Payment) ¦ STAGING-MORE Full Dual Matrix ¦ Foreman ¦ Take Payment (New Payment) ¦ STAGING-MORE Full Dual Matrix ¦ Parts Manager ¦ Take Payment (New Payment) ¦ STAGING-MORE Full Dual Matrix ¦ Parts Technician ¦ Take Payment (New Payment) ¦ STAGING-MORE Full Dual Matrix ¦ Office User ¦ Take Payment (New Payment) ¦ STAGING-MORE
QA-12 | Intended-loss-to-confirm | Service Advisor, Foreman, Technician, Office User (lose) + Service Manager (gains) | "Delete Work Order" now Admin / Service Manager / Senior Service Advisor ONLY — confirm the 4 losing roles + the SM gain | STAGING-LESS (prod SHOWN → staging hidden): Service Advisor (prod SA Limited View), Foreman, Technician, Office User. STAGING-MORE: Service Manager (prod hidden → staging SHOWN). Admin + Senior Service Advisor: MATCH SHOWN. NOTE: the ground-truth matrix shows 4 losing roles (not 5). | “Delete work orders, Reverse Invoices as long as validation criteria is met (e.g. no payments made)” (spec §1a Work Orders Delete; CRUD matrix Work Orders row: Delete only for Admin / Service Manager / Senior Service Advisor) | Destructive, customer-facing capability re-scoped. Intended per spec, but each losing role must be regression-confirmed (and the SM gain smoke-tested) on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is each of: Service Advisor, Foreman, Technician, Office User, then Service Manager (one at a time) (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open Work Orders and open a ZZAUTOTEST work order in a deletable state (Estimate status, no payments) 3. Click the ⋮ (three-dot) menu on the work order detail page 4. Look for the "Delete Work Order" option | "Delete Work Order" is ABSENT for Service Advisor, Foreman, Technician and Office User; PRESENT for Service Manager (and Admin / Senior Service Advisor). | C26376 — Work orders Delete lets the user delete work orders https://shopview.testrail.io/index.php?/cases/view/26376 C26384 — Without Delete, no delete option is shown on a work order https://shopview.testrail.io/index.php?/cases/view/26384 | build/custom-roles-run/live-ui-2026-07-15/ (per-role WO-detail captures; estimate-state WO) | QA retest on release build | Full Dual Matrix ¦ Service Advisor ¦ WO Delete ¦ STAGING-LESS Full Dual Matrix ¦ Foreman ¦ WO Delete ¦ STAGING-LESS Full Dual Matrix ¦ Technician ¦ WO Delete ¦ STAGING-LESS Full Dual Matrix ¦ Office User ¦ WO Delete ¦ STAGING-LESS Full Dual Matrix ¦ Service Manager ¦ WO Delete ¦ STAGING-MORE

## P2 — Should check
ID | Category | Role(s) | Capability (plain language) | What we observed (prod vs staging) | Spec says (verbatim + citation) | Why it needs checking | Check steps (manual tester) | Expected result per spec | TestRail Case ID(s) + link(s) | Evidence path | Suggested owner | Source row(s) in the ground-truth workbook
QA-13 | Intended-loss-to-confirm | Technician | Work order "History" tab (WO-level audit log) removed for Technician | PROD: SHOWN. STAGING: hidden. | “Users can view the work order and work order line level audit logs” (spec §1a Work Orders Edit + 7/7 change log; Technician lacks Work Orders Create & Edit in the CRUD matrix) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Technician (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open any work order detail page 3. Look for the "History" tab (the work-order-level audit log) | The "History" tab is ABSENT for Technician. | C26488 — View History Logs ON: work order history and line history are visible (work orders only) https://shopview.testrail.io/index.php?/cases/view/26488 C26489 — View History Logs OFF: work order history and line history are hidden (work orders only) https://shopview.testrail.io/index.php?/cases/view/26489 C27870 — Work order lines Create & Edit lets the user mark a core OK/Not-OK and add line history https://shopview.testrail.io/index.php?/cases/view/27870 | build/custom-roles-run/live-ui-2026-07-15/ (per-role WO-detail captures) | QA retest on release build | Full Dual Matrix ¦ Technician ¦ WO-level History (History tab) ¦ STAGING-LESS
QA-14 | Intended-loss-to-confirm | Parts Technician | Work order "History" tab (WO-level audit log) removed for Parts Technician | PROD: SHOWN. STAGING: hidden. | “Users can view the work order and work order line level audit logs” (spec §1a Work Orders Edit + 7/7 change log; Parts Technician lacks Work Orders Create & Edit in the CRUD matrix) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Parts Technician (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open any work order detail page 3. Look for the "History" tab (the work-order-level audit log) | The "History" tab is ABSENT for Parts Technician. | C26488 — View History Logs ON: work order history and line history are visible (work orders only) https://shopview.testrail.io/index.php?/cases/view/26488 C26489 — View History Logs OFF: work order history and line history are hidden (work orders only) https://shopview.testrail.io/index.php?/cases/view/26489 C27870 — Work order lines Create & Edit lets the user mark a core OK/Not-OK and add line history https://shopview.testrail.io/index.php?/cases/view/27870 | build/custom-roles-run/live-ui-2026-07-15/ (per-role WO-detail captures) | QA retest on release build | Full Dual Matrix ¦ Parts Technician ¦ WO-level History (History tab) ¦ STAGING-LESS
QA-15 | Intended-loss-to-confirm | Office User | Work order "History" tab (WO-level audit log) removed for Office User | PROD: SHOWN. STAGING: hidden. | “Users can view the work order and work order line level audit logs” (spec §1a Work Orders Edit + 7/7 change log; Office User lacks Work Orders Create & Edit in the CRUD matrix) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Office User (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open any work order detail page 3. Look for the "History" tab (the work-order-level audit log) | The "History" tab is ABSENT for Office User. | C26488 — View History Logs ON: work order history and line history are visible (work orders only) https://shopview.testrail.io/index.php?/cases/view/26488 C26489 — View History Logs OFF: work order history and line history are hidden (work orders only) https://shopview.testrail.io/index.php?/cases/view/26489 C27870 — Work order lines Create & Edit lets the user mark a core OK/Not-OK and add line history https://shopview.testrail.io/index.php?/cases/view/27870 | build/custom-roles-run/live-ui-2026-07-15/ (per-role WO-detail captures) | QA retest on release build | Full Dual Matrix ¦ Office User ¦ WO-level History (History tab) ¦ STAGING-LESS
QA-16 | Intended-loss-to-confirm | Technician | Change the Customer on an existing work order removed for Technician | PROD: SHOWN. STAGING: hidden. | “edit customer details and change customer, change asset” (spec §1a Work Orders Edit; Technician lacks Work Orders Create & Edit in the CRUD matrix) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Technician (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open an existing ZZAUTOTEST work order 3. On the work order header, look for the edit (pencil) control next to the Customer 4. If present, change the customer to another ZZAUTOTEST customer and save (then change it back) | The edit (pencil) control next to the Customer is ABSENT for Technician. | NO EXISTING CASE — coverage gap | build/custom-roles-run/live-ui-2026-07-15/ (per-role WO-detail captures) | QA retest on release build | Full Dual Matrix ¦ Technician ¦ Change Customer on WO ¦ STAGING-LESS
QA-17 | Intended-loss-to-confirm | Technician | Change the Asset on an existing work order removed for Technician | PROD: SHOWN. STAGING: hidden. | “edit customer details and change customer, change asset” (spec §1a Work Orders Edit; Technician lacks Work Orders Create & Edit in the CRUD matrix) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Technician (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open an existing ZZAUTOTEST work order 3. On the work order header, look for the edit (pencil) control next to the Asset 4. If present, change the asset and save (then change it back) | The edit (pencil) control next to the Asset is ABSENT for Technician. | NO EXISTING CASE — coverage gap | build/custom-roles-run/live-ui-2026-07-15/ (per-role WO-detail captures) | QA retest on release build | Full Dual Matrix ¦ Technician ¦ Change Asset on WO ¦ STAGING-LESS
QA-18 | Intended-loss-to-confirm | Office User | Change the Customer on an existing work order removed for Office User | PROD: SHOWN. STAGING: hidden. | “edit customer details and change customer, change asset” (spec §1a Work Orders Edit; Office User lacks Work Orders Create & Edit in the CRUD matrix) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Office User (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open an existing ZZAUTOTEST work order 3. On the work order header, look for the edit (pencil) control next to the Customer 4. If present, change the customer to another ZZAUTOTEST customer and save (then change it back) | The edit (pencil) control next to the Customer is ABSENT for Office User. | NO EXISTING CASE — coverage gap | build/custom-roles-run/live-ui-2026-07-15/ (per-role WO-detail captures) | QA retest on release build | Full Dual Matrix ¦ Office User ¦ Change Customer on WO ¦ STAGING-LESS
QA-19 | Intended-loss-to-confirm | Office User | Change the Asset on an existing work order removed for Office User | PROD: SHOWN. STAGING: hidden. | “edit customer details and change customer, change asset” (spec §1a Work Orders Edit; Office User lacks Work Orders Create & Edit in the CRUD matrix) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Office User (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open an existing ZZAUTOTEST work order 3. On the work order header, look for the edit (pencil) control next to the Asset 4. If present, change the asset and save (then change it back) | The edit (pencil) control next to the Asset is ABSENT for Office User. | NO EXISTING CASE — coverage gap | build/custom-roles-run/live-ui-2026-07-15/ (per-role WO-detail captures) | QA retest on release build | Full Dual Matrix ¦ Office User ¦ Change Asset on WO ¦ STAGING-LESS
QA-20 | Intended-loss-to-confirm | Technician | Work order "Parts" tab / Order Parts area removed for Technician | PROD: SHOWN. STAGING: hidden. | “Enabling Order Parts requires See Financial Data setting” (spec §1a Order Parts sub-setting (woOrderParts); Order Parts = — for Technician in the WO Sub-Settings table) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Technician (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open any work order detail page and look for the "Parts" tab 3. Also open the Parts area (/parts/orders) and look for the "New PO" button | The work order "Parts" tab is ABSENT for Technician (no ordering surface). | C26381 — Order parts needs Work orders View and See Financial Data (not Create & Edit) https://shopview.testrail.io/index.php?/cases/view/26381 C27868 — Order parts controls the work order Parts tab (on shows it, off hides it) https://shopview.testrail.io/index.php?/cases/view/27868 C27869 — Turning on Order parts while See Financial Data is OFF asks you to also turn on See Financial Data https://shopview.testrail.io/index.php?/cases/view/27869 | build/custom-roles-run/live-ui-2026-07-15/ (per-role parts_orders.png) | QA retest on release build | Full Dual Matrix ¦ Technician ¦ Order Parts area (Parts tab) ¦ STAGING-LESS
QA-21 | Intended-loss-to-confirm | Office User | Work order "Parts" tab / Order Parts area removed for Office User | PROD: SHOWN. STAGING: hidden. | “Enabling Order Parts requires See Financial Data setting” (spec §1a Order Parts sub-setting (woOrderParts); Order Parts = — for Office User in the WO Sub-Settings table) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Office User (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open any work order detail page and look for the "Parts" tab 3. Also open the Parts area (/parts/orders) and look for the "New PO" button | The work order "Parts" tab is ABSENT for Office User (no ordering surface). | C26381 — Order parts needs Work orders View and See Financial Data (not Create & Edit) https://shopview.testrail.io/index.php?/cases/view/26381 C27868 — Order parts controls the work order Parts tab (on shows it, off hides it) https://shopview.testrail.io/index.php?/cases/view/27868 C27869 — Turning on Order parts while See Financial Data is OFF asks you to also turn on See Financial Data https://shopview.testrail.io/index.php?/cases/view/27869 | build/custom-roles-run/live-ui-2026-07-15/ (per-role parts_orders.png) | QA retest on release build | Full Dual Matrix ¦ Office User ¦ Order Parts area (Parts tab) ¦ STAGING-LESS
QA-22 | Intended-loss-to-confirm | Technician | "Send to Portal" button removed for Technician | PROD: SHOWN. STAGING: hidden. Explicit per spec: 28-Jun change log “Technicians lose “send to portal””. | “Send to Portal button: can be anyone who can approve a WOL” (Open Q6 answer; §4 View Mode; 6/10 change log; Technician has no WO Lines Create & Edit) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Technician (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open a work order that has a line eligible to send to the portal (an approved/estimate line) 3. Look for the "Send to Portal" button on the work order | The "Send to Portal" button is ABSENT for Technician (per the Open-Q6 reading). | C26465 — Tech view: the 'Send to Portal' button is hidden https://shopview.testrail.io/index.php?/cases/view/26465 C26466 — Full View: a user who can approve lines sees the 'Send to Portal' button https://shopview.testrail.io/index.php?/cases/view/26466 | build/custom-roles-run/live-ui-2026-07-15/ + build/custom-roles-run/live-ui-2026-07-16/ (per-role portal captures) | QA retest on release build | Full Dual Matrix ¦ Technician ¦ Send to Portal ¦ STAGING-LESS
QA-23 | Intended-loss-to-confirm | Parts Technician | "Send to Portal" button removed for Parts Technician | PROD: SHOWN. STAGING: hidden. Spec wording is contradictory for this role — see QA-09; the observed loss matches the Open-Q6 reading. | “Send to Portal button: can be anyone who can approve a WOL” (Open Q6 answer; §4 View Mode; 6/10 change log; Parts Technician has no WO Lines Create & Edit) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Parts Technician (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open a work order that has a line eligible to send to the portal (an approved/estimate line) 3. Look for the "Send to Portal" button on the work order | The "Send to Portal" button is ABSENT for Parts Technician (per the Open-Q6 reading). | C26465 — Tech view: the 'Send to Portal' button is hidden https://shopview.testrail.io/index.php?/cases/view/26465 C26466 — Full View: a user who can approve lines sees the 'Send to Portal' button https://shopview.testrail.io/index.php?/cases/view/26466 | build/custom-roles-run/live-ui-2026-07-15/ + build/custom-roles-run/live-ui-2026-07-16/ (per-role portal captures) | QA retest on release build | Full Dual Matrix ¦ Parts Technician ¦ Send to Portal ¦ STAGING-LESS
QA-24 | Intended-loss-to-confirm | Office User | "Send to Portal" button removed for Office User | PROD: SHOWN. STAGING: hidden. Spec wording is contradictory for this role — see QA-09; the observed loss matches the Open-Q6 reading. | “Send to Portal button: can be anyone who can approve a WOL” (Open Q6 answer; §4 View Mode; 6/10 change log; Office User has no WO Lines Create & Edit) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Office User (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open a work order that has a line eligible to send to the portal (an approved/estimate line) 3. Look for the "Send to Portal" button on the work order | The "Send to Portal" button is ABSENT for Office User (per the Open-Q6 reading). | C26465 — Tech view: the 'Send to Portal' button is hidden https://shopview.testrail.io/index.php?/cases/view/26465 C26466 — Full View: a user who can approve lines sees the 'Send to Portal' button https://shopview.testrail.io/index.php?/cases/view/26466 | build/custom-roles-run/live-ui-2026-07-15/ + build/custom-roles-run/live-ui-2026-07-16/ (per-role portal captures) | QA retest on release build | Full Dual Matrix ¦ Office User ¦ Send to Portal ¦ STAGING-LESS
QA-25 | Intended-loss-to-confirm | Technician | "Timesheets" navigation item removed for Technician | PROD: SHOWN. STAGING: hidden. | “View timesheets from work orders. If OFF, the Timesheets top level nav item is hidden” (spec §1j Timesheets View; Timesheets = — for Technician in the CRUD matrix; clock in/out + “My Timesheets” stay available) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Technician (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Look for "Timesheets" in the main navigation and open it 3. Separately confirm clock in / clock out and "My Timesheets" still work (they are always available) | "Timesheets" is ABSENT from the main navigation for Technician; clock in/out and "My Timesheets" still work. | C26430 — Timesheets View only: timesheet entries are read-only https://shopview.testrail.io/index.php?/cases/view/26430 C26433 — Timesheets View OFF with Reports ON: the timesheet activities report is still available https://shopview.testrail.io/index.php?/cases/view/26433 C27394 — A clock-capable role without Timesheets View can still see and open My Timesheets https://shopview.testrail.io/index.php?/cases/view/27394 | build/custom-roles-run/live-ui-2026-07-15/ (per-role nav captures) | QA retest on release build | Full Dual Matrix ¦ Technician ¦ Timesheets (tab) ¦ STAGING-LESS
QA-26 | Intended-loss-to-confirm | Parts Manager | "Timesheets" navigation item removed for Parts Manager | PROD: SHOWN. STAGING: hidden. | “View timesheets from work orders. If OFF, the Timesheets top level nav item is hidden” (spec §1j Timesheets View; Timesheets = — for Parts Manager in the CRUD matrix; clock in/out + “My Timesheets” stay available) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Parts Manager (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Look for "Timesheets" in the main navigation and open it 3. Separately confirm clock in / clock out and "My Timesheets" still work (they are always available) | "Timesheets" is ABSENT from the main navigation for Parts Manager; clock in/out and "My Timesheets" still work. | C26430 — Timesheets View only: timesheet entries are read-only https://shopview.testrail.io/index.php?/cases/view/26430 C26433 — Timesheets View OFF with Reports ON: the timesheet activities report is still available https://shopview.testrail.io/index.php?/cases/view/26433 C27394 — A clock-capable role without Timesheets View can still see and open My Timesheets https://shopview.testrail.io/index.php?/cases/view/27394 | build/custom-roles-run/live-ui-2026-07-15/ (per-role nav captures) | QA retest on release build | Full Dual Matrix ¦ Parts Manager ¦ Timesheets (tab) ¦ STAGING-LESS
QA-27 | Intended-loss-to-confirm | Technician | Work order "Finance" tab removed for Technician | PROD: SHOWN. STAGING: hidden. | “Controls visibility of all financial data across the application” (spec §5a; plus §1i Invoicing View — Technician has Invoicing = — AND See Financial Data = — in the matrix/toggles) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Technician (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open an Invoiced work order 3. Look for the "Finance" tab | The "Finance" tab is ABSENT for Technician. | C26420 — Invoicing & payments View shows the Finance tab and lets the user see invoices https://shopview.testrail.io/index.php?/cases/view/26420 C26426 — Invoicing & payments View OFF with See Financial Data ON: prices show but invoices are not reachable https://shopview.testrail.io/index.php?/cases/view/26426 | build/custom-roles-run/live-ui-2026-07-15/ (per-role WO-detail captures) | QA retest on release build | Full Dual Matrix ¦ Technician ¦ Invoicing/Finance view (Finance tab) ¦ STAGING-LESS
QA-28 | Intended-loss-to-confirm | Parts Technician | "New Line" (add a work order line) removed for Parts Technician | PROD: SHOWN. STAGING: hidden. | “Add new lines, edit line details, move parts between lines, authorize lines” (spec §1b WO Lines Edit; Parts Technician has WO Lines = V (no Create & Edit) in the CRUD matrix) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Parts Technician (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open a work order's lines page 3. Look for the "New Line" (add line) button | The "New Line" button is ABSENT for Parts Technician. | C26390 — Work order lines Create & Edit allows adding, editing, moving parts, authorizing and managing part requests https://shopview.testrail.io/index.php?/cases/view/26390 C26461 — Tech view: the user can add new work order lines but cannot edit existing ones https://shopview.testrail.io/index.php?/cases/view/26461 C27272 — The Build Lines entry point is shown for a role with Work order lines Create & Edit https://shopview.testrail.io/index.php?/cases/view/27272 | build/custom-roles-run/live-ui-2026-07-15/ (per-role line captures) | QA retest on release build | Full Dual Matrix ¦ Parts Technician ¦ Create/Edit WO Lines (New Line) ¦ STAGING-LESS
QA-29 | Intended-grant-to-confirm | Parts Manager | Review action ("Reviewed") newly granted to Parts Manager | PROD: hidden. STAGING: SHOWN. | “Without this setting, users will not see the Review option on work orders” (spec §1a WO sub-setting Review Work Orders (woReviewWorkOrders); Review WOs = ON for Parts Manager in the WO Sub-Settings table) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Parts Manager (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open a completed ZZAUTOTEST work order 3. Look for the Review action ("Reviewed") on the work order | The Review action IS available to Parts Manager. | C26379 — The Review work orders sub-toggle controls the Review action on work orders https://shopview.testrail.io/index.php?/cases/view/26379 | build/custom-roles-run/live-ui-2026-07-15/ (per-role WO-detail captures) | QA retest on release build | Full Dual Matrix ¦ Parts Manager ¦ Review Work Orders (Reviewed) ¦ STAGING-MORE
QA-30 | Intended-grant-to-confirm | Parts Manager | Change the Customer on an existing work order newly granted to Parts Manager | PROD: hidden. STAGING: SHOWN. | “edit customer details and change customer, change asset” (spec §1a Work Orders Edit; Parts Manager has Work Orders V/E in the CRUD matrix) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Parts Manager (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open an existing ZZAUTOTEST work order 3. On the work order header, look for the edit (pencil) control next to the Customer 4. If present, change the customer to another ZZAUTOTEST customer and save (then change it back) | The edit (pencil) control next to the Customer IS available to Parts Manager. | NO EXISTING CASE — coverage gap | build/custom-roles-run/live-ui-2026-07-15/ (per-role WO-detail captures) | QA retest on release build | Full Dual Matrix ¦ Parts Manager ¦ Change Customer on WO ¦ STAGING-MORE
QA-31 | Intended-grant-to-confirm | Parts Manager | Change the Asset on an existing work order newly granted to Parts Manager | PROD: hidden. STAGING: SHOWN. | “edit customer details and change customer, change asset” (spec §1a Work Orders Edit; Parts Manager has Work Orders V/E in the CRUD matrix) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Parts Manager (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open an existing ZZAUTOTEST work order 3. On the work order header, look for the edit (pencil) control next to the Asset 4. If present, change the asset and save (then change it back) | The edit (pencil) control next to the Asset IS available to Parts Manager. | NO EXISTING CASE — coverage gap | build/custom-roles-run/live-ui-2026-07-15/ (per-role WO-detail captures) | QA retest on release build | Full Dual Matrix ¦ Parts Manager ¦ Change Asset on WO ¦ STAGING-MORE
QA-32 | Intended-grant-to-confirm | Parts Manager | "Approve" button on a "Needs Approval" line newly granted to Parts Manager | PROD: hidden (line renders, no Approve/Decline). STAGING: SHOWN. | “authorize lines” (spec §1b WO Lines Edit (‘authorize lines’); Parts Manager has WO Lines V/E + Full View) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Parts Manager (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open a work order that has a line whose Status = "Needs Approval" (seed one via a part request that requires authorization if none exists; delete it after) 3. Look at the line's Action column for the green "Approve" and red "Decline" buttons | The green "Approve" and red "Decline" buttons ARE shown to Parts Manager on a Needs-Approval line. | C26390 — Work order lines Create & Edit allows adding, editing, moving parts, authorizing and managing part requests https://shopview.testrail.io/index.php?/cases/view/26390 C26458 — Tech view: the user cannot approve work order lines https://shopview.testrail.io/index.php?/cases/view/26458 C26466 — Full View: a user who can approve lines sees the 'Send to Portal' button https://shopview.testrail.io/index.php?/cases/view/26466 | build/custom-roles-run/live-ui-2026-07-16/staging/approve-decline-REALHOLDER-ALL.json + production/approve-decline-ALL.json | QA retest on release build | Full Dual Matrix ¦ Parts Manager ¦ Approve line ¦ STAGING-MORE
QA-33 | Intended-grant-to-confirm | Parts Manager | "Decline" button on a "Needs Approval" line newly granted to Parts Manager | PROD: hidden (line renders, no Approve/Decline). STAGING: SHOWN. | “authorize lines” (spec §1b WO Lines Edit (‘authorize lines’); Parts Manager has WO Lines V/E + Full View) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Parts Manager (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open a work order that has a line whose Status = "Needs Approval" (seed one via a part request that requires authorization if none exists; delete it after) 3. Look at the line's Action column for the green "Approve" and red "Decline" buttons | The green "Approve" and red "Decline" buttons ARE shown to Parts Manager on a Needs-Approval line. | NO EXISTING CASE — coverage gap | build/custom-roles-run/live-ui-2026-07-16/staging/approve-decline-REALHOLDER-ALL.json + production/approve-decline-ALL.json | QA retest on release build | Full Dual Matrix ¦ Parts Manager ¦ Decline line ¦ STAGING-MORE
QA-34 | Intended-grant-to-confirm | Parts Manager | "New" work order button (create WO) newly granted to Parts Manager | PROD: hidden (no New button). STAGING: SHOWN (dialog opens). | “Create new work orders” (spec §1a Work Orders Edit; Parts Manager has Work Orders V/E in the CRUD matrix) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Parts Manager (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open the Work Orders list and look for the "New" button 3. If present, click "New" and in the New Work Order dialog look for the "Add" button next to Customer and the "Add" button next to Asset (the Asset Add enables after a customer is chosen) | The "New" button IS shown and the New Work Order dialog opens for Parts Manager. | C26375 — Work orders Create & Edit lets the user create and change work orders https://shopview.testrail.io/index.php?/cases/view/26375 C26383 — Without Create & Edit, create/edit options are hidden on work orders https://shopview.testrail.io/index.php?/cases/view/26383 | build/custom-roles-run/live-ui-2026-07-15/production/Parts_Manager/new_wo_nobutton.png + staging/Parts_Manager/new_wo_dialog.png | QA retest on release build | New-WO Create Dual LIVE ¦ Parts Manager ¦ Create Work Order ("New" button on Work Orders list) ¦ STAGING-MORE
QA-35 | Intended-grant-to-confirm | Parts Manager | "Add" Customer inside the New Work Order dialog newly granted to Parts Manager | PROD: hidden (dialog unreachable). STAGING: SHOWN. | “Create/Edit customer also affect the ability to create a customer in the New WO flow” (6/1 change log; §1d Customer Management Edit; Parts Manager holds Customers V/E/D + Work Orders V/E) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Parts Manager (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open the Work Orders list and look for the "New" button 3. If present, click "New" and in the New Work Order dialog look for the "Add" button next to Customer and the "Add" button next to Asset (the Asset Add enables after a customer is chosen) | The "Add" button next to Customer IS shown in the New Work Order dialog for Parts Manager. | C26387 — The 'Add Customer' button in the New Work Order flow when Customers Create & Edit is OFF https://shopview.testrail.io/index.php?/cases/view/26387 | build/custom-roles-run/live-ui-2026-07-15/staging/Parts_Manager/new_wo_dialog.png | QA retest on release build | New-WO Create Dual LIVE ¦ Parts Manager ¦ Create Customer from New-WO ("Add" next to Customer) ¦ STAGING-MORE
QA-36 | Intended-grant-to-confirm | Parts Manager | "Add" Asset inside the New Work Order dialog newly granted to Parts Manager | PROD: hidden (dialog unreachable). STAGING: SHOWN (enables after a customer is chosen). | “Create/Edit customer also affect the ability to create a customer in the New WO flow” (6/1 change log; §1d Customer Management Edit (manage vehicles); Parts Manager holds Customers V/E/D + Work Orders V/E) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Parts Manager (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open the Work Orders list and look for the "New" button 3. If present, click "New" and in the New Work Order dialog look for the "Add" button next to Customer and the "Add" button next to Asset (the Asset Add enables after a customer is chosen) | The "Add" button next to Asset IS shown (enabled once a customer is chosen) for Parts Manager. | C26388 — The 'Add Asset' button is hidden in the New Work Order flow when Customers Create & Edit is OFF https://shopview.testrail.io/index.php?/cases/view/26388 | build/custom-roles-run/live-ui-2026-07-15/staging/Parts_Manager/new_wo_dialog.png | QA retest on release build | New-WO Create Dual LIVE ¦ Parts Manager ¦ Create Asset control from New-WO ("Add" next to Asset) ¦ STAGING-MORE
QA-37 | Intended-grant-to-confirm | Sales Representative | See Financial Data (rates / margins / money columns) newly granted to Sales Representative | PROD: hidden. STAGING: SHOWN. | “Controls visibility of all financial data across the application” (spec §5a; See Financial = ON for Sales Representative in the Cross-Cutting table) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Sales Representative (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open a work order with labor and parts lines 3. Look for money data: labor rate, part prices, total/labor/parts columns, margins | Money data (rates, prices, totals, margins) IS visible to Sales Representative. | C26464 — Money columns are controlled by See Financial Data, not by View mode https://shopview.testrail.io/index.php?/cases/view/26464 C26470 — With See Financial Data OFF, Part sales and Invoicing & payments stay inaccessible even with View, Create & Edit and Delete on https://shopview.testrail.io/index.php?/cases/view/26470 | build/custom-roles-run/live-ui-2026-07-15/ (per-role captures) | QA retest on release build | Full Dual Matrix ¦ Sales Representative (+Reporting) ¦ See Financial Data (Rate/Margin) ¦ STAGING-MORE
QA-38 | Intended-grant-to-confirm | Sales Representative | Work order "Notes" tab newly reachable for Sales Representative | PROD: hidden. STAGING: SHOWN. | “Users can also see the Notes tab, create notes, and edit any note” (spec §1a Work Orders View; Sales Representative has Work Orders = V in the CRUD matrix) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Sales Representative (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open Work Orders from the main navigation (if the nav item is hidden, paste a work order detail URL directly into the browser) 3. If a work order opens, open its "Notes" tab 4. Try to add a note and to edit an existing note | The "Notes" tab IS reachable (create + edit any note) for Sales Representative. | NO EXISTING CASE — coverage gap | build/custom-roles-run/live-ui-2026-07-15/ (per-role WO-detail captures) | QA retest on release build | Full Dual Matrix ¦ Sales Representative (+Reporting) ¦ WO Notes (Notes tab) ¦ STAGING-MORE
QA-39 | Intended-grant-to-confirm | Time Clock User | Work order "Notes" tab newly reachable for Time Clock User | PROD: hidden. STAGING: SHOWN. | “Users can also see the Notes tab, create notes, and edit any note” (spec §1a Work Orders View; Time Clock User has Work Orders = V in the CRUD matrix) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Time Clock User (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open Work Orders from the main navigation (if the nav item is hidden, paste a work order detail URL directly into the browser) 3. If a work order opens, open its "Notes" tab 4. Try to add a note and to edit an existing note | The "Notes" tab IS reachable (create + edit any note) for Time Clock User. | NO EXISTING CASE — coverage gap | build/custom-roles-run/live-ui-2026-07-15/ (per-role WO-detail captures) | QA retest on release build | Full Dual Matrix ¦ Time Clock User ¦ WO Notes (Notes tab) ¦ STAGING-MORE
QA-40 | Intended-grant-to-confirm | Time Clock User | "Timesheets" navigation item newly granted to Time Clock User | PROD: hidden. STAGING: SHOWN. | “View timesheets from work orders. If OFF, the Timesheets top level nav item is hidden” (spec §1j Timesheets View; Timesheets = V for Time Clock User in the CRUD matrix) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Time Clock User (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Look for "Timesheets" in the main navigation and open it 3. Separately confirm clock in / clock out and "My Timesheets" still work (they are always available) | "Timesheets" IS shown in the main navigation for Time Clock User. | C26430 — Timesheets View only: timesheet entries are read-only https://shopview.testrail.io/index.php?/cases/view/26430 C27394 — A clock-capable role without Timesheets View can still see and open My Timesheets https://shopview.testrail.io/index.php?/cases/view/27394 C26432 — Clock in / clock out is always available, whatever the Timesheets permission https://shopview.testrail.io/index.php?/cases/view/26432 | build/custom-roles-run/live-ui-2026-07-15/ (per-role nav captures) | QA retest on release build | Full Dual Matrix ¦ Time Clock User ¦ Timesheets (tab) ¦ STAGING-MORE
QA-41 | Intended-grant-to-confirm | Service Manager | A/R + A/P Aging reports newly visible to Service Manager | PROD: hidden. STAGING: SHOWN (tiles render). | “AR/AP aging reports are part of Reports — a user with Reports ON sees all reports, including AR/AP aging, regardless of Manage AP/AR” (spec §2a Reports note; Reports = ON for Service Manager in the Toggles table) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Service Manager (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open "Reports" from the main navigation 3. Look for the A/R Aging and A/P Aging report tiles in the reports list | The A/R Aging and A/P Aging report tiles ARE listed for Service Manager. | C26478 — With Reports ON, all 6 AP/AR aging reports are listed (whether or not AP/AR is on) https://shopview.testrail.io/index.php?/cases/view/26478 C26482 — With AP/AR OFF but Reports ON, all 6 AP/AR aging reports are still listed https://shopview.testrail.io/index.php?/cases/view/26482 | build/custom-roles-run/live-ui-2026-07-16/ (Pass-11 AP/AR captures) | QA retest on release build | Pass-11 LIVE (2026-07-16) ¦ Service Manager ¦ See AP/AR ¦ STAGING-MORE
QA-42 | Intended-grant-to-confirm | Parts Manager | A/R + A/P Aging reports newly visible to Parts Manager | PROD: hidden. STAGING: SHOWN (tiles render). | “AR/AP aging reports are part of Reports — a user with Reports ON sees all reports, including AR/AP aging, regardless of Manage AP/AR” (spec §2a Reports note; Reports = ON for Parts Manager in the Toggles table) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Parts Manager (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open "Reports" from the main navigation 3. Look for the A/R Aging and A/P Aging report tiles in the reports list | The A/R Aging and A/P Aging report tiles ARE listed for Parts Manager. | C26478 — With Reports ON, all 6 AP/AR aging reports are listed (whether or not AP/AR is on) https://shopview.testrail.io/index.php?/cases/view/26478 C26482 — With AP/AR OFF but Reports ON, all 6 AP/AR aging reports are still listed https://shopview.testrail.io/index.php?/cases/view/26482 | build/custom-roles-run/live-ui-2026-07-16/ (Pass-11 AP/AR captures) | QA retest on release build | Pass-11 LIVE (2026-07-16) ¦ Parts Manager ¦ See AP/AR ¦ STAGING-MORE
QA-43 | Intended-grant-to-confirm | Sales Representative | A/R + A/P Aging reports newly visible to Sales Representative | PROD: hidden. STAGING: SHOWN (tiles render). | “AR/AP aging reports are part of Reports — a user with Reports ON sees all reports, including AR/AP aging, regardless of Manage AP/AR” (spec §2a Reports note; Reports = ON for Sales Representative in the Toggles table) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Sales Representative (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open "Reports" from the main navigation 3. Look for the A/R Aging and A/P Aging report tiles in the reports list | The A/R Aging and A/P Aging report tiles ARE listed for Sales Representative. | C26478 — With Reports ON, all 6 AP/AR aging reports are listed (whether or not AP/AR is on) https://shopview.testrail.io/index.php?/cases/view/26478 C26482 — With AP/AR OFF but Reports ON, all 6 AP/AR aging reports are still listed https://shopview.testrail.io/index.php?/cases/view/26482 | build/custom-roles-run/live-ui-2026-07-16/ (Pass-11 AP/AR captures) | QA retest on release build | Pass-11 LIVE (2026-07-16) ¦ Sales Representative ¦ See AP/AR ¦ STAGING-MORE
QA-44 | Intended-grant-to-confirm | Sales Representative | Part "Return" (picked-part menu) newly reachable for Sales Representative | PROD: hidden (WO detail not accessible). STAGING: SHOWN. | “Returning a part from a WOL does not require a permission” (spec §1a + 6/29 change log; Sales Representative has Work Orders = V so the Return point is reachable) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Sales Representative (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open a work order that has a picked inventory part on a line (seed a ZZAUTOTEST work order and pick a part if needed) 3. On the picked part, open the ⋮ (three-dot) part menu 4. Look for the "Return" option | The "Return" option IS shown in the picked-part menu for Sales Representative. | NO EXISTING CASE — coverage gap | build/custom-roles-run/live-ui-2026-07-16/ (Pass-11 Part Return captures) | QA retest on release build | Pass-11 LIVE (2026-07-16) ¦ Sales Representative ¦ Part Return ¦ STAGING-MORE
QA-45 | Intended-grant-to-confirm | Time Clock User | Part "Return" (picked-part menu) newly reachable for Time Clock User | PROD: hidden (WO detail not accessible). STAGING: SHOWN. | “Returning a part from a WOL does not require a permission” (spec §1a + 6/29 change log; Time Clock User has Work Orders = V so the Return point is reachable) | Intended per spec — regression-confirm on the release build. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Time Clock User (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open a work order that has a picked inventory part on a line (seed a ZZAUTOTEST work order and pick a part if needed) 3. On the picked part, open the ⋮ (three-dot) part menu 4. Look for the "Return" option | The "Return" option IS shown in the picked-part menu for Time Clock User. | NO EXISTING CASE — coverage gap | build/custom-roles-run/live-ui-2026-07-16/ (Pass-11 Part Return captures) | QA retest on release build | Pass-11 LIVE (2026-07-16) ¦ Time Clock User ¦ Part Return ¦ STAGING-MORE

## P3 — Monitor - no action
ID | Category | Role(s) | Capability (plain language) | What we observed (prod vs staging) | Spec says (verbatim + citation) | Why it needs checking | Check steps (manual tester) | Expected result per spec | TestRail Case ID(s) + link(s) | Evidence path | Suggested owner | Source row(s) in the ground-truth workbook
QA-46 | Env-config | Admin, Service Manager, Senior Service Advisor, Service Advisor, Parts Manager | "Send to Terminal" appears on staging but not prod for the 5 roles that DO meet the spec role-gate — org-device config, not a role delta | PROD: hidden for every role (the prod test org has NO card-terminal device and no UI path to add one; all terminal APIs 404). STAGING: SHOWN (the staging org has a terminal). | “To send to terminal use must have this and “Customer Portal: ON” enabled” (spec §1i Invoicing Edit; these 5 roles hold Invoicing C&E + Customer Portal ON, so the role-gate is met) | Fully-characterized ORG-DEVICE config gate (Pass-12), not a role/migration difference. Monitor only: confirm the release org's terminal-device configuration matches what customers should have. | 1. Confirm with the release/ops team whether the target org has a card terminal device registered with the payment processor 2. If a terminal exists: as any of the 5 roles, open an Invoiced WO > "Finance" > "New Payment" and confirm "Send to Terminal" appears 3. If no terminal exists: confirm the button is absent for every role (expected) | Button presence follows the org's terminal device: shown for these 5 roles when a terminal is registered, absent for everyone when not. | C29434 — Send to Terminal needs Invoicing & payments Create & Edit AND Customer portal ON https://shopview.testrail.io/index.php?/cases/view/29434 C26427 — The Send to Terminal action needs Invoicing & payments Create & Edit https://shopview.testrail.io/index.php?/cases/view/26427 | build/custom-roles-run/live-ui-2026-07-16/ (Pass-12: prod Settings/Payment-Methods nav screenshots; terminal APIs 404 captures) | QA monitor / ops config check | Send to Terminal LIVE ¦ Admin ¦ Send to Terminal ¦ STAGING-MORE Send to Terminal LIVE ¦ Service Manager ¦ Send to Terminal ¦ STAGING-MORE Send to Terminal LIVE ¦ Senior Service Advisor ¦ Send to Terminal ¦ STAGING-MORE Send to Terminal LIVE ¦ Service Advisor ¦ Send to Terminal ¦ STAGING-MORE Send to Terminal LIVE ¦ Parts Manager ¦ Send to Terminal ¦ STAGING-MORE
QA-47 | Spec-contradiction | Service Manager, Parts Manager, Parts Technician, Foreman, Office User (observed holders) | "Issue Credit" button (Finance tab) — the spec is SILENT on who may issue a credit | STAGING: "Issue Credit" shows alongside "New Payment" for every role that reaches the Finance tab. PROD: Finance tab hidden for these legacy roles. | The spec defines NO issuance gate for credits anywhere — §5b covers only the visibility of the Credits TAB on Customer/Vendor pages. (Spec-silent register: build/custom-roles-run/spec-conformance/spec-truth-table.md §5.) | Money-facing button with no spec gate. No action required for release, but the PO should define a gate; QA should monitor that it at least tracks Finance-tab access. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Service Manager (spot-check one or two of the listed roles) (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open an Invoiced ZZAUTOTEST work order > "Finance" tab 3. Confirm "Issue Credit" appears next to "New Payment" and note which roles can see it | No spec expectation exists (spec silent). Record observed behavior; ask the PO to define the intended gate. | NO EXISTING CASE — coverage gap | build/custom-roles-run/live-ui-2026-07-16/ (Pass-11 Finance captures) | PO decision (define a gate); QA monitor | Pass-11 LIVE (2026-07-16) ¦ Service Manager ¦ Finance ¦ STAGING-MORE
QA-48 | Intended-grant-to-confirm | All roles except Technician (see QA-08) and Parts Manager (see QA-33) | "Decline" button parity — Decline is gated together with Approve everywhere it was observed | Both envs: Decline shows exactly where Approve shows, for every role (Admin/SM/SSA/SA/Foreman shown; PT/Office/Sales Rep/Time Clock hidden). Only deltas: Parts Manager (QA-33) and the Technician ambiguity (QA-08). | “authorize lines” (spec §1b WO Lines Edit — ‘authorize lines’ covers declining a pending line) | Smoke-only if time permits: parity already observed live in both envs on 2026-07-16. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Admin (or any Approve-holding role) (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open a work order with a "Needs Approval" line 3. Confirm the green "Approve" and red "Decline" buttons appear together | "Decline" appears wherever "Approve" appears (same gate: WO Lines Create & Edit). | NO EXISTING CASE — coverage gap | build/custom-roles-run/live-ui-2026-07-16/staging/approve-decline-REALHOLDER-ALL.json + production/approve-decline-ALL.json | QA smoke (time permitting) | Approve-Decline LIVE ¦ Admin ¦ Approve/Decline line ¦ MATCH
QA-49 | Intended-grant-to-confirm | All roles with Work Orders View | Part "Return" parity (MATCH rows) — ungated return works the same in both envs for WO-View roles | Both envs SHOWN for Admin, Service Manager, Senior Service Advisor, Service Advisor, Foreman, Technician, Parts Manager, Parts Technician (MATCH). | “Returning a part from a WOL does not require a permission” (spec §1a; 6/29 change log) | Smoke-only if time permits: parity already observed live (Pass-11). | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Technician (representative WO-View role) (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open a work order that has a picked inventory part on a line (seed a ZZAUTOTEST work order and pick a part if needed) 3. On the picked part, open the ⋮ (three-dot) part menu 4. Look for the "Return" option | "Return" appears in the picked-part menu for any role that can open the work order. | NO EXISTING CASE — coverage gap | build/custom-roles-run/live-ui-2026-07-16/ (Pass-11 Part Return captures) | QA smoke (time permitting) | Pass-11 LIVE (2026-07-16) ¦ Technician ¦ Part Return ¦ MATCH
QA-50 | Intended-grant-to-confirm | Admin, Service Manager, Senior Service Advisor, Service Advisor, Foreman, Parts Manager, Parts Technician | Parts module parity (MATCH rows): "New PO" + "Receive" on /parts/orders | Both envs SHOWN for the 7 granted roles; both envs hidden for Office User, Sales Representative, Technician, Time Clock User (all MATCH). | “Enabling Order Parts requires See Financial Data setting” (spec §1a Order Parts sub-setting + §1g Vendor & Order Management Edit: “create and manage purchase orders, manage deliveries”) | Smoke-only if time permits: full dual grid already observed live 2026-07-15. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Parts Manager (representative granted role) (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open the Parts area (/parts/orders) 3. Confirm the "New PO" button and the per-PO "Receive" button appear | "New PO" and "Receive" appear for the granted roles only. | C27876 — A Vendor and order management View-only role can open the Purchase Orders list and a purchase order https://shopview.testrail.io/index.php?/cases/view/27876 C26417 — Vendor and order management Create & Edit lets the user manage vendors, purchase orders, receiving and returns https://shopview.testrail.io/index.php?/cases/view/26417 C26381 — Order parts needs Work orders View and See Financial Data (not Create & Edit) https://shopview.testrail.io/index.php?/cases/view/26381 | build/custom-roles-run/live-ui-2026-07-15/ (per-role parts_orders.png, both envs) | QA smoke (time permitting) | Parts-Module Dual LIVE ¦ Admin ¦ Order Parts (create Purchase Order — "New PO" on /parts/orders) ¦ MATCH
QA-51 | Intended-grant-to-confirm | Admin, Service Manager, Senior Service Advisor, Service Advisor, Foreman | New Work Order dialog parity (MATCH rows): "New" button + "Add" Customer / "Add" Asset | Both envs SHOWN for the granted roles; both envs hidden for Office User, Parts Technician, Sales Representative, Technician, Time Clock User (all MATCH). Only delta = Parts Manager (QA-34/35/36). | “Create new work orders” (spec §1a Work Orders Edit + 6/1 change log (Add Customer in the New-WO flow)) | Smoke-only if time permits: full dual grid already observed live 2026-07-15. | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Service Advisor (representative granted role) (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open the Work Orders list and look for the "New" button 3. If present, click "New" and in the New Work Order dialog look for the "Add" button next to Customer and the "Add" button next to Asset (the Asset Add enables after a customer is chosen) | "New" opens the New Work Order dialog with "Add" next to Customer and Asset for the granted roles only. | C26375 — Work orders Create & Edit lets the user create and change work orders https://shopview.testrail.io/index.php?/cases/view/26375 C26387 — The 'Add Customer' button in the New Work Order flow when Customers Create & Edit is OFF https://shopview.testrail.io/index.php?/cases/view/26387 C26388 — The 'Add Asset' button is hidden in the New Work Order flow when Customers Create & Edit is OFF https://shopview.testrail.io/index.php?/cases/view/26388 | build/custom-roles-run/live-ui-2026-07-15/ (per-role new_wo_dialog.png / new_wo_nobutton.png, both envs) | QA smoke (time permitting) | New-WO Create Dual LIVE ¦ Admin ¦ Create Work Order ("New" button on Work Orders list) ¦ MATCH
QA-52 | Intended-grant-to-confirm | Admin, Service Manager, Senior Service Advisor, Service Advisor, Foreman | "Approve"/"Decline" line parity (MATCH rows) for the 5 approving roles | Both envs SHOWN for Admin, Service Manager, Senior Service Advisor, Service Advisor, Foreman; both envs hidden for Technician, Parts Technician, Office User, Sales Representative, Time Clock User. Only delta = Parts Manager (QA-32/33). | “authorize lines” (spec §1b WO Lines Edit + §4 Tech View approve-block) | Smoke-only if time permits: all 11 staging + 13 prod roles observed live 2026-07-16 (Pass-12). | 1. On the staging build (app.staging.shopview.com), sign in as a user whose role is Foreman (representative approving role) (create a fresh ZZAUTOTEST staff member with that role and log in as them; do not reuse a drifted account) 2. Open a work order that has a line whose Status = "Needs Approval" (seed one via a part request that requires authorization if none exists; delete it after) 3. Look at the line's Action column for the green "Approve" and red "Decline" buttons | Green "Approve" + red "Decline" appear on a Needs-Approval line for the 5 approving roles only. | C26390 — Work order lines Create & Edit allows adding, editing, moving parts, authorizing and managing part requests https://shopview.testrail.io/index.php?/cases/view/26390 C26458 — Tech view: the user cannot approve work order lines https://shopview.testrail.io/index.php?/cases/view/26458 | build/custom-roles-run/live-ui-2026-07-16/staging + /production (approve-decline JSON + PNG captures) | QA smoke (time permitting) | Pass-12 LIVE (2026-07-16) ¦ Foreman ¦ Approve/Decline line ¦ MATCH

## Coverage Gaps
Gap ID | Type | Role(s) | Capability / surface | What is missing and why it matters | Suggested action for QA | Related checklist item(s) | Evidence path
GAP-01 | No existing TestRail case | All roles | Red "Decline" button on a "Needs Approval" line (role-based) | No case in the Custom Roles suite mentions Decline. It is a discrete money/authorization action gated with Approve (§1b ‘authorize lines’), and it carries an open Technician ambiguity (QA-08) and a Parts Manager migration delta (QA-33). | Author per-role cases: Decline shows/works for Admin/SM/SSA/SA/Foreman/Parts Manager; hidden for the rest; Technician pending PO ruling. | QA-08, QA-33, QA-48 | build/custom-roles-run/live-ui-2026-07-16/staging/approve-decline-REALHOLDER-ALL.json
GAP-02 | No existing TestRail case | All roles with Work Orders View | Work order "Notes" tab (see tab, create note, edit any note) | Only a customer-notes case exists (C27873). No case covers the WO Notes tab riding on Work Orders View, which is also the surface of the Office User deviation (QA-05). | Author cases: WO Notes tab visible + create/edit-any-note for WO-View roles; unreachable for Office User (per the 7/14 spec). | QA-05, QA-38, QA-39 | build/custom-roles-run/live-ui-2026-07-15/ (per-role WO-detail captures)
GAP-03 | No existing TestRail case | All roles with Work Orders View | Part "Return" from a work order (ungated picked-part menu action) | Existing return cases (C26419, C27871, C26417) cover inventory/vendor returns, a different surface. The ungated return-from-WO (29-Jun rule) has no case, and it carries the Office User deviation (QA-06). | Author cases: "Return" appears in the picked-part menu for every WO-View role; unreachable for Office User (per the 7/14 spec). | QA-06, QA-44, QA-45, QA-49 | build/custom-roles-run/live-ui-2026-07-16/ (Pass-11 Part Return captures)
GAP-04 | No existing TestRail case | Roles with / without Work Orders Create & Edit | Change the Customer on an existing work order | C26375 covers status/lead-tech/service-advisor changes only; no case exercises changing the Customer on an existing WO, which is a live migration delta (lost by Technician/Office User, gained by Parts Manager). | Author cases: pencil control next to Customer present for WO-C&E roles (incl. Parts Manager), absent for Technician/Office User. | QA-16, QA-18, QA-30 | build/custom-roles-run/live-ui-2026-07-15/ (per-role WO-detail captures)
GAP-05 | No existing TestRail case | Roles with / without Work Orders Create & Edit | Change the Asset on an existing work order | Same gap as GAP-04 for the Asset control (lost by Technician/Office User, gained by Parts Manager). | Author cases: pencil control next to Asset present for WO-C&E roles (incl. Parts Manager), absent for Technician/Office User. | QA-17, QA-19, QA-31 | build/custom-roles-run/live-ui-2026-07-15/ (per-role WO-detail captures)
GAP-06 | No existing TestRail case | Roles reaching the Finance tab | "Issue Credit" button on the work order Finance tab | No case covers issuing a credit, and the spec is silent on its gate (QA-47). Money-facing surface with zero coverage. | Ask the PO to define the gate, then author per-role cases for "Issue Credit". | QA-47 | build/custom-roles-run/live-ui-2026-07-16/ (Pass-11 Finance captures)
GAP-07 | No existing TestRail case | Admin, Service Manager, Senior Service Advisor | "Reverse" invoice via the Work Orders → Delete gate (positive case) | Only the negative case exists (C26422: Invoicing Delete does NOT reverse invoices). No positive case asserts that WO Delete holders see and can use "Reverse" on the Finance tab — and the SM answer is PO-pending (QA-07). | After the QA-07 PO ruling, author positive cases: "Reverse" present for Admin/SSA (and SM per ruling), absent for all non-WO-Delete roles. | QA-07, QA-10 | build/custom-roles-run/live-ui-2026-07-16/ (Pass-11 Finance captures)
GAP-08 | Re-observe on release build | Foreman, Office User, Parts Technician | Staging "Send to Terminal" for these 3 roles — peer-observed method cell | The workbook READ ME labels these staging cells as method-derived: "New Payment reachable (Take Payment observed SHOWN); org-device gate satisfied" — the button itself was pixel-observed for the invoicing-role set, and derived from the reachable New Payment dialog for these 3. Re-observe directly on the release build. | On the release build, as each of the 3 roles, open Finance > "New Payment" on an invoiced WO and pixel-confirm the "Send to Terminal" button state. | QA-01, QA-02, QA-03 | build/custom-roles-run/live-ui-2026-07-16/ (Pass-12 SendToTerminal_dialog.png set)
GAP-09 | Re-observe on release build | Parts Technician | Staging "Approve"/"Decline" for Parts Technician — taken from the 2026-07-15 capture | The Approve-Decline LIVE tab sources the staging Parts Technician verdict from the 2026-07-15 role-swap capture (live-ui-2026-07-15/staging/Parts_Technician/refwo-caps.json) rather than the 2026-07-16 real-holder pass. Re-observe on the release build. | On the release build, as Parts Technician, open a WO with a "Needs Approval" line and confirm no "Approve"/"Decline" buttons appear. | QA-52 | build/custom-roles-run/live-ui-2026-07-15/staging/Parts_Technician/refwo-caps.json