## Change list (4)
Simple Flow spec-recheck — cases that need a change or a decision (4 of 184).
LIVE-BUILD CHECK 2026-07-23: 0 of 4 rows re-verified live on staging (green); 0 characterised-blocked on an env defect (orange, see column D); the rest flagged '⏳ LIVE CHECK PENDING'.
The other 180 cases need no change (151 Verified, 21 Blocked-on-environment, 4 to re-verify live, 3 retired, plus 4 Create-Purchase-Orders cases deleted from TestRail and ignored per your ruling). Nothing pushed to TestRail yet. Orange rows = waiting on a ticket that is NOT yet done.
Case ID | TestRail link | Area | What needs to change | Driving ticket | Ticket status | Action
C29373 | https://shopview.testrail.io/index.php?/cases/view/29373 | Accept Delivery | ⏳ LIVE CHECK PENDING (2026-07-23 run: not yet observed) — prior finding: On the Accept Delivery screen the group of parts with no vendor yet appears at the TOP of the list; the product owner wanted it at the BOTTOM. Reviewed and accepted as a look-only difference (no effect on how it works) — confirm we keep it as-is and change nothing. | SV-7707 | DONE | DECISION
C29375 | https://shopview.testrail.io/index.php?/cases/view/29375 | Accept Delivery | ⏳ LIVE CHECK PENDING (2026-07-23 run: not yet observed) — prior finding: Same Accept-Delivery point as C29373 — the position of the no-vendor group and the multi-vendor indicator. Accepted as look-only — confirm keep as-is, no case change. | SV-7707 | DONE | DECISION
C29396 | https://shopview.testrail.io/index.php?/cases/view/29396 | Review before completion | ⏳ LIVE CHECK PENDING (2026-07-23 run: not yet observed) — prior finding: When 'require review before completion' is on, signing off finishes the work order straight away with no separate 'Reviewed' holding step. Whether invoicing should be blocked until a review happens is a product decision (Milos). Don't finalise this case until that review ticket ships. | SV-7870 | NOT DONE (Blocked) | DECISION
C29404 | https://shopview.testrail.io/index.php?/cases/view/29404 | Completion screen — Close/Cancel | ⏳ LIVE CHECK PENDING (2026-07-23 run: not yet observed) — prior finding: The 'Close' vs 'Cancel' confirmation pop-up on the completion screens isn't finalised in the design yet, so the exact behaviour isn't defined. Needs Milos to confirm what Close and Cancel should do before the case can state a result. | SV-7710 | NOT DONE (Blocked) | DECISION

## Waiting on open tickets
Cases whose change depends on a ticket that is NOT yet done
These should NOT be finalised until the ticket ships; keep the case tracking the target and re-verify after the fix.
Case ID | TestRail link | Area | What needs to change | Driving ticket | Ticket status | Action
C29396 | https://shopview.testrail.io/index.php?/cases/view/29396 | Review before completion | ⏳ LIVE CHECK PENDING (2026-07-23 run: not yet observed) — prior finding: When 'require review before completion' is on, signing off finishes the work order straight away with no separate 'Reviewed' holding step. Whether invoicing should be blocked until a review happens is a product decision (Milos). Don't finalise this case until that review ticket ships. | SV-7870 | NOT DONE (Blocked) | DECISION
C29404 | https://shopview.testrail.io/index.php?/cases/view/29404 | Completion screen — Close/Cancel | ⏳ LIVE CHECK PENDING (2026-07-23 run: not yet observed) — prior finding: The 'Close' vs 'Cancel' confirmation pop-up on the completion screens isn't finalised in the design yet, so the exact behaviour isn't defined. Needs Milos to confirm what Close and Cancel should do before the case can state a result. | SV-7710 | NOT DONE (Blocked) | DECISION