## Questions for PO
Filters - Questions for Branko - 2026-07-30 (revised again 2026-07-31) - 8 questions
# | Topic | What happens now | The question | Options | Your answer
1 | Mobile: single filter windows - instant or with an Apply button | On a phone, tapping one filter button opens a small window from the bottom. The design pictures show an "Apply filter" button in that window; the engineering plan makes single-filter windows apply INSTANTLY as you tick (no button) - only the combined "All Filters" window keeps an "Apply filters" button. | In the single-filter window on a phone, should choices apply instantly as you tick, or only after tapping an "Apply filter" button? | A) Instantly as you tick, no Apply button (the engineering plan's way). B) Only after tapping an "Apply filter" button (as the design pictures show). | A - no apply button
2 | Which tab opens first | Engineering decided that the very FIRST time someone opens the redesigned Work Orders page, the ESTIMATES tab is selected (even though "All" is the first tab in the row). After that, the page always reopens on the tab you used last. This was decided for speed reasons and is not written down anywhere. | Is Estimates the right tab to open first for a brand-new visit? | A) Yes - Estimates first is fine. B) No - it should open on All (please note: engineering chose Estimates to keep the heaviest list off the landing page; picking B needs a talk with them). | A - it's fine
3 | The Parts "Vendors" page filters | The written description lists a Vendors view among the Parts pages that get filters, but engineering could not find a design picture for it and will not build its filters until a design exists. They have requested the design. | Please confirm the Vendors page IS meant to get filters, and have the design added - or tell us it is out of scope. | A) Vendors gets filters - design coming. B) Vendors is out of scope for now. | Disign for vendors exists in figma. Check it
4 | Sorting the Work Orders list | The design pictures include a sorting panel for the Work Orders list: you pick a column (for example Status, or WO Number), there is a direction box next to it, there is an "Add Sort" option that lets you sort by a second column at the same time, and a "Delete sort" option to remove sorting. The written description does not describe any sorting control at all, so we have no tests for sorting - not one. The sorting pictures are also marked "Work In Progress", which is why we are asking rather than assuming. A sort button also shows on the phone version of the Work Orders page, and on two report pages (Notes and Reminders). Two details we cannot work out from the pictures: (1) once two sorts have been added, the "Add Sort" option is no longer shown - only "Delete sort" is left - so we cannot tell whether two at a time is the intended maximum or simply as far as the picture was drawn; (2) every sort row reads "Ascending", no picture shows a way to switch it the other way round, and the sorted column heading carries no mark, so we cannot tell how someone reverses a sort or whether the sorted column should show any sign that it is sorted. | Is sorting part of this project? If yes: is two sorts at a time the intended maximum; how does someone reverse a sort so it runs the other way, and should the sorted column show a mark; and are the sort buttons on the phone version and on those two report pages included too? | A) Yes - sorting is in scope for this project, including more than one sort level at a time (please add it to the written description, including the maximum number of sorts and how the direction is reversed, so we can write the tests). B) Yes, but single-level only - one column at a time, no "Add Sort". C) No - sorting is not part of this project (the design pictures are exploration only). | C
5 | Which details the new in-page search box looks at | Each list page is getting its own small search box that narrows the list as you type. The written description says each page keeps looking at the same details it already searches today, and it also says the list of those details is still to come from engineering - so right now nobody has written down what each page's search box actually looks at (on Work Orders, for example: the order number? the customer name? the unit number?). Until that list exists we cannot write or run a test that proves the search box looks at the right details - we can only check that typing narrows the list. | Please have that list written down per page and shared with us - or tell us to accept "whatever each page's search finds today" as correct. | A) The list of searchable details will be written down and shared (please say roughly when). B) Accept whatever each page's search finds today - we will only test that typing narrows the list, not which details it matches. | B - *Note - Have Engineering write up that list as technical documentation (not as a blocker for tests, but as a reference document). Tests can work with "typing narrows the list" until the list is complete.
6 | Your latest written description (a request, not a choice) | We now have your latest written description of the filters (version 1.6, updated 28 July) and we are bringing all the tests in line with it. Our earlier copy was the very first version, so for a while we were testing against out-of-date wording without knowing it. | Please confirm version 1.6 is the current one, and let us know each time you change it, so we can re-check the tests straight away. | A) Yes - version 1.6 is current, and I will let you know whenever I update it. B) There is something newer than version 1.6 (please share it). | A
7 | The search box on the page itself, versus the pop-up search | You told us the pop-up search box ("Search or ask a question") should be tested with the global search work, not here - so we have moved those tests out. But the written requirements for THIS project also describe a different search box: a small one that sits on the page's own toolbar. You type in it and the list below narrows, with no separate results window. We have tests written for that page toolbar search box here. | Is that search box on the page toolbar still part of this project? | A) Yes - the search box on the page toolbar stays in this project; only the pop-up search moves to the global search work. B) No - everything to do with searching moves to the global search work, including the search box on the page toolbar. Please note: if the answer is B, a sizeable set of tests we have already written moves out of this project, so we want to be sure before we move them. | A — Toolbar search box is part of this project. These are two completely different functionalities: - Toolbar search = filters the current list/table on the page (inline, no popup) - Global search = searches the entire application (popup, "Search or ask a question") This is not part of this scope, therefore not in the PRD. It is logical that inline filtering of the list goes with filters. The thing that is part of this prd is we have to remove this page search filtering functionality from the global search as right now it is part of it.
8 | Six of the newer filter buttons are never shown opened | You told us the filter behaviour and the filter types are fully shown in the design pictures. For one of them that is exactly right: the Parts "Part type" button is drawn opened, so we can see its choices (Core, Non Core, and a "Clear selection" option) - we have everything we need for that one. For six others the pictures only show the button sitting in the toolbar and never show it opened: Location, Transaction Type, Invoice Status, Type, User and Mention. We have now been through every one of the 85 design pictures, so there is no unopened picture left for us to find. That means a tester cannot tell what happens when one of those six is used - what choices it offers, or what picking one does to the list. | For those six buttons, can we get a one or two line written description of each - what choices it offers, and what happens to the list when you pick one? | A) Yes - a short written description will be added for those six. B) No - treat the design pictures as the source, and ask me about each one as you come to it. | We do not have list of all filter items. we should have all filters we support now per each page plus we should add new ones. For example let's use parts sales page. Currently support only status but we can also have customer, created by and date. We already have those values in the table, we just need to include those as filters.
9 | The Parts and Reports filters — the page-by-page list (a request, not a choice) | Thank you — your written description now covers the Parts and Reports filters, and you confirmed on 17 July that they are part of this release, so we are not asking that again. What is still missing is the page-by-page detail. Your description names the eight Parts pages that get a filter bar, and gives an example of the buttons on two of them (Inventory, and Purchase Orders). It does not say which buttons belong on the other six Parts pages, and it does not name a single report. We have had to read those off the design pictures instead, so our tests are only as reliable as our reading of the pictures. | Please write down, page by page, which filter buttons each Parts page and each report should show — set out the same numbered way the Work Orders filters are. Three points to cover for each: (1) which pages and reports get a filter bar at all; (2) which filter buttons appear on each one; (3) where anything works differently from the Work Orders page. The other rules you have already given us — choices are remembered per page, the same behaviour as Work Orders, and the same buttons for everyone — we have taken as settled and are not re-asking. | A) Yes — a page-by-page list will be added to the written description (please say roughly when). B) No — read the buttons off the design pictures, and we will check each page with you as we test it. | Same as before, we do not have concrete list. If this is really necessary i suggest Engineering + PO together make a list for remaining 6 Parts pages i Reports, using same format as Work Orders do.