## Change list (12)
Fees and Discounts spec-recheck — cases that need a change or a decision (12 of 186).
The other 174 cases need no change (167 Verified, 21 Blocked-on-environment, 1 to re-verify live, 4 retired). Note: the Fees & Discounts V1 stories are still Open in Jira even though the feature is live, so most rows below wait on an open ticket. Nothing pushed to TestRail yet. Orange rows = waiting on a ticket that is NOT yet done.
Case ID | TestRail link | Area | What needs to change | Driving ticket | Ticket status | Action
C28436 | https://shopview.testrail.io/index.php?/cases/view/28436 | Whole-WO Fee/Discount | Confirm which permission controls adding or editing a whole-work-order fee/discount — the build may use one single 'edit work order' check instead of the separate whole-WO and line-level permissions the spec describes. Needs a check on staging with a restricted user. | SV-8277 / SV-8289 | NOT DONE (Open) | DECISION
C28456 | https://shopview.testrail.io/index.php?/cases/view/28456 | Inline display (Lines tab) | On a labour line with two or more fees/discounts the build shows every row and has NO 'Show more / Show less' collapse control the spec asks for. Confirmed difference — decide whether to change the case to match the build or log a fix for the build. | SV-8279 / SV-8288 | NOT DONE (Open) | DECISION
C28460 | https://shopview.testrail.io/index.php?/cases/view/28460 | Statistics tab | The Statistics tab shows fees/discounts as one combined total with no per-item rows, so there is no per-item link to jump to the item. Confirmed difference from the design — decide keep-as-is or log a fix. | SV-8280 | NOT DONE (Open) | DECISION
C28462 | https://shopview.testrail.io/index.php?/cases/view/28462 | Statistics tab | Wording check: the spec says work-order screens list fees/discounts oldest-first (the order they were created); an internal note said newest-first. The case was written to the spec (oldest-first) — confirm the actual order on staging. | SV-8280 | NOT DONE (Open) | DECISION
C30618 | https://shopview.testrail.io/index.php?/cases/view/30618 | Labor-line Fee/Discount | The 'Add Labor Fee / Discount' label is correct, but the three-dot menu shows to the RIGHT of 'Unassigned' and should be on the LEFT. A fix is expected (this is why the ticket re-opened) — re-check the LEFT position on staging, then update the case. | SV-8479 | DONE | Apply update
C28489 | https://shopview.testrail.io/index.php?/cases/view/28489 | Customer Fees & Discounts tab | On the customer Fees & Discounts tab the 'add template' dropdown lists the template NAME only (no Type/Calc/Amount columns), and a Processing Fee shows as 'Fee'. Confirm the accepted display and update the case wording to match the build. | SV-8284 / SV-8285 | NOT DONE (Open) | Apply update
C28490 | https://shopview.testrail.io/index.php?/cases/view/28490 | Customer Fees & Discounts tab | When every template is already linked, the dropdown shows 'No results' instead of the spec's 'No templates available to add.' The product owner accepted 'No results' as-is — update the case's expected message to 'No results'. | SV-8285 | NOT DONE (Open) | Apply update
C28511 | https://shopview.testrail.io/index.php?/cases/view/28511 | Template admin — scoping | On a single labour/part line there is NO 'Apply from template' picker at all, so the template-scoping rule can't be exercised at line level (the picker only exists on the whole work-order dialog). Confirm and adjust the case's scope. | SV-8278 / SV-8281 | NOT DONE (Open) | DECISION
C28526 | https://shopview.testrail.io/index.php?/cases/view/28526 | Processing Fee — WO behavior | A processing fee can't be edited (the backend blocks it), but the work-order ⋮ menu still shows 'Edit ¦ Remove'; the spec wants Remove/Delete only. Decide keep-as-is or log a fix. | SV-8279 / SV-8284 | NOT DONE (Open) | DECISION
C28527 | https://shopview.testrail.io/index.php?/cases/view/28527 | Processing Fee — calculation | The processing-fee amount is worked out on the wrong base — it includes the whole-work-order fees and their tax, when the spec says to leave those out. Confirmed calculation defect — log the fix; the case stays as-is and will correctly fail until it's fixed. | SV-8284 | NOT DONE (Open) | DECISION
C28580 | https://shopview.testrail.io/index.php?/cases/view/28580 | Calculation contract | Same processing-fee base problem as C28527 in the overall calculation check — the grand-total base wrongly includes whole-work-order fees and their tax. Confirmed calculation defect — log the fix. | SV-7865 | NOT DONE (Testing QA) | DECISION
C28586 | https://shopview.testrail.io/index.php?/cases/view/28586 | Permissions (Story 13) | Adding a whole-work-order fee/discount is not blocked by the backend for a user without work-order edit rights (the block is front-end only). Confirm the intended enforcement. | SV-8289 | NOT DONE (Open) | DECISION

## Waiting on open tickets
Cases whose change depends on a ticket that is NOT yet done
These should NOT be finalised until the ticket ships; keep the case tracking the target and re-verify after the fix.
Case ID | TestRail link | Area | What needs to change | Driving ticket | Ticket status | Action
C28436 | https://shopview.testrail.io/index.php?/cases/view/28436 | Whole-WO Fee/Discount | Confirm which permission controls adding or editing a whole-work-order fee/discount — the build may use one single 'edit work order' check instead of the separate whole-WO and line-level permissions the spec describes. Needs a check on staging with a restricted user. | SV-8277 / SV-8289 | NOT DONE (Open) | DECISION
C28456 | https://shopview.testrail.io/index.php?/cases/view/28456 | Inline display (Lines tab) | On a labour line with two or more fees/discounts the build shows every row and has NO 'Show more / Show less' collapse control the spec asks for. Confirmed difference — decide whether to change the case to match the build or log a fix for the build. | SV-8279 / SV-8288 | NOT DONE (Open) | DECISION
C28460 | https://shopview.testrail.io/index.php?/cases/view/28460 | Statistics tab | The Statistics tab shows fees/discounts as one combined total with no per-item rows, so there is no per-item link to jump to the item. Confirmed difference from the design — decide keep-as-is or log a fix. | SV-8280 | NOT DONE (Open) | DECISION
C28462 | https://shopview.testrail.io/index.php?/cases/view/28462 | Statistics tab | Wording check: the spec says work-order screens list fees/discounts oldest-first (the order they were created); an internal note said newest-first. The case was written to the spec (oldest-first) — confirm the actual order on staging. | SV-8280 | NOT DONE (Open) | DECISION
C28489 | https://shopview.testrail.io/index.php?/cases/view/28489 | Customer Fees & Discounts tab | On the customer Fees & Discounts tab the 'add template' dropdown lists the template NAME only (no Type/Calc/Amount columns), and a Processing Fee shows as 'Fee'. Confirm the accepted display and update the case wording to match the build. | SV-8284 / SV-8285 | NOT DONE (Open) | Apply update
C28490 | https://shopview.testrail.io/index.php?/cases/view/28490 | Customer Fees & Discounts tab | When every template is already linked, the dropdown shows 'No results' instead of the spec's 'No templates available to add.' The product owner accepted 'No results' as-is — update the case's expected message to 'No results'. | SV-8285 | NOT DONE (Open) | Apply update
C28511 | https://shopview.testrail.io/index.php?/cases/view/28511 | Template admin — scoping | On a single labour/part line there is NO 'Apply from template' picker at all, so the template-scoping rule can't be exercised at line level (the picker only exists on the whole work-order dialog). Confirm and adjust the case's scope. | SV-8278 / SV-8281 | NOT DONE (Open) | DECISION
C28526 | https://shopview.testrail.io/index.php?/cases/view/28526 | Processing Fee — WO behavior | A processing fee can't be edited (the backend blocks it), but the work-order ⋮ menu still shows 'Edit ¦ Remove'; the spec wants Remove/Delete only. Decide keep-as-is or log a fix. | SV-8279 / SV-8284 | NOT DONE (Open) | DECISION
C28527 | https://shopview.testrail.io/index.php?/cases/view/28527 | Processing Fee — calculation | The processing-fee amount is worked out on the wrong base — it includes the whole-work-order fees and their tax, when the spec says to leave those out. Confirmed calculation defect — log the fix; the case stays as-is and will correctly fail until it's fixed. | SV-8284 | NOT DONE (Open) | DECISION
C28580 | https://shopview.testrail.io/index.php?/cases/view/28580 | Calculation contract | Same processing-fee base problem as C28527 in the overall calculation check — the grand-total base wrongly includes whole-work-order fees and their tax. Confirmed calculation defect — log the fix. | SV-7865 | NOT DONE (Testing QA) | DECISION
C28586 | https://shopview.testrail.io/index.php?/cases/view/28586 | Permissions (Story 13) | Adding a whole-work-order fee/discount is not blocked by the backend for a user without work-order edit rights (the block is front-end only). Confirm the intended enforcement. | SV-8289 | NOT DONE (Open) | DECISION